## Data
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Actual Costs Accumulated | Oct: 1; Nov: 2; Dec: 3; Jan: 4; Feb: 5
Budget (Planned Costs) | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 11 | 13
Earned Value (Tasks Completed) | Oct: 3; Nov: 3; Dec: 3; Jan: 3; Feb: 4
Schedule Variance (Earned - Plan) | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Variance (Earned - Actual) | 2 | 1 | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0