## DRE Table
Phase in which defect is found
|  | Reqmts | Design | Build | Int Test | Acc Test | Prod'n
R
Phase | D
in which | C
Defect | I
Originated | A
| P | [6 empty] | Definitions:
Total defects found in phase |  | 0 | 0 | 0 | 0 | 0 | 0 | This is the total number of defectsfound in this phase, by all the defect-finding activities
Incoming defects from prior phases |  | - | 0 | 0 | 0 | 0 | 0 | These are the defects coming into the particular phase from previous phases (ones that were missed)
Total defects injected in this phase |  | 0 | 0 | 0 | 0 | 0 | 0 | This totals up all the defects found which originated in this phase
Phase-injected escapes |  | 0 | 0 | 0 | 0 | 0 | 0 | This tells how many defects originated in this phase and were not found in this phase (escaped)
Incoming escapes (Pass-throughs) |  | 0 | 0 | 0 | 0 | 0 | 0 | This tells you how many defects originated in previous phases, came into this phase, and were not detected in this phase (escaped)
Overall escapes |  | 0 | 0 | 0 | 0 | 0 | 0 | This tells you how many defects escaped from this phase overall
Phase Containment % |  | - | - | - | - | - | - | This tells you the percentage of defects you were able to contain; that is, how many of the defects which originated in this phase were detected in this phase
DRE % |  | - | - | - | - | - | - | This tells you what was the efficiency of the defect-removal activities conducted in this phase

## Example
|  | Phase in which defect is found | [5 empty] | Instructions
|  | Reqmts | Design | Build | Int Test | Acc Test | Prod'n | Each column represents a life cycle phase.
| R | 21 | 36 | 64 | 128 | 22 | 12 | The cells in each column represent the current phase and the
Phase | D |  | 4 | 3 | 78 | 6 | 2 | previous phases in which defects could have originated.
in which | C |  |  | 5 | 37 | 3 | 3 | Enter into each cell in each column the number of defects
Defect | I |  |  |  | 7 | 3 | 1 | that originated in the particular life cycle phase. For example:
Originated | A |  |  |  |  | 2 | 1 | In the Integration testing phase:
| P | [5 empty] | 0 | 128 defects were found that had originated in the Requirements phase
Total defects found in phase |  | 21 | 40 | 72 | 250 | 36 | 19 | 78 defects were found that had originated in the Design phase
Incoming defects from prior phases |  | - | 262 | 315 | 291 | 52 | 19 | 37 defects were found that had originated in the Build (Construction) phase
Total defects injected in this phase |  | 283 | 93 | 48 | 11 | 3 | 0 | 7 defects were found which had originated in the Integration Test phase
Phase-injected escapes |  | 262 | 89 | 43 | 4 | 1 | 0
Incoming escapes (Pass-throughs) |  | 0 | 226 | 248 | 48 | 18 | 0
Overall escapes |  | 262 | 315 | 291 | 52 | 19 | 0
Phase Containment % |  | 7.42% | 4.301% | 10.42% | 63.64% | 66.67% | -
DRE % |  | 7.42% | 11.27% | 19.83% | 82.78% | 65.45% | 100%