Euromethod
Case Study

EM-2.5-CS

____________________________________

Abstract

This document describes the National Abstract Service and EU-Rent case studies. The National Abstract Service case study defines a chargeable ancillary library service. It provides an abstract searching service with the opportunity to borrow technical journals and reference manuals. The EU-Rent case study is based on the need of a car-rental company to replace its existing computer systems, which are increasingly obsolete, with a new distributed computer system.

The Case Study considers how the Euromethod concepts can be applied in practice. In particular, the Case Study provides examples of how to establish the initial and final states profiles and decision point descriptions within a call for tender document and a tender response document.

____________________________________

© Euromethod Project 1994

This document,

Euromethod Case Study,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod, it constitutes a part of the Guides Level. It makes use of the definitions in all the Guides and Concepts Manuals; and it is used as a source of examples in the other Guides.

ContentsÊofÊtheÊCaseÊStudy

1.	Introduction	6

1.1.	TargetÊAudience	6

1.2.	Scope	6

1.3.	HowÊtoÊuseÊthisÊDocument	7

CaseÊStudyÊI:ÊNationalÊAbstractÊServiceÊ(NAS)	9

2.	TheÊNASÊCaseÊStudyÊContext	9

2.1.	NASÊBusinessÊDescription	9

2.2.	CurrentÊComputerÊSystemÊProblems	12

2.3.	CurrentÊBusinessÊProblems	12

2.4.	SeniorÊManagementÊDecisions	13

3.	PreparationÊofÊtheÊCallÊforÊTender	16

3.1.	AssessmentÊofÊtheÊProblemÊSituation	16

3.1.1.	FinalÊStateÊofÊtheÊIS-adaptation	16

3.1.2.	InitialÊStateÊofÊtheÊIS-adaptation	19

3.1.3.	DefiningÊaÊSequenceÊofÊIS-adaptations	24

3.2.	IS-adaptationÊRequirements	27

4.	PreparationÊofÊaÊTenderÊResponse	28

4.1.	AssessmentÊofÊtheÊProblemÊSituation	29

4.1.1.	TargetÊDomainÊSituationalÊFactors	29

4.1.2.	ProjectÊDomainÊSituationalÊFactors	32

4.1.3.	Risks	35

4.2.	DefinitionÊofÊanÊIS-adaptationÊStrategy	35

4.2.1.	DevelopmentÊApproach	35

4.2.2.	ProjectÊControlÊApproach	37

4.2.3.	RiskÊManagement	37

4.3.	DefinitionÊofÊDecisionÊPoints	40

4.3.1.	SequenceÊofÊDecisionÊPoints	40

4.3.2.	DescriptionÊofÊaÊDecisionÊPoint	42

4.4.	IS-adaptationÊRequirements	44

5.	PreparationÊofÊtheÊSupplierÊSelection	46

6.	PreparationÊofÊtheÊContractÊAwarding	48

7.	TheÊProductionÊandÊCompletionÊProcesses	49

7.1.	WhatÊhappenedÊatÊDecisionÊPointÊ1?	49

7.1.1.	Deliverable:ÊNASÊRequirementsÊStatement	49

7.1.2.	DeliveryÊbyÊtheÊsupplier	52

7.1.3.	DecisionÊmakingÊbyÊtheÊcustomer	52

7.2.	CompletionÊofÊtheÊproject	59

8.	InitialÊStateÊProducts:ÊNASÊSpecifications	60

8.1.	NASÊVolumeÊForecasts	60

8.2.	CurrentÊNASÊOperations	64

CaseÊStudyÊII:ÊEU-Rent	67

9.	TheÊEU-RentÊCaseÊStudyÊContext	67

9.1.	EU-RentÊBusinessÊDescription	67

9.2.	CurrentÊComputerÊSystemÊProblems	69

9.3.	SeniorÊManagementÊDecisions	70

10.	PreparationÊofÊtheÊCallÊforÊTender	71

10.1.	AssessmentÊofÊtheÊProblemÊSituation	71

10.1.1.	FinalÊStateÊProfile	71

10.1.3.	SituationalÊFactorsÊandÊRisks	83

10.2.	DefinitionÊofÊaÊSequenceÊofÊIS-adaptations	87

10.3.	DefinitionÊofÊanÊIS-adaptationÊStrategy	88

10.3.1.	DevelopmentÊApproach	88

10.3.2.	ProjectÊControlÊApproach	89

10.3.3.	RiskÊManagement	90

10.4.	DefinitionÊofÊDecisionÊPoints	92

10.4.1.	IS-adaptationÊregardingÊtheÊCarÊRentalÊSystem	93

10.4.2.	IS-adaptationÊregardingÊtheÊMarketingÊSystem	93

10.4.3.	SequenceÊofÊDecisionÊPoints	93

10.4.4.	DescriptionÊofÊaÊDecisionÊPoint	95

10.5.	ConfirmationÊofÊtheÊSequenceÊofÊIS-adaptations	99

10.6.	TheÊCallÊforÊTender	100

11.	PreparationÊofÊaÊTenderÊResponse	102

11.1.	AssessmentÊofÊtheÊProblemÊSituation	102

11.2.	AmendmentÊofÊtheÊInitialÊStateÊProducts	104

11.3.	EnhancingÊtheÊDeliveryÊPlan	104

11.3.1.	FinalÊStateÊProfile	105

11.3.2.	InitialÊStateÊProfile	105

11.3.3.	DecisionÊPoints	105

11.3.4.	DeliveryÊPlan	110

12.	Initial State Products: EU-Rent Specifications	111

12.1.	EU-RentÊBranchÊandÊDepotÊVolumetricÊDetails	111

12.2.	EU-RentÊOperations	112

12.3.	EU-RentÊInformationÊSupport	115

References	117

Index	118

# 1.	Introduction

This document describes the National Abstract Service and EU-Rent case studies. The National Abstract Service case study defines a chargeable ancillary library service. It provides an abstract searching service with the opportunity to borrow technical journals and reference manuals. The EU-Rent case study is based on the need of a car-rental company to replace its existing computer systems, which are increasingly obsolete, with a new distributed computer system.

The case studies consider how the Euromethod concepts can be applied in practice. In particular, the case studies provide examples of how to establish the initial and final states profiles and a delivery plan both within a call for tender and also within the tender response.

## 1.1.	TargetÊAudience

This document is intended to be used by customer's and supplier's contract and project authorities for IS-adaptations. These are the person or group of persons :

¥	Holding the authority of making contractually binding arrangements for a given procurement;

¥	Having the responsibility for managing the execution of the customer or supplier organisationÕs internal activities related to this procurement.

## 1.2.	Scope

The basic assumptions for the guidance provided by this document are that:

¥	Readers of the Customer, Supplier and Delivery Planning Guides would prefer to be supported by one or more complete examples to understand what the advice presented within those guides means in practice.

¥	Readers of the Customer, Supplier and Delivery Planning Guide will find it useful to have the examples within the context of case studies which are presented in a single, physical document in which the thread of the examples can be traced.

¥	Only limited guidance should be provided to explain the context of the examples in the case studies. Additional support can always be obtained from the other Euromethod guides. References to the other guides and to the concepts manuals are made by arrows and keywords in the margin.

## 1.3.	HowÊtoÊuseÊthisÊDocument

The style utilised in this document, may appear at some points, to look somewhat brief. This is intended, since all the relevant guidance to support the reader's understanding about a particular example within the case studies can be found within the other Euromethod guides.

These case studies thus aim to help the user of the other guides to understand a problem he or she is currently addressing within the other Euromethod guides, by relating that problem to practical examples.

Warning: The Euromethod case studies should not be read in isolation.
Rather, they should be read in conjunction with the Euromethod guides.

In this way, this document intends to help a person determine which step to take next, in order to provide the basis for a decision to be taken during the course of an IS-adaptation.

Furthermore, the style which has been adopted can also be used as a kind of checklist that helps to avoid important activities and their dependencies being forgotten, but still allows the reader to consciously omit those activities which are not considered to be relevant in the situation under consideration.

The complete document is intended to be used by both contract authorities and project authorities in the sense that the guidance provided is relevant to both of them; although the perspective of the two roles is different:

¥	The project authority approaches the document with the point of view: ÒI have to ensure that the required products are delivered to the required qualityÓ. Therefore, the project authority's perspective is to find examples within these case studies which help that person perform a task within the IS-adaptation.

¥	The contract authority approaches the document with the point of view: ÒI have to ensure that the procurement results in a sound contract, giving value for money and that the contract is effectively managed". Therefore, the contract authority's perspective is to understand more about what practical examples look like using Euromethod, and understand how these can help support the decisions that have to be made.

It is recommended that readers of this document who are unfamiliar with the concepts of Euromethod treat the National Abstracting Service case study as the appropriate entry point.

However, it is recommended that readers of this document who are familiar with the concepts of Euromethod, and are more interested in some of the flexible ways in which the Euromethod concepts can be applied treat the EU-Rent case study as the appropriate entry point.

In all cases, 
readers are requested to frequently revisit the appropriate guide to find out what the guidance related to the examples found within this document is.

# CaseÊStudyÊI:ÊNationalÊAbstractÊServiceÊ(NAS)

# 2.	TheÊNASÊCaseÊStudyÊContext

## 2.1.	NASÊBusinessÊDescription

The National Abstract Service (NAS) is part of the public library service of Euland. NAS has been operating for 10 years and provides support to customers by keeping track of technical and scientific publications (books and journals) and holding copies of them for loan.

NAS researchers monitor books and journals in specialised areas of interest (e.g. electronics, computers, telecommunications) and create abstracts on specific topics (e.g. large scale integrated circuits, data storage devices, fibre optic communications) which are stored in an abstracts database. An abstract is a summary of up to 50 words of a paper or article of interest, with a reference to the relevant journal or book, that can be retrieved by topic or by keywords.

NAS employees tend towards two perceptions of what service NAS is providing:

¥	A highly-optimised mechanism for finding out what is available in current scientific and technical publications, based on research expertise in identifying what is important and creating high-quality abstracts that can be easily searched. The provision of the actual publications is an additional service (NAS has them, since it has to buy them to do the abstracting) but many customers use the abstracting service to find out what they want, then get the publications elsewhere (from an in-house library, or they purchase them).

¥	Access to an up-to-date body of reference publications, as and when needed, without the need to purchase them. The abstracting service is a convenient way of indexing the publications, but many customers know what they want and request it without going through the abstracting service.

It is also recognised that some customers use NAS for other purposes; for example, to try out new reference books before deciding which ones to purchase for in-house libraries.

UsersÕ perceptions of NASÕs essential business affect their priorities in what they want from the IS-adaptation.

CurrentÊBusinessÊOperations

NAS has a central research department that monitors what is being published in its areas of interest and decides what to purchase. Researchers analyse the content of the publications and produce abstracts, with keywords for search and retrieval.

NAS has 6 regional branches. Each branch holds copies of the reference books and journals that the research department has decided to purchase; the number of copies will vary according to local demand.

Clients are mainly research departments in commercial companies and academic institutions, some with substantial in-house libraries of their own. Each client is registered with one or more NAS branches, and nominates users at each branch of registration. Only nominated users may use NAS. Although each nominated user has a ÔhomeÕ branch at which his personal details, including his areas of interest, are kept, he may use any NAS branch on production of his identification card.

NAS originally envisaged a two-stage service:

1.	Abstract search:

A user submits a request for a search, either by ÔkeywordÕ or by Ôkeyword within area of interestÕ, which results in a printout of abstracts.

2.	Delivery:

When the user has selected the items he wants, he asks either to borrow books or copies of journals, or for reprints of articles from them. NAS has to maintain records of reprints in order to pay royalties to the copyright owners under reprinting agreements.

In practice, the two parts of the service are not connected. Users can (and do) ask for each part independently. When a user asks for a search and then selects items identified in the search for borrowing or reprint, NAS does not track that the two requests are connected.

Section 8.2 provides details on the current NAS business operations.

Charging

A client organisation pays a registration fee for each branch at which it is registered, and a fee for each nominated user.

There are no charges for abstract searches or borrowing for up to 10 working days, other than postage where appropriate. If borrowed items are not returned by the due date, a penalty is charged. Reprints are charged at a fee per page copied.

CurrentÊComputerÊSystems

Each branch has a local computer system that supports the:

¥	Local registration of clients and users, and recording of user interest in subject areas; collection of annual fees.

¥	A copy of the abstracts database, updated weekly; this is normally accessed by NAS staff but there are facilities for direct access by users from a limited number of terminals in the branch.

¥	Acquisition of new publications.

¥	Production of lists of new abstracts in users' areas of interest.

¥	Borrowing of books and journals by users, including reminders and charges for late returns.

¥	Reprints, including charging for them and the accumulation of royalties due to copyright holders.

¥	Production of monthly statements of charges to clients and receipt of payment for them; statements are itemised and each item is referenced to the user who incurred the charge.

The branch in the capital city has a bigger system that supports two additional functions:

¥	Compilation of the abstracts database.

¥	A clearing service for the cross-charging of services provided by branches to users registered at other branches.

## 2.2.	CurrentÊComputerÊSystemÊProblems

Each branch computer system is based on terminals and a processor with limited disk space. Because of restrictions on disk space, only one yearÕs history of loans and reprints is retained; this limits analysis of change of demand and use of services. No record is kept of abstract searches, which means that no analysis can be made.

The equipment is obsolete and limited in capacity (especially RAM). Hardware failures - screens, disk drives and power supplies - are increasingly frequent.

The application programs have been maintained over several years. Limited RAM and disk space has necessitated intricate, complex programs which makes amendments progressively more difficult and expensive.

Each branch operates almost independently of the others. Communication between locations is mainly by phone and fax and co-ordination is very variable. A publication may be returned to a branch other than the one that owns it for one of two reasons:

¥	Most users use their ÔhomeÕ branches most of the time. But a user may borrow publications from any branch and return them to any branch.

¥	If a user requests a book or journal from his ÔhomeÕ branch that is currently being borrowed, the branch may ask another branch to provide it. If the other branch can provide the publication, it sends it to the users ÔhomeÕ branch, and then charges for the service through the central clearing system (as if the user had borrowed it directly). The user may return the publication to any branch.

But control of return of publications to the branches that own them is poor. This sometimes results in usersÕ being charged for late returns on borrowing when they have already returned the publications, but to branches other than those that own them.

## 2.3.	CurrentÊBusinessÊProblems

¥	Financial return:

Even ignoring any return on the investment in publications, the system runs at a loss. The government of Euland has so far supported NAS as an essential research facility to support EulandÔs industry, but questions about value for money are being raised and there would be substantial resistance to any further subsidy.

¥	Customer perception of cost:

Customers generally see the service as expensive; it costs them about 3,600 ECUs for each branch at which they are registered. NAS staff disagree (see Chapter 8 for figures). Nevertheless, the customer perception is there, and has to be overcome.

¥	Publication base:

The publication base is increasing. Each year 3,000 more reference volumes and 12,000 copies of issues of journals are acquired at each branch. This causes two problems - physical storage and size of database of abstracts. The size of the database has two effects on system performance:

-	The number of ÔhitsÕ for a keyword gets larger each year. This increases processing time and the size of printouts. It also makes it more difficult for users to choose which items to borrow or have reprinted.

-	Users borrow more items because more items are suggested in the printout. This increases handling and administration costs.

Thus, the system throughput is increasing but without opportunity for additional revenue (other than increase of membership fees), since unlimited abstract searches and borrowing of publications are provided without charge to registered users.

¥	Coverage:

The numbers of publications in NASÕs areas of interest are increasing every year. If NAS stays at its current levels of purchasing and research, it is in danger of failing to provide the coverage its clients expect.

## 2.4.	SeniorÊManagementÊDecisions

NAS senior management has decided that a new computer system is needed. Business activity may have to change - there are problems to be addressed and technology opportunities that might be exploited. But whatever happens in the business, the current computer system cannot be kept going much longer. This is the NAS problem situation.

TheÊnewÊNASÊservice:ÊE-MailÊinterface

NAS has carried out a survey among its clients on the acceptability of an E-Mail interface for users to submit their own enquiries and submit reprint and borrowing requests, via a public network. Many clients responded that they would welcome E-Mail for convenience and availability of NAS services outside branch office hours. Indications are that 60% of requests for abstract searches, borrowing and reprints would be submitted via E-Mail, and that abstracts requested via E-Mail could be sent via E-Mail.

The main advantages for NAS are:

¥	Access and network management are provided by the E-Mail network owner.

¥	Many clients already use such networks.

¥	With a batch interface to E-Mail, throughput could be increased and staff could be reduced or reallocated.

NAS management has decided for an E-Mail interface in the new system.

TheÊconsideredÊfutureÊoption:ÊCD-ROM

There are further possibilities for the future. The abstracts database might be made available via a public network for direct browsing (rather than just submitting search requests to be handled by the NAS systems). The number of reference works available on CD-ROM is increasing, as is the number of journals with past issues on CD-ROM. These might be made available directly via the network, although the issues of copyright protection would have to be explored.

However, very large storage capacity is needed and this kind of service is currently not feasible. When the appropriate technology is available and affordable, NAS would like to be well placed to exploit it, and this should be taken into account when developing the required system.

ReviewÊofÊtheÊexistingÊservices:ÊchangeÊ requirements

Although, in general, the existing services shall also be offered by the new system, some slight changes shall be explored, and introduced if considered useful, during the production of the new NAS information system. The requirements to pay special attention to are:

¥	Reduce numbers of old publications:

There are, on average, 7 or 8 copies of each reference book and 12 copies of each journal issue, going back 10 years. Demand is skewed towards recent acquisitions (see Chapter 8).

Space could be saved by reducing the numbers of older publications (not holding copies at every branch). This will require a decision support model that would classify reference titles by level of demand, to determine how many copies should be kept and where (e.g. there is consistent demand for standard reference works, regardless of when they were acquired: there should be copies at every branch).

¥	Offer Ôreprints onlyÕ for journals over, say, 3 years old:

Journals are available on microfiche. Dispose of journals after some period, say 3 years, and keep only microfiche copies, from which reprints can be made. This would be, in effect, a price increase since users can currently borrow copies of journals of any age without charge, but have to pay for reprints.

¥	Offer Ôreprints onlyÕ for all journals:

Take out only one subscription to each journal, with a reprinting agreement. Journals cannot usually be bought on microfiche month-by-month; usually they are provided a yearÕs issues at a time. To obtain journals immediately when they are published, hard copies will have to be bought.

¥	Separate the abstracting service from the lending service:

Cover a wider range of publications in abstract than are actually bought for branches. Buy only the Ôgood betsÕ in advance, and wait and see what demand is before buying the majority of publications. This could cause a substantial deterioration in service for many clients.

¥	Charge more directly for usage:

Reduce the basic subscription and charge for abstract searches and all borrowings. This will require a carefully constructed tariff to ensure that charges are perceived as fair, and a usage accounting system that works at a low level of detail.

# 3.	PreparationÊofÊtheÊCallÊforÊTender

## 3.1.	AssessmentÊofÊtheÊProblemÊSituation

Based on the decision of the NAS senior management (see Section 2.4), the nominated contract authority and the project authority for the envisaged procurement of the required information system, had to analyse the problem situation that they were facing.

Therefore, they had to:

¥	How to prepare the Call for Tender transaction

¥	Document what the senior management decision means, in terms of requirements to the final state of the envisaged IS-adaptation, i.e. final state profiles.

¥	Document what the currently available products contain, in terms of deliverable profiles of the initial state products of the envisaged IS-adaptation.

¥	Decide on the preferred sequence of IS-adaptations based on the understanding of the initial state and the desired final state of the overall IS-adaptation decided by the senior management.

### 3.1.1.	FinalÊStateÊofÊtheÊIS-adaptation

The first goal of the envisaged IS-adaptation stated in the NAS senior managementÕs decision was to get an information system installed, that additionally to the existing services offers an external E-Mail interface for the clients of NAS:

=>	Therefore, all the operational items of the new information system must be produced and installed as a result of the IS-adaptation.

Secondly, the NAS senior management had decided that the system should be able to exploit CD-ROM technology as soon as this is available and affordable:

=>	Therefore, the IS-adaptation must produce the documentation that will be the necessary input to a future IS-adaptation where this will be achieved. That is, the IS-adaptation must produce a complete specification of the computer system architecture view. This specification should be the basis of any extension of the computer system.

=>	As for the future amendment of the system with CD-ROM technology no substantial change to the core computer system is expected (it is even likely that load will be taken off that system), technology independent specifications of the computer system do not seem to have great importance for future IS-adaptations. This means consistent specifications of the computer system data and functions views are not required as an IS-adaptation result; and therefore not considered as part the final state. (Some specifications of this type will probably be delivered for the decision making during the production process. These should not be kept in a consistent state after they have served their purpose, i.e. they are not part of the final state.)

The third goal the NAS senior management wants to achieve is to make the services offered, so far, more cost effective:

=>	The introduced changes shall be documented as a result of the IS-adaptation. As the business processes of NAS are fairly simple, a specification of the work practice view is considered to be sufficient as a result of the IS-adaptation. The only IS-property from within the other information system views that shall be specified is the business rules property.

FinalÊStateÊProfile

The final state profile consisted of the required deliverable profile of the IS-descriptions that should be produced as a result of the IS-adaptation and which the NAS customer wanted to continue to use after the termination of the IS-adaptation:

¥	A specification of the NAS final state information system (see Figure 1).

Deliverable profile:	Final state of the NAS IS-adaptation.

1.	Description of States.

1.1.		Development States:

-	D means detailed development state,

i.e. high degree of decomposition and specialisation.

1.2.		Quality States:

-	QR means that a quality review must have been performed prior to 		the delivery. The review documentation must be complete.

2.	Captured Properties.

2.1.		List of new operational items:

This list may be partially derived from the text in Sections 2.4. 		It must be completed by the customer project authority.

2.2.		Required specification of the NAS final state information system:

Captured properties table: Figure 1.a.

Figure 1: Final state profile of the NAS IS-adaptation.
(Technical specification)

| Required specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the NAS final state information system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business rules | D | QR | Ã |  |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |

Figure 1.a: The required deliverable profile:required ~ of a specification of the NAS final state information system. (Technical Specification)

### 3.1.2.	InitialÊStateÊofÊtheÊIS-adaptation

After having documented the requirements to the final state of the envisaged IS-adaptation, the next thing to do was to produce an inventory of the available inputs to the IS-adaptation and to document it in terms of deliverable profiles;.

The following initial state :~ products were available:

¥	A problem statement document (as presented in Chapter 2):

This document provides an informal statement of the requirements to the future information system (see Section 2.4). It also provides some information that adds to an informal specification of the current information system (see Section 2.1 to 2.3).

¥	System specification documents containing descriptions of the existing computer system:

These documents provide specifications of some IS-properties of the computer system architecture view. Anyhow, most of the descriptions of programs are difficult to interpret because they are incorporated in the source code and describe the implementation rather than the function that is implemented. The following IS-properties are captured:

-	Hardware descriptions,

in terms of technical data are provided in the Hardware Inventory List. The Hardware Manuals provide the descriptions of the hardware interfaces (the scope is partial because some of the manuals got lost).

-	System software descriptions,

in terms of required hardware are given in the Operating System Components List. A description of the interfaces to application software is provided in the System Manuals.

-	Physical data descriptions (of application software),

in terms of file definitions from the Source Code Library.

-	Program descriptions (of application software),

in terms of informal text comments in the source code.

Additionally specifications of some IS-properties of the computer system data and function views are available in the form of entity-relationship and data flow diagrams. But these have not been kept consistent with recent changes to the computer system. The IS-properties that are captured are:

-	Retained data.

-	Static dependencies / relationships.

-	Functions.

-	Input messages.

-	Output messages.

-	Function decomposition.

-	Data access.

¥	Descriptions of existing manual procedures:

These descriptions are basically the texts provided by the on-line help system of the currently operational computer system. They provide an informal specification of some of the IS-properties within the work practice view. Nevertheless, these on-line help texts provide a good understanding of the NAS tasks as they are generally followed. The IS-properties that are captured are:

-	Tasks.

-	Task decomposition.

-	Dynamic dependencies.

The tasks described in the on-line help texts are:

Creating an abstract; recording a new publication; maintaining client; user information; requesting an abstract search; loaning a publication; providing a reprint; sending search results, books, reprints; charging other branch for service to its users; inform on contract terms and conditions; requesting a publication or reprint.

¥	Detailed NAS specifications (see Chapter 8).

These specifications contain specifications of non-functional properties of the initial state information system and requirements to non-functional properties of the final state information system.

Two logical components of the initial state products were recognised according to the deliverable types and the considered contexts (see initial state profile in Figure 2):

¥	Requirements to the NAS final state information system (see Figure 2.a).

¥	Specifications of the NAS initial state information system (see Figure 2.b and the following explanation).

Deliverable profile:	Initial state of the NAS IS-adaptation.

1.	Description of States.

1.1.		Development States:

-	D means 'detailed', i.e. high degree of decomposition and 			specialisation.

-	G means 'global', i.e. not detailed.

1.2.		Quality States:

-	NQ means that 'no quality control' has been performed.

-	NC means 'not consistent' with the current operational system.

-	U means 'up-to-date' with the current operational system.

2.	Captured Properties.

2.1.		List of existing operational items:

This list may be derived from the text in Sections 2.1 to 2.3.

2.2.		Existing requirements to the NAS final state information system:

Captured properties table: Figure 2.a.

2.3.		Existing specification of the NAS initial state information system.

Captured properties table: Figure 2.b.

Figure 2: Initial state profile of the NAS IS-adaptation.

| Existing requirements to | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the NAS final state information system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business rules | G | NQ |  | Ã |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Tasks | G | NQ |  | Ã |  |  | Ã |
| Costs (actors, tasks, information use and gen.) | D | U |  | Ã |  |  | Ã |
| Benefit (computer system) | D | U |  | Ã |  |  | Ã |
| Volume (actors, tasks, information use and gen.) | D | U |  | Ã |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| System software | G | NQ |  | Ã |  |  | Ã |

Figure 2.a: Captured properties table:method ~ ;of the existing requirements to the NAS final state information system. (Technical Specification)

| Existing specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the NAS initial state information system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊinformationÊview |  |  |  |  |  |  |  |
| Information items | G | U |  | Ã |  |  | Ã |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business processes | G | U |  | Ã |  |  | Ã |
| Business rules | G | U |  | Ã |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Actors | G | U |  | Ã |  |  | Ã |
| Tasks | D | U | Ã |  |  |  | Ã |
| Task decomposition | G | U |  | Ã |  |  | Ã |
| Dynamic dependencies | G | U |  | Ã |  |  | Ã |
| ComputerÊsystemÊdataÊview |  |  |  |  |  |  |  |
| Retained data | G | U |  | Ã |  |  | Ã |
| Retained data | D | NC | Ã |  |  | Ã |  |
| Value ranges | G | U |  | Ã |  |  | Ã |
| Static dependencies | D | NC | Ã |  |  | Ã |  |
| ComputerÊsystemÊfunctionÊview |  |  |  |  |  |  |  |
| Functions | D | NC | Ã |  |  | Ã |  |
| Input messages | D | NC | Ã |  |  | Ã |  |
| Output messages | D | NC | Ã |  |  | Ã |  |
| Function decomposition | D | NC | Ã |  |  | Ã |  |
| Data access | D | NC | Ã |  |  | Ã |  |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| Hardware description | D | U |  | Ã |  |  | Ã |
| System software description | D | U | Ã |  |  |  | Ã |
| Physical data description (application software) | D | U | Ã |  |  | Ã |  |
| Program descriptions (application software) | D | U | Ã |  |  |  | Ã |

Figure 2.b: Captured properties table:method ~; of the existing specifications of the NAS initial state information system. (Technical Specification)

BusinessÊinformationÊview:

¥	Information Items,

are informally mentioned in the NAS Problem Statement (Chapter 2) and in the detailed NAS specifications.

BusinessÊprocessÊview:

¥	Business Processes, triggering business events and business rules,

are informally mentioned in the NAS Problem Statement (Chapter 2) and in the detailed NAS specifications.

WorkÊpracticeÊview:

¥	Actors, tasks and organisational structure,

are informally mentioned in the NAS Problem Statement (Chapter 2) and in the detailed NAS specifications.

¥	Tasks,

Detailed informational descriptions of the tasks are provided by the help texts of the on-line help system.

ComputerÊsystemÊdataÊview:

¥	Retained data,

are defined in terms of entities and attributes in the entity-relationship diagrams of the System Specification Documents. They are also informally mentioned in the NAS Problem Statement.

¥	Value ranges,

are informally mentioned in the NAS Problem Statement.

¥	Static dependencies,

are defined in terms of relationships between entities and the assignment of attributes to entities in the entity-relationship diagrams of the System Specification Documents.

ComputerÊsystemÊfunctionÊview:

¥	Functions,

are defined in terms of processes and mini-specs in the data flow diagrams within the System Specification Documents.

¥	Input messages,

are defined in terms of data flows entering a process in the data flow diagrams within the System Specification Documents.

¥	Output messages,

are defined in terms of data originating from a process in the data flow diagrams within the System Specification Documents.

¥	Function decomposition,

is defined in terms of levelled data flow diagrams within the System Specification Documents.

¥	Data access,

is defined in terms of data flows between processes and data stores in the data flow diagrams of the System Specification Documents.

ComputerÊsystemÊarchitectureÊview:

¥	Hardware descriptions, system software descriptions, physical data descriptions and program descriptions,

are described in the System Specification Documents.

Non-functional properties:

¥	Costs, benefits and volumes,

are described in the detailed NAS specifications, see Chapter 8.

### 3.1.3.	DefiningÊaÊSequenceÊofÊIS-adaptations

In their search for an adequate sequence of IS-adaptation:sequence of ~ss to achieve the overall goal of the procurement, the contract and project authority of NAS made use of the Customer GuideÕs guidance on how to identify and reduce risks associated with an IS-adaptation. Due to time scales, resourcing and capability limitations within the customer organisation, they decided to try to avoid performing a detailed assessment of the problem situation.

¥	How to identify and reduce risks in the tendering process

Thus, the first thing they did was to map the initial and final state profiles against the descriptions of typical initial and final states of the Customer Guide. The result of this activity was:

¥	Typical initial and final states

¥	The final state profile could be mapped to the description of the typical final state :typical ~Òinstalled information systemÓ:

From its description, an IS-adaptation ending with this typical final state produces roughly the same results as defined in the final state profile of the NAS IS-adaptation. The differences are:

-	The typical final state does not contain IS-descriptions covering properties from views other than the work practice and the computer system architecture view, whereas the NAS final state additionally contain a specification of the business rules (from the business process view).

-	The typical final state contains requirements statements of the work practice and the computer system architecture view, while these are not required as part of the NAS final state.

Based on these facts, the customer contract authority decided that this was evidence enough to consider the NAS final state as being near to the typical final state Òinstalled information systemÓ. Furthermore, it was decided not to change the NAS final state profile to include requirements statements, as suggested by the typical final state. It was because no substantial change to the core computer system was expected in future IS-adaptations.

¥	The initial state profile could be mapped to the description of the typical initial state :typical ~Òproblem descriptionÓ:

From the descriptions of the typical initial states the available products could not be considered as constituting a Òglobal designÓ. The differences from the typical initial state Òproblem descriptionÓ are:

-	The typical initial state includes global specifications for the business information and process view and requirements statements for the business information and process, the work practice and the computer system architecture view.

-	The NAS initial state includes an informal specification of the work practice view and requirements statements as the typical initial state does, although they might need some improvement.

Based on these facts the customer contract authority decided that the NAS initial state can be considered as being similar to the typical initial state Òproblem descriptionÓ. In particular, the perceived good quality of the informal task specifications and the perceived simplicity of the business processes gave good reason to assume that the informal specifications of the work practice view could substitute for a global specification of the business process view.

The differences from the typical initial state "problem description" may require specific actions in the beginning of the IS-adaptation to improve the initial state products.

Based on this mapping of the NAS initial and final state profiles to the descriptions of the typical initial and final states, the table of critical combinations of initial and final states could be consulted. There, an IS-adaptation starting with Òproblem descriptionÓ and resulting in Òinstalled information systemÓ is marked as containing several risks.

¥	Critical combinations of initial and final states

Thus, some further thought had to be given on whether to split the envisaged IS-adaptation into one starting with Òproblem descriptionÓ and resulting in Òdetailed business designÓ and a subsequent one starting with Òdetailed business designÓ and resulting in Òinstalled information systemÓ, which are both marked as less risky; or whether to issue a call for tender with the current versions of the initial and final state profiles.

Based on the assumption that the IS-adaptation was not complex or uncertain and the goals were clearly known, the customer contract authority finally decided that an IS adaptation with the current versions of the initial and final state profiles was manageable, and thus issued the call for tender document.

## 3.2.	IS-adaptationÊRequirements

The IS-adaptation :~ requirements within the technical specification of the call for tender document consisted of the:

¥	Delivery plan: see Figure 3.

¥	Initial state products: see Section 3.1.2.

¥	Project plans: no project plans were provided.

Delivery Plan:	The NAS IS-adaptation.

1.	Problem Situation

-	A summary of Chapter 2: The NAS case study context.

1.1.		Starting Point: The Initial State of the IS-adaptation

-	A summary of Section 3.1.2: Initial state of the IS-adaptation.

1.2.		Goal: The Final State of the IS-adaptation

-	A summary of Section 3.1.1: Final state of the IS-adaptation.

1.3.		Appreciation of the Problem Situation

-	No analysis of the problem situation is provided.

2.	IS-adaptation Strategy

-	No IS-adaptation strategy is provided.

3.	Decision Points

-	No decisions points are provided.

Annex A.	Initial State Profile

-	Figure 2 and related text.

Annex B. 	Final State Profile

-	Figure 1 and related text.

Annex C. 	Situational Factor Tables

-	No situational factor values are provided.

Annex D. 	Decision Point Descriptions

-	No decision point descriptions are provided.

Figure 3: Contents of a delivery plan for the NAS IS-adaptation
(Technical specification)

# 4.	PreparationÊofÊaÊTenderÊResponse

This chapter of the NAS case study considers an example supplier who, after receiving the NAS call for tender decided to produce a tender response in order to win the IS-adaptation contract.

Because they considered the IS-adaptation the NAS is requesting as relatively simple, the supplierÕs contract and project authority appointed to manage the production of a  Technical Proposal, decided to define the delivery plan based on the in-house methodÕs process model. This method is based on a waterfall process model, and thus assumes one shot construction and installation approaches.

¥	How to prepare the Tender Response transaction

Nevertheless, the supplierÕs contract authority decided to perform an assessment of the problem situation based on the Euromethod Delivery Planning Guide.

¥	How to assess a problem situation

This assessment was intended to achieve two results:

¥	It should confirm the supplierÕs initial judgement that a one-shot construction and installation approach was actually suitable in the NASÕ problem situation.

¥	It should identify the main uncertainties and the related risks, in order to support the choice of the decision points for the production process.

Furthermore, the supplier was aware that he needed to present an understanding of the problem situation. Participating in a Euromethod based tendering process, he could be almost certain that in the evaluation of the Technical Proposals the customer would pay attention to:

¥	A sound justification of the choice of IS-adaptation strategy and sequence of decision points.

¥	The supplier's ability to demonstrate the capability of achieving the IS-adaptation requirements defined in the call for tender document.

## 4.1.	AssessmentÊofÊtheÊProblemÊSituation

### 4.1.1.	TargetÊDomainÊSituationalÊFactors

Figure 4 provides an overview of the supplier organisationÕs perception of the customerÕs problem situation regarding the target domain of the envisaged IS-adaptation. The target domain in this case study was the whole NAS part of the public library service of Euland together with the involved administrations in the NAS client organisations.

¥	Situational factors

Following the figure, you can find the rationales behind the assessment of the situational factors that indicates a complex or an uncertain problem situation.

| Target domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Information System | Heterogeneity of actors |  |  | high | Attitude of actors |  |  | nega-tive |
|  | Size of target domain |  | medium |  | Ability of actors | high |  |  |
|  | Size of distribution |  | medium |  | Stability of environment | high |  |  |
|  | Complexity of information |  | medium |  | Formality of information | high |  |  |
|  | Complexity of business processes |  | medium |  | Formality of business processes | high |  |  |
|  |  |  |  |  | Stability of information and business processes | high |  |  |
|  |  |  |  |  | Specificity of information system |  |  | high |
|  |  |  |  |  | Understandability of existing system | high |  |  |
|  |  |  |  |  | Strategic importance |  |  | high |
|  |  |  |  |  | Importance of organisational changes |  |  | high |
|  |  |  |  |  | Availability, clarity & stability of requirements |  | medium |  |
|  |  |  |  |  | Quality of existing specifications |  | medium |  |
| Computer System | Complexity of data |  | medium |  | Importance of technological changes |  |  | high |
|  | Complexity of functions |  | medium |  |  |  |  |  |
|  | Complexity of non-functional requirements |  | medium |  |  |  |  |  |
|  | Number of replications of computer system |  | few |  |  |  |  |  |
|  | Complexity of target technology |  | medium |  | Novelty of target technology | low |  |  |

Figure 4: Situational factor table for the NAS .
(supplier view)

ComplexityÊofÊtheÊinformationÊsystem:

¥	Heterogeneity of actors:

Actors include branch manager, customer ÔservicerÕ at branch, researcher, publications purchaser, service marketer, financial manager.

UncertaintyÊofÊtheÊinformationÊsystem:

¥	Attitude of actors:

It is apparent that the attitudes of actors will vary depending on their perceptions of NAS services and the options developed, but there will be resistance to any perceived reductions in services in order to reduce costs. There will also be negative responses to possible reductions in branch staff if direct access by users is increased (e.g. via E-Mail).

¥	Specificity of information and business processes:

The current system was developed specifically for NAS. It has some general similarities to other keyword-based abstract services, but the services were developed without regard to how other organisations' services work.

¥	Strategic importance:

This information system is of medium strategic importance to the Euland Library Service, but will form the basis for the entire business strategy of NAS.

¥	Importance of organisational changes:

This system could support or reflect changes in almost every aspect of NAS operations - level of service, costs of service, coverage of domains of interest, storage media for publications, staff, premises, modes of communication (within NAS and between NAS and its users).

UncertaintyÊofÊtheÊcomputerÊsystem:

¥	Importance of technological changes:

Even though the technology itself will not be complex, almost all the benefits of the system will derive from effective use of technology rather than fundamental changes in work practice.

### 4.1.2.	ProjectÊDomainÊSituationalÊFactors

Figure 5 provides an overview of the supplier organisationÕs perception of the customerÕs situation regarding the project domain of the envisaged IS-adaptation.

Again, following the figure, you can find the rationales behind the assessment of the situational factors that indicate a moderate complex or uncertain problem situation.

| Project domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Task | Size of project |  | medium |  | Novelty of IS-adaptation |  | medium |  |
|  | Complexity of migration |  | medium |  | Adequacy of schedules |  | nor-mal |  |
|  |  |  |  |  | Adequacy of budget |  | nor-mal |  |
| Project Structure | Number of sub-contractors | none |  |  | Dependency on sub-contractors | none |  |  |
|  | Number of interfaces to other IS-adaptations | none |  |  | Dependency on other IS-adaptations | none |  |  |
|  |  |  |  |  | Formality of customer-supplier context | high |  |  |
| Project Actors | Number of project actors | small |  |  | Capability of project team |  | medium |  |
| Project Technology | Complexity of develop-ment technology |  | medium |  | Novelty of develop-ment technology |  | medium |  |
|  |  |  |  |  | Availability of appro-priate dev. technology | high |  |  |

Figure 5: Situational factor table for the NAS project domain.
(supplier view)

ComplexityÊofÊtheÊprojectÊtask:

¥	Complexity of migration:

The abstract and delivery services could be installed separately, and installation should be piloted at one branch, i.e. start with an installation with partial geographical coverage.

ComplexityÊofÊtheÊprojectÊtechnology:

¥	Complexity of development technology:

The supplier will use modern development tools - CASE, repository, support for GUI etc., and structured development methodologies.

UncertaintyÊofÊtheÊprojectÊtask:

¥	Novelty of IS adaptation:

The IS-adaptation is expected to be fairly conventional, apart from the possible public communication interface and use of CD-ROM for storage of some publications.

¥	Adequacy of schedules:

The supplier has been informed that while it is urgent to replace the existing systems, NAS management wants a good solution (rather than "get something in as-soon-as-possible") and is prepared for this to be reflected in the schedules.

¥	Adequacy of budget:

The supplier has been informed that NAS management is more interested in cost-benefits than in absolute budgets.

UncertaintyÊofÊtheÊprojectÊtechnology:

¥	Novelty of development technology:

The project team will be generally familiar with the development technology, but it is accepted that they will have to fit the various development tools to local standards and implementation technology.

### 4.1.3.	Risks

The main complexity that has to be managed in the project is:

C.1.	Heterogeneity of actors.

The main uncertainty is related to:

U.1.	Attitude of actors.

U.2.	Specificity of information system.

U.3.	Strategic importance of information system.

U.4.	Importance of organisational changes.

U.5.	Importance of technological changes.

That means, the following risks have to be avoided or contained (risks mentioned in the Delivery Planning Guide related to the uncertainty factors):

¥	Risks

R.1.	IS-adaptation not accepted by actors. (U.1, U.4, U.5)

R.2.	Uncertain or unfeasible requirements to the IS-adaptation. (U.2)

R.3.	Unpredictable costs for the organisation. (U.3, U.4, U.5)

R.4.	There are business implications of IS-adaptation failure. (U.3, U.4)

R.5.	Shortfalls in non-functional requirements. (U.5)

R.6.	Developing wrong or unfeasible information system. (U.1, U.5)

## 4.2.	DefinitionÊofÊanÊIS-adaptationÊStrategy

### 4.2.1.	DevelopmentÊApproach

SystemÊinstallationÊapproach

¥	Development approaches

In determining the installation approach, the following factors were noted:

¥	The problem situation is not complex.

¥	The size of distribution is regarded as small to medium (only 6 branches).

¥	The schedules are normal.

¥	It is feasible to manage the risks associated to the factors implying uncertainty.

From these factors, the supplier proposed the use of a one-shot installation approach with a stepwise installation of the whole information system in the different branches, i.e. only partial geographical coverage in the first installation.

SystemÊconstructionÊapproach

In determining the construction approach, the following factors were noted:

¥	The problem situation is not complex.

¥	The schedules are normal.

¥	It is feasible to manage the risks associated to the factors implying uncertainty.

From these factors, the supplier proposed the use of a one-shot construction approach.

SystemÊdescriptionÊapproach

TheThe supplier proposed to adopt an analytical mode of operation and an expert driven co-operation approach. The justification was that:

¥	The complexity of the situation is moderate.

¥	The situation is certain regarding stability and formality.

¥	The understandability of existing system is high.

¥	The supplier was most experienced in an analytical and expert driven approach. That means, the uncertainty regarding the strategic importance and the importance of organisational changes would be less risky by adopting a well-known approach.

¥	This approach is easier to manage than a more experimental or participatory approach. The approach would be supplemented by some participation of representatives of the actors to handle the complexity and uncertainty implied by the heterogeneity and negative attitude of the actors.

¥	The risks related to the specificity of the information system is reduced because the understandability of existing system is high.

### 4.2.2.	ProjectÊControlÊApproach

The following decisions were taken with regard to the project control approach:

¥	Project control approach

¥	The frequency of the customer-supplier transactions in the development control process should be frequent (thereby helping to address U.4. - Importance of organisational changes is high).

¥	Quality control should be frequent (because the strategic importance of the IS-adaptation is high).

¥	The customer's responsibility should be defined with particular emphasis on the development and quality control of the descriptions with respect to the requirements and business needs, thereby helping to address:

C.1.	Heterogeneity of actors is high.

U.1.	Attitude of actors is negative.

U.3.	Strategic importance of the information system is high.

U.4.	Importance of organisational changes is high.

### 4.2.3.	RiskÊManagement

ManagementÊofÊcomplexity

¥	Risk management

The complexity factor related to the heterogeneity of the actors determined the following additional requirements on the IS-project in order to manage the complexity aspect of the project:

=>	Ask the customer for the nomination of one representative of the actors.

=>	Agree with the actor representative on the presentation to the actors regarding their changed roles in the new system, with particular regard to:

-	The separation of the services for abstract searching and borrowing/reprinting

-	The need for fewer hard copies of journals resulting in fewer borrowings of books and journals and more reprints

-	Email access by users for abstract searches and delivery of results (possibly resulting in fewer branch staff)

-	The requirement to market the services more.

ManagementÊofÊuncertainty

The following was proposed regarding the management of the risks related to the uncertainty factors:

R.1.	IS-adaptation not accepted by actors. (U.1, U.4, U.5)

=>	You should emphasise in the presentation of the new system to the actors that although the service to users may become:

-	more expensive (e.g. have to pay for reprints for journals rather 	than borrowing them at no charge),

-	less convenient (e.g. have to view on microfiche at branch 	rather than borrowing copies of journals),

-	slower (e.g. fewer copies will mean longer waits for high-	demand publications, such as recent issues of journals);

the current system is unsustainable because of pressure on space and rising costs. The changes being made provide the best that can be done for what the clients are prepared to pay, given that the Euland government is not prepared to increase its subsidy.

R.2.	Uncertain or unfeasible requirements to the IS-adaptation. (U.2)

=>	You have to utilise the fact that the understanding of the existing system is high and that the uncertainty regarding the operational system is low.

=>	Functional requirements are very closely based on those of the current system. You need to produce well-documented requirements statements and specifications from them.

=>	The major new requirement will be the E-Mail interface for borrowing and reprint requests and recovery of abstract search results - abstract searches should be similar to the direct access currently provided in branches. Get actor participation.

R.3.	Unpredictable costs for the organisation (U.3, U.4, U.5)

=>	It is important to put focus on the cost calculations in the tender response and during the IS-project. The uncertainty regarding the cost calculations should be decreased as early as possible, i.e. early decision points in the delivery plan regarding costs.

=>	In particular, you need an early investigation of:

-	prediction of the volume of activity that will switch to E-Mail

-	costs of E-Mail: interfaces, connect time, storage, provision of 	standing information

-	costs of hardware and system software to support throughput

-	impact on NAS staff levels

-	savings (and reduced future costs) on publication purchases and 	storage

R.4.	There are business implications of IS-adaptation failure (U.3, U.4)

=>	The risk has been reduced by adopting a well-known development approach.

R.5.	Shortfalls in non-functional requirements (U.5)

=>	The choice of hardware technology should take this risk into account. That means, the customer should choose safe and mature technology either before the start of the tendering process or very early in the IS-adaptation process. The supplier should demonstrate good knowledge about the technology with references to successful installation and usage of the technology. Especially the distribution and communication aspects should be in focus in the planning of the IS-adaptation.

=>	There should be focus on the traceability of the non-functional requirements.

=>	The most important non-functional requirements are:

-	Efficiency in handling throughput:

This depends upon the cost-justification and quality of the 	prediction of how much throughput will be E-Mail-based

-	Usability of the E-Mail interface:

You may need to develop prototypes of the E-Mail interface.

R.6.	Developing wrong information system (U.1, U.5)

=>	The business functionality is well-understood, the issue of most concern to NAS regards the exploitation of technology

=>	The biggest risk linked to the system being unfeasible is the case where the marketing is successful and results in increased throughput, but less volume than is expected moves to E-Mail resulting in NAS staff and number of terminals being unable to cope.

## 4.3.	DefinitionÊofÊDecisionÊPoints

### 4.3.1.	SequenceÊofÊDecisionÊPoints

The sequence of decision points was derived from the supplier's method process model as described in the Method Bridging Guide. The method process model was based on the chosen development approach:

¥	How to derive decision points

¥	One shot installation.

¥	One shot construction.

¥	Analytical and expert driven description.

The main principles in the process model are:

¥	Go from decisions on requirements statements to decisions on specifications.

¥	Go from decisions on business setting to decisions on the technical system.

The method process model was tailored to a stepwise installation approach. The result was the following sequence of decision points:

1.	Requirements (including costs and benefits).

2. 	NAS business processes and work practices.

3. 	Technical architecture of the computer system.

4. 	NAS computer system specification.

5. 	Installation and test plan.

6.	Acceptance test.

7. 	Installation of the system in the first branch.

8.	Installation in all branches.

The schedules of the decision points were presented relatively to the start of the production process as illustrated in Figure 6.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Requirements |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Buss. proc./ work prac. |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Technical architecture |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |
| 4. CS specification |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |
| 5. Installation & test plan |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |
| 6. Acceptance test |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |
| 7. Installation in 1.branch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 8. Installation in all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure 6: The schedules of the decision points in the NAS IS-adaptation.
(Technical Proposal)

### 4.3.2.	DescriptionÊofÊaÊDecisionÊPoint

Figure 7 shows an example of a decision point description.

Decision point:	1.	Requirements.

1.	Purpose
Approval of detailed requirements to the NAS IS-adaptation.

1.1.		Target domain purpose.
	To agree on the complete description of the requirements to the 	information system and to determine the direction of the IS-adaptation.
	This includes an acceptance of the costs and benefits of the IS-	adaptation by the customer management and an agreement on the 	organisational impact by the main actors of the IS.

1.2.		Project domain purpose.
	To control the progress of the project and the plan for the future work.

2.	Deliverables
The following deliverables should support the above mentioned decisions:
¥	Requirements Statement.
¥	Project plans and reports.

3.	Roles involved

¥	Customer roles (should be fulfilled by the customer):

-	Contract authority:

-	Project authority:

-	IS-expertise: user representatives.

-	QA-expertise: user representatives.

¥	Supplier roles:

-	Contract authority: Hans Christian Andersen

-	Project authority: Alice Carroll

-	IS-expertise: key project team members

-	QA-expertise: the QA responsible:

Annex A.	Required deliverable profile: Figure 8.

Figure 7: The contents of the description of decision point 1 in the 
NAS IS-adaptation (Technical proposal).

Required deliverable profile

Decision point:	1.	Requirements

1.	Description of States.

1.1.		Development States:

-	D means 'detailed' development state,

i.e. high degree of decomposition and specialisation.

1.2.		Quality States:

-	QR means that a 'quality review' must have been performed prior 		to the delivery. The review documentation must be complete.

2.	Captured Properties.

2.1.		Requirements to the NAS final state information system.

Captured properties table, Figure 8.a.

2.2.		Project plans and reports.

Captured properties table, Figure 8.b.

Figure 8: Required deliverable profile of deliverables at decision point 1 in the NAS IS-adaptation. (Technical proposal)

| Requirements to the NAS final state information system | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (decision point 1) | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business processes (only new business processes) | D | QR |  | Ã |  |  | Ã |
| Business rules | D | QR |  | Ã |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |
| All non-functional properties | D | QR | Ã |  |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |
| All non-functional properties | D | QR | Ã |  |  |  | Ã |

Figure 8.a: Captured properties table:method ~ ;of the requirements to the NAS final state information system, delivered at decision point 1. (Technical proposal)

| Project plans and reports (decision point 1) | Quality state |
| --- | --- |
| ProjectÊStatus Report |  |
| Deviations from the delivery plan | QR |
| New issues to the project | QR |
| Development Report |  |
| Progress statement | QR |
| Used manpower and cost statement | QR |
| Customer resources actually involved | QR |
| Supplier resources actually involved | QR |
| Development Plan |  |
| Development organisation | QR |
| Tasks, network and schedules | QR |
| Manpower and budget | QR |
| Customer resources to be involved | QR |
| Supplier resources to be involved | QR |
| Input products | QR |
| Infrastructure | QR |
| QualityÊAssurance Plan |  |
| Quality management organisation | QR |
| Quality assurance procedures | QR |
| ConfigurationÊManagement Plan |  |
| Configuration management organisation | QR |
| Change procedure | QR |
| Type of version control | QR |

Figure 8.b: Captured properties table of the project domain deliverable at decision point 1 in the NAS IS-adaptation. (Technical proposal)

## 4.4.	IS-adaptationÊRequirements

The IS-adaptation :~ requirements within the technical proposal of the tender response document consisted of the:

¥	Delivery plan: see Figure 9.

¥	Initial state products: see Section 3.1.2.

¥	Project plans: no project plans were provided.

Delivery Plan:	The NAS IS-adaptation.

1.	Problem Situation
-	The supplier's understanding of the technical specification.

1.1.		Starting Point: The Initial State of the IS-adaptation
	-	The supplier's understanding of the technical specification.

1.2.		Goal: The Final State of the IS-adaptation
	-	The supplier's understanding of the technical specification.

1.3.		Appreciation of the Problem Situation
	-	A summary of Section 4.1: Assessment of the problem situation.

2.	IS-adaptation Strategy
-	A summary of Section 4.2: Definition of an IS-adaptation strategy.

2.1.		Approach to Change Situational Factors
	-	No approach is proposed.

2.2.		Development Approach
	-	Section 4.2.1: Development approach.

2.3.		Project Control Approach
	-	Section 4.2.2: Project control approach.

2.4.		Risk Management
	-	Section 4.2.3: Risk management.

3.	Decision Points
-	Section 4.3.1: Sequence of decision points,
	with justification from the supplier's method.

Annex A.	Initial State Profile

-	Figure 2 (from the technical specification).

Annex B. 	Final State Profiles
-	Figure 1 (from the technical specification).

Annex C. 	Situational Factor Tables
-	Figures 4 and 5.

Annex D. 	Decision Point Descriptions
-	Figures 7 and 8 and similar for the other decision points.

Figure 9: Contents of a delivery plan for the NAS IS-adaptation 
(Technical proposal)

# 5.	PreparationÊofÊtheÊSupplierÊSelection

Prior to the start of the tender evaluation, the NAS Contract Authority made an analysis of NAS requirements for the evaluation team by seeing what operational expertise and organisational authorities were required. In particular, it was confirmed again, that the NAS had neither sufficient resources, nor the depth of operational expertise capability to constitute a competent evaluation team. Accordingly a consultant, with both a strong operational expertise and tendering evaluation background, was sub-contracted to support the NAS's Contract Authority and Project Authority within the tender evaluation.

Firstly, led by their consultant, the tender evaluation team assessed the situational factor values related to the IS-adaptation. The result of this was that the team felt that completing their situational factor matrix had clearly illustrated some perceptions that they had developed through their day-to-day work. That is, some values attributed to several factors were becoming more entrenched (for example, there was increasing concern about the attitude of some of the actors within the information system and about the importance of the organisational changes).

¥	How to prepare the Supplier Selection transaction

Secondly, the team made a re-assessment of the final state for the IS-adaptation, in the light of the discussions that they had had with the suppliers during the time that the suppliers were developing their Technical Proposals. Again, although the NAS's Contract Authority and Project Authority both felt that they now knew more about, for example, electronic mail systems and the uses to which electronic mail could be put, they did not feel that any change was required to the final state required by the IS-adaptation.

Based on this understanding, the evaluation team felt ready to evaluate the Technical Proposals. For the supplier whose Technical Proposal we saw developed in Chapter 4, the following evaluation activities were performed.

Firstly, the team visited the situational analysis developed by the case study supplier. For the most part this was felt to be in line with the understanding held by the evaluation team. However, based on their perception of their own capabilities, they were surprised by the supplier's value for the Quality of Existing Specifications situational factor. They had imagined that their existing specifications would be regarded as having a low quality! Furthermore, they were unclear why the Heterogeneity of the Actors value was regarded as high. An action was taken to carry these forward to the Contract Awarding (if this supplier was selected) to clarify why the supplier had this perception.

The evaluation team was satisfied with the IS-adaptation strategy defined within the Delivery Plan, but the consultant wondered whether an evolutionary approach had been considered. An action was taken to carry this forward to the Contract Awarding (if this supplier was selected) to clarify whether the supplier had sound reasons for proposing a one shot approach rather than an evolutionary approach. The evaluation team were also slightly concerned as to whether they had the available resources and capability to meet the requirements for customer responsibility in the decision point descriptions.

The evaluation team, then reviewed the mappings of the method product profiles to the deliverable profiles. The consultant noticed that the mappings of the method product profiles conformed exactly with the requirements of the decision point descriptions.

Once the evaluation team had completed its evaluation of all the suppliers' Technical Proposals, they had one last meeting in which they calculated the results for all their evaluation criteria. At the end of the meeting, it was agreed that the supplier highlighted within this case study should be selected - subject to the evaluation team obtaining acceptable responses to the concerns highlighted above.

The NAS Contract Authority then informed the selected supplier of his conditional selection, and also informed the unlucky suppliers as to their unsuccessful bids. One supplier demanded to know why their technical proposal had been rejected, and the NAS Contract Authority provided that supplier with a copy of their evaluation result, as they were obliged by the Services Directive [92/50/EEC].

# 6.	PreparationÊofÊtheÊContractÊAwarding

The selected supplier responded quickly to the questions asked by the NAS contract authority, and the tendering process moved on to its final transaction. Because of the legal environment within Euland, no negotiation of the technical proposal was permitted. Consequently, this transaction simply involved the incorporation of the IS-adaptation requirements within the technical specification and the technical proposal into the technical annex of the IS-adaptation contract (see Sections 3.2 and 4.4). Subsequently, the contract was formally signed by the senior management of the two organisations, and the project was ready for launch!

¥	How to prepare the Contract Awarding transaction

# 7.	TheÊProductionÊandÊCompletionÊProcesses

The project has been executed, and the planned deliverables have been produced by the selected supplier to support the decisions identified in the contract delivery plan.

In order to illustrate the production and completion processes we present, in the following section, what has happened in one of the decision points: decision point 1 (see Section 4.3.2).

## 7.1.	WhatÊhappenedÊatÊDecisionÊPointÊ1?

In decision point 1 (see Section 4.3.2), two transactions take place: an Approval of Deliverables transaction and an Approval of Project Status and Plan transaction.

The following deliverables have been delivered by the supplier:

¥	NAS Requirements Statement.

¥	Project status report.

¥	Development report.

¥	Development plan.

¥	Quality assurance plan.

¥	Configuration management plan.

In the following we focus the discussion on the first deliverable: NAS Requirements Statement. This deliverable is given in Section 7.1.1. To make the discussion easier to understand, this deliverable has obvious deficiencies.

### 7.1.1.	Deliverable:ÊNASÊRequirementsÊStatement

This requirements statement to the final state information system has been produced by the supplier and delivered to the customer at the first decision point regarding decisions on the requirements to a future information system. That means, this product is a deliverable within the production process of the IS-adaptation. It should meet the requirements described in the required deliverable profile related to the decision point, see Chapter 4.

DifferencesÊinÊbusinessÊfunctionality

¥	Service to clients:

-	Clients shall be billed for abstract searches and borrowing of publications.

-	Clients shall be able to set a budget per user, and change it as and when they require. A user shall not be permitted to use services costing more than is available in his budget.

¥	Service to users:

-	In addition to the current methods, users shall be able to request abstracts, reprints and borrowing of publications, by E-Mail. Abstracts requested by E-Mail shall be normally delivered by E-Mail.

-	For some abstracts there may be no corresponding publications available for loan; users shall have to obtain the publications elsewhere.

-	Hard copies of journals shall be kept for only one year. After this they shall be kept on microfiche and shall be available only as reprints.

-	Users shall be budget-limited. If a user wants to use a branch other than his 'home' branch, he shall have to sign an indemnity form, accepting responsibility for payment of any charges incurred in excess of his budget.

¥	Abstracts:

-	Abstract searches shall be charged for.

¥	Publications:

No change in functionality, but:

-	Generally only one subscription to each journal. Journals kept in hard copy for only one year, then microfiche.

-	Fewer copies of reference books, based on better decision support information.

¥	Borrowing of publications:

-	Borrowings shall be charged.

-	Fewer borrowings of journals.

-	Borrowing may be requested by E-Mail.

¥	Reprints:

-	More reprints of journals.

-	Reprints may be requested by E-Mail.

¥	Services for other branches:

When items are returned to branches other than those that own them, the receiving branches shall let the owning branches know, by E-Mail, that the items have been received (this shall avoid incorrect late returns charges to users).

CentralÊoperations

(on the larger computer system in the Euland capital branch)

¥	Abstracts:

No change in functionality: some abstracts shall be compiled for books and publications that are not purchased for NAS branches.

¥	Inter-branch charging:

No change in central functionality, but abstract searches and borrowings also charged for at branches.

Non-functionalÊproperties

¥	Volume:

A branch information system needs to be able to handle about 1500 borrowings per week (request & return). The information system as a whole (between central and branches) needs to be able to handle about 22,000 abstract searches and reprint requests per week. A crucial factor is how much of the load shall be switched to E-Mail - input by NAS staff could be a problem. This needs to be investigated further.

¥	Security:

The only significant factor is protection of user identifiers to prevent unauthorised use of users' budgets - this is a fairly common requirement with well-understood solutions.

¥	Criticality:

The most critical component is the abstracts database; it is of moderate size (currently 2M+ abstracts), does not have urgent update requirements, and it can be replicated.

¥	Reliability:

The service is currently available during branch office hours; one of the advantages to E-Mail users is access to the service outside office hours, but it does not have to be 24 hours per day. Also, most of the interaction is 'transaction shipping' rather than conversational, with the E-Mail service acting as a buffer.

¥	Maintainability:

Important - NAS management wants to be well placed to exploit opportunities for electronic publications and electronic distribution when technology becomes available and/or affordable.

¥	Portability:

Not a major issue.

¥	Usability:

Usability of the E-Mail interface is vital for acceptability of the system. However, the NAS-specific interface shall be built on to the well-tried and well-understood interfaces to whatever public networks are selected, and improvements to the NAS-specific interface can be distributed via the networks.

### 7.1.2.	DeliveryÊbyÊtheÊsupplier

The supplier has delivered the deliverables to the customer after having decided that they were meeting the IS-adaptation requirements within the technical annex of the contract.

Not enough attention has been given by the supplier to the guidance provided within Euromethod, to assist him in making that decision. For example, the checklist which allows the supplier to control the content of the method products (Method Products and Deliverable Quality), given in Section 4.1 of the Supplier Guide has not been used. The deliverables have undergone a quality review but they were not reviewed in light of the customer's decision they should support. Consequently, as will be shown, the deliverables will be rejected by the customer thereby causing rework by the supplier.

¥	How do you use Euromethod in the Production Process

### 7.1.3.	DecisionÊmakingÊbyÊtheÊcustomer

The customer has received the deliverables which were specified in the technical annex of the contract for decision point 1. Two transactions are part of that decision: an Approval of Deliverables and an Approval of Project Status and Plan.

#### 7.1.3.1.	Approval of deliverables

The customer has performed the deliverable assessment procedure as explained in 5.1. Approval of Deliverables of the Customer Guide.

For this purpose, the customer has installed a review committee containing persons fulfilling the roles specified for this decision point. This committee has performed the review easily, because the spectrum of needed skills had been well specified and people have been made available for this work when making the delivery plan.

¥	How to use Euromethod in the Production Process

The customer had first to decide whether the received products were in a state to be approved. For this, he has used the checklist on method products and deliverable quality provided by the Customer Guide in Section 5.1.

The result of the NAS Requirements Statement assessment is presented below.

×	Has the purpose of the method product been fully achieved to meet the requirements of this decision point?

No, the product shows major deficiencies which make it unsuitable for the support of the planned decision. These deficiencies are stated in the next points.

×	Is the system (either the current or future) considered by the method products consistent with that specified in the decision point description?

Yes, the product is stating requirements to the NAS final state information system, as specified in the required deliverable profile (see Figure 8).

×	Do the delivered method products cover all of the views required to satisfy the requirements of the decision point description?

No, the required views are not completely covered, as is shown in the next point.

×	Do the method products consider all of the properties (IS-properties, project properties and non-functional properties) required to satisfy the requirements of the decision point description?

No, all the required IS-properties are not considered.

Business process view is acceptable:

-	The business rules are well covered.

-	They are sufficiently detailed.

-	They have undergone a quality review by the supplier.

-	Their scope is partial because they address only the new business processes as required.

-	They are informal as required.

Work practice view is not acceptable:

-	Most IS-properties are not considered:

¡ 	There is no consideration of the actors (except the clients and the 	users of the NAS services).

¡ 	The tasks are not really covered; there is some informal 	requirements on the tasks of the users (use of E-mail, etc..), but 	there is no consideration of the tasks of the internal actors; this is 	a major deficiency and it prevents the product from providing 	the basis for getting the agreement of the concerned actors as 	stated in the purpose of the decision point.

-	The IS-properties, when they are not missing, are insufficiently detailed; they cannot support the decision as stated in Section 4.3.2. It is impossible to determine thoroughly the direction of the IS-adaptation.

-	The IS-properties have undergone a quality review by the supplier; but the effectiveness of the supplier quality procedures can be questioned. These seem to ignore the contractual IS-adaptation requirements.

-	The scope is not full.

-	The IS-properties are not expressed in a semi-formal modelling technique.

Computer system architecture view is not acceptable:

-	Most IS-properties are not considered:

¡	There is no consideration of the processing units, their location, 	the distribution of data and functions among them, etc.

¡	What are the requirements to the hardware and the software? 	What is the consequence of installing an E-mail service on the 	hardware and system software? What kind of impact will it have 	on the application software?

-	The IS-properties, when they are not missing, are insufficiently detailed; they cannot support the decision as stated in Section 4.3.2. In particular, it is impossible to determine the direction of the IS-adaptation and to evaluate the costs and benefits of it.

-	The IS-properties have undergone a quality review by the supplier; but one can question the effectiveness of the supplier quality procedures, which seem to ignore the contractual IS-adaptation requirements.

-	The scope is not full.

-	The IS-properties are not expressed in a semi-formal modelling technique.

Non-functional properties are useful but not acceptable:

-	Two major non functional properties are missing: the costs, and the benefits. These have probably not been estimated because of the lack of information regarding the work practice view and the computer architecture view. Unfortunately, costs and benefits are a major input to the decision of decision point 1!

-	The existing requirements to non-functional properties are convincing; however, it is not clear whether they relate to processes, tasks, the computer system, etc. It is admitted however that this reveals a lack of clarity of the contractual IS-adaptation requirements (see Section 4.3.2) which do not specify which level (system, sub-system, task, etc.) had to be addressed by those non-functional properties.

-	The non-functional properties have undergone a quality review by the supplier.

-	The scope is not full: they are not covering the whole system systematically.

-	They are expressed in an informal way which is what was demanded.

×	Is the development state of the method products consistent with that specified in the decision point description?

No, a lot of IS-properties are either missing or developed with an insufficient level of detail (see previous point).

×	Is the quality state of the method products consistent with that specified in the decision point description?

Formally, yes. But the poor result shows that the supplier's quality procedures are not effective. Therefore, a request should be put on the supplier to improve the quality procedures.

×	Is the deliverable scope of the method products consistent with that specified in the decision point description?

No, the scope is not full as required for the properties of the work practice and computer system architecture views (see above).

×	Does the method product developed correspond with the product glossary specified in the supplier's method product profile for the decision point?

Impossible to assess because the product uses informal techniques.

×	Have all the rules for internal consistency of the method product been observed?

The product is consistent (the requirements do not contradict each other).

×	Has the method product developed demonstrated the supplier's claims about its suitability in this situation?

No, the planned decision cannot be made on its basis.

The result of the assessment of the NAS Requirements Statement has lead to a rejection of this product, thereby entailing rework by the supplier. It has been considered that the product could not provide the adequate basis for an agreement on the direction of the IS-adaptation which is a major purpose of decision point 1. Similarly, the product is not suitable to get an agreement on costs, benefits and organisational impact.

In consequence, some of the main risks of the project have not been reduced (see Section 4.2.3 Risk Management):

R.1.	IS-adaptation not accepted by actors:

The product makes it impossible to get the agreement of the main actors on the IS-adaptation.

R.2.	Uncertain or unfeasible requirements to the IS-adaptation:

Work practice and computer system architecture views requirements are still uncertain.

R.3.	Unpredictable costs for the organisation:

There is no assessment of costs.

R.6.	Developing wrong information system:

There is no clear perception of the requirements on the work practice view.

However, in order to facilitate the IS-adaptation, the customer has taken a positive view on the deliverables, trying to identify which part of the decision could be taken on its basis. The decision in point 1 is a very complex decision which can be sub-divided in partial decisions. In particular, it seemed to the customer that it was worth reaching an agreement on the business rules and the non-functional properties, which were in a good shape, before waiting for the reworked deliverable. The business rules and non-functional properties have been carefully examined by the review committee.

The result of that review was positive with a few amendments:

¥	Service to users: the signing of an indemnity form by the user which wants to use another branch than his home branch, is unpractical.

¥	Portability: is considered as an issue; the customer requests the supplier to use only open systems.

The overall result of the review has then fed the decision on the approval of project status and plans.

#### 7.1.3.2.	Approval of Project Status and Plans

The project status and plans delivered by the supplier have been examined by the customer, using the guidance provided by Section 5.2. Approval of Status and Plan of the Customer Guide.

First, the review committee has checked whether the deliverables were in line with the deliverable profiles of Figure 8.b. The result was positive: all the required project properties were present in the deliverables.

Then, a careful examination of the contents of the deliverables was performed. The one thing that struck the review committee was that the supplier complained about the lack of involvement of customer resources (part of the Development Report). In the Project Status Report, the supplier considered that delivery dates could not be kept because of this problem, and was asking for a Contract Change Control.

The customer agreed on having such a Contract Change Control transaction made even more necessary due to the poor quality of some of the deliverables.

This poor quality questioned the effectiveness of the supplier's quality plan, and the customer decided to request a process improvement from the supplier.

#### 7.1.3.3.	Contract change control

The customer and the supplier agreed to organise a meeting to treat the identified problems, assess the situation and analyse the risks, decide whether the IS-adaptation was still on course, and possibly change the delivery plan and the project plans.

This meeting gathered the two contract authorities and the two project authorities, accompanied by some of their key operational expertise.

The new situation was reassessed, and both the customer and the supplier considered that the IS-adaptation should still be on course. No additional risks had been identified from the beginning of the project, and the original situational factors had not changed.

The reasons for the failure were internal to the project: lack of skills within the supplier's project team, lack of availability of the customer resources and deficiencies in the supplier's quality assurance procedures. Both parties agreed to improve these aspects without delay.

The customer insisted on keeping the final state and the final delivery date unchanged, but agreed that the intermediate decision points could shift in time. An additional decision point should be added for the approval of the reworked deliverables.

The supplier thought that, although the situation had moved towards a tight schedule situation, the proposed IS-adaptation strategy could be kept. He also promised to put his best skills on board, and to improve his quality assurance procedures.

Eventually, this agreement and the revised delivery plan and project plan were considered as an addendum to the original contract. The contract includes indeed a clause on the possibility to revise the plans where both parties agree.

## 7.2.	CompletionÊofÊtheÊproject

In the next decision points, it happened that the supplier improved substantially his performance. The deliverables were produced on time at the required quality. This resulted from an enhancement of the skills of the project team, a substantial involvement of the customer resources, an improvement of the quality procedures, and last but not least from a more confident relationship between the customer and the supplier. The more positive attitude of the users made it possible to involve them, thereby shifting the approach slightly from expert driven to participatory.

All these measures resulted in the acceptance of the next deliverables by the customer, an effective decision making process and finally, the acceptance and the operational success of the final state system.

The final deliverables, in this case, was the installation of the tested system in all branches. i.e. the new computer system, the trained actors and the new organisation in place.

As part of the Contract Completion transaction, financial and technical aspects were phased out. For example, it was checked whether all the documentation and manuals were available to the customer.

The customer and the supplier also decided to have a maintenance contract, to be started after the warranty period where the detected bugs had to be corrected by the supplier.

Both the customer and the supplier recorded their process within the framework of Euromethod, in order to capitalise their experience. This eventually contributed to an enhancement of the maturity of both organisations.

# 8.	InitialÊStateÊProducts:ÊNASÊSpecifications

This chapter contains some of the IS-descriptions available for the IS-production, i.e. some of the initial state products. The products are described in the initial state profile in Chapter 3. The products contain both descriptions of the current information system and forecasts about a future information system.

## 8.1.	NASÊVolumeÊForecasts

NAS has six branches and about 500 clients. Each branch has about 120 clients registered (some clients register at more than one branch) and, on average, 40 users per registered client.

Clients pay 500 ECUs to register at a branch, and 50 ECUs per user. For this they have unlimited abstract searches and publication borrowing for up to 10 days at a time. They are charged for reprints (average 2 ECUs per reprint) and for late returns of borrowed publications (2 ECUs per publication).

The typical pattern of use by a client at a branch is:

480 reprints @ 2 ECUs	960 ECU

penalties for late returns from borrowing	160 ECU

balance	2,500 ECU

other transactions: 600 searches + 800 borrowings = 1,400

cost per search/borrowing	1.79 ECU

Under the proposed new system the following charges will apply:

User registration fee	15 ECU

cost per abstract search	1 ECU

cost per borrowing	2 ECU

cost reprint	2 ECU

cost per late return	2 ECU

Each user will have a budget that he should not be allowed to exceed (although in practice it will be possible to exceed budget by incurring late returns charges).

NAS expect that, under the new charging scheme, clients will register more users. They expect at least 10% and hope for up to 25% increase in users. The tables on the next two pages give current volumes and volumes for the future system at current numbers of users, 10% increase in users and 25% increase in users.

Also, under the new system, only one year' issues of journals will be kept as hard copy. Older issues will be kept on microfiche and available for reprints. This is expected to change the pattern of borrowing and reprints.

Only one subscription will be taken out for most journals; better decision support for anticipated demand is expected to reduce books purchased per branch from 3,000 copies per year to 2,500 copies per year.

|  | current | new: same | new + 10% | new + 25% |
| --- | --- | --- | --- | --- |
| Client registrations per branch | 120 | 120 | 120 | 120 |
| Users per registration | 40 | 40 | 44 | 50 |
| Users registered per branch | 4,800 | 4,800 | 5,280 | 6,000 |
| Publications |  |  |  |  |
| Reference titles per branch | 80,000 | 80,000 | 80,000 | 80,000 |
| Reference volumes per branch | 100,000 | 100,000 | 100,000 | 100,000 |
| Journal titles | 500 | 500 | 500 | 500 |
| Journal subscriptions per branch | 1,000 | 500 | 500 | 500 |
| Journal issue copies per branch | 12,000 | 9,000 | 9,000 | 9,000 |
| Books purchased per year per branch | 3,000 | 2,500 | 2,500 | 2,500 |
| Journal issue copies per year per branch | 12,000 | 6,000 | 6,000 | 6,000 |
| Usage |  |  |  |  |
| Abstract searches per user per year | 15 | 15 | 15 | 15 |
| Abstract searches per branch per year | 72,000 | 72,000 | 79,200 | 90,000 |
| Borrowings per user per year | 20 | 12 | 12 | 12 |
| Borrowings per branch per year | 96,000 | 57,600 | 63,360 | 72,000 |
| Reprints per user per year | 12 | 15 | 15 | 15 |
| Reprints per branch per year | 57,600 | 72,000 | 79,200 | 90,000 |
| Average borrowing (working days) | 12 | 12 | 12 | 12 |
| Item-borrowing days per branch per year | 1,152,000 | 691,200 | 760,320 | 864,000 |
| Item-available days per branch per year | 66,000,000 | 32,700,000 | 32,700,000 | 32,700,000 |
| Availability of publications | 98.25% | 97.89% | 97.67% | 97.36% |

Figure 10: VolumesÊofÊactivity:ÊcurrentÊandÊnewÊsystem.

|  | current | new: same | new +10% | new + 25% |
| --- | --- | --- | --- | --- |
| cost per subscription | 40.00 | 40.00 | 40.00 | 40.00 |
| journals cost per year | 40,000.00 | 20,000.00 | 20,000.00 | 20,000.00 |
| cost per volume | 50.00 | 50.00 | 50.00 | 50.00 |
| books purchase cost per year | 150,000.00 | 125,000.00 | 125,000.00 | 125,000.00 |
| reprints cost per year | 70,000.00 | 87,500.00 | 96,250.00 | 109,375.00 |
| publications cost per branch per year | 260,000.00 | 232,500.00 | 241,250.00 | 254,375.00 |
| Client registration | 500.00 | 500.00 | 500.00 | 500.00 |
| User registration | 50.00 | 15.00 | 15.00 | 15.00 |
| cost per search |  | 1.00 | 1.00 | 1.00 |
| search cost per user | 0.00 | 15.00 | 15.00 | 15.00 |
| cost per borrowing |  | 2.00 | 2.00 | 2.00 |
| borrowing cost per user | 0.00 | 24.00 | 24.00 | 24.00 |
| cost per reprint | 2.00 | 2.00 | 2.00 | 2.00 |
| reprint cost per user | 24.00 | 30.00 | 30.00 | 30.00 |
| late returns penalty per user | 4.00 | 2.40 | 2.40 | 2.40 |
| cost per user | 78.00 | 86.40 | 86.40 | 86.40 |
| income per client | 3,620.00 | 3,956.00 | 4,301.60 | 4,820.00 |
| client income per office | 434,400.00 | 474,720.00 | 516,192.00 | 578,400.00 |
| contribution to overheads | 174,400.00 | 242,220.00 | 274,942.00 | 324,025.00 |

Figure 11: IncomeÊandÊdirectÊcostsÊ(ECUs):ÊcurrentÊandÊnewÊsystem.

## 8.2.	CurrentÊNASÊOperations

The following is a description of the current operations at the branches and in the central computer system. The descriptions are based on a data model which has been developed, but not incorporated in this documentation.

BranchÊoperations

¥	Service to clients.

Clients can register at more than one branch, and nominate an indefinite number of users at each branch.

Clients are billed separately for each branch at which they are registered:

-	Annually , for membership fees.

-	Monthly, for reprints, late returns, postage and addition of new users; statements are itemised and each item is referenced to the user who incurred the charge.

¥	Service to users.

Each user is registered at one branch, but may use any branch on production of his identification card.

Users may invoke three services - abstract searches, publication borrowing and reprints - up to the limit of their budgets.

Each service may be invoked by attending the branch in person or by post. There are two terminals at each branch on which users can make abstract searches directly.

Abstracts, publications and reprints may be collected from the branch, or posted to the user. Borrowed publications may be returned to any branch.

Users' areas of interest are recorded and each month users receive a list of new abstracts in their areas.

¥	Abstracts.

Each branch holds a copy of the abstracts database, and receives an update of it each week from the central system.

Each month, branches send each of their users a list of new abstracts in the user's areas of interest. The list contains author, title and publication, not the text of the abstracts.

¥	Publications.

Each branch holds copies of most of the reference books (currently 80,000 titles, some with multiple copies) and journals (500 titles, some with multiple subscriptions, with issues going back over 10 years) that the research department has decided to purchase, although the number of copies may vary according to local demand.

A branch may request purchases. If central research agrees (the deciding factor is the effort needed to create abstracts, rather than purchase cost), other branches are polled to see if they also want copies.

As new books are purchased, each copy is given an unique identifier, which includes the identifier of the branch it belongs to.

¥	Borrowing of publications.

Users normally borrow books from their home branches, but may use any branch. When a user requests loan of a book or an issue of a journal, then if the publication is available, the branch will provide it on a 10-day loan, and record the loan in the computer system.

If it is already on loan, the branch will check when it is due for return and ask the user if he is prepared to wait for it; if so, the user can reserve it.

If the user does not want to wait, the branch will contact other branches to see if they have it available; if available, it can usually be posted to the user to arrive the following day.

If a reserved item is not collected within two days the reservation is cancelled.

A user can extend the borrowing of a book or publication by further 10-day periods, by phone or in person, provided that nobody else has reserved it. If a borrowed item is not returned at the end of its loan period and no extension has been arranged, the user is charged a late return penalty (currently 2 ECUs); this charge is repeated every 10 days until the item is returned.

If a user returns a borrowed item to a branch other than the one that owns it, the item is then sent to its owner branch.

¥	Reprints.

Reprints may be requested by post or in person at a branch, and may be collected or posted.

Reprints are made at branches; each one is recorded in the computer system; the client is charged for the reprint and counts of reprints are sent to the central system for calculation of royalties due to copyright owners.

¥	Services to other branches.

When a branch provides services to a user registered at another branch, it records his user number and branch (both on his identification card). At the end of each week, a summary of these services is sent to the central system, which directs the charges to the appropriate branches, for charging to clients.

When items are returned to branches other than those that own them, the receiving branches send them to the owning branches. The owning branches do not know what has happened until the items arrive.

CentralÊoperations

(on the larger computer system in the Euland capital branch)

¥	Abstracts.

Researchers compile abstracts, identifying keywords and subject areas. As new abstracts are created, they are recorded in a master abstracts database, of which there is a copy in each branch.

Each week, an update of the abstracts database is sent to each branch.

¥	Inter-branch charging.

Each week, each branch submits details of all services provided to users of other branches. They are regrouped to produce a file for each branch of all services provided to its clients by other branches. Only reprints and postage are charged to clients, but details of all services are recorded, for usage statistics for management.

# CaseÊStudyÊII:ÊEU-Rent

# 9.	TheÊEU-RentÊCaseÊStudyÊContext

This case study addresses the use of Euromethod in an open tendering process. Within the call for tender, the customer therefore provides the following documentation of the requirements to the IS-adaptation:~ requirements within the Technical Specification of the call for tender document (and thereby remains in line with the Services Directive [92/50/EEC]):

¥	Initial state products.

(the requirements to the contents of the IS-adaptation products)

¥	A delivery plan with the contents defined in Euromethod (see FigureÊ20) (the requirements to the IS-adaptation process):

¥	The Delivery Plan

-	Final state profiles in Euromethod deliverables profile terminology.

-	Initial state profiles in Euromethod deliverables profile terminology.

-	IS-adaptation strategy using the Euromethod terminology.

-	Decision points with the contents defined in Euromethod: sequence, target domain purpose, project domain purpose, deliverable profiles and roles involved.

## 9.1.	EU-RentÊBusinessÊDescription

EU-Rent is a car rental company. It is one of three businesses owned by the EU-Corporation; the other two being hotels and an airline. These are run as separate businesses and operate their own computer systems. However, they share a common customer base. Consequently, many of the car rental customers also fly EU-Fly and stay at EU-Stay hotels.

EU-Corporation are considering whether to manage customers at corporate level. Even if customers are not stored in a single shared database, it makes sense for all three business areas to have consistent customer information on current address, telephone number, credit rating etc. It will be useful to know in each company when there are problems with a customer in other companies. And it may be possible to run promotions in one company, based on what EU-Corporation knows from the other companies about customers.

EU-Rent operates in many towns all over Europe, from 1000 branches of three types:

¥	Branches in major airports:

There are 100 of these, each of which manages an average of 700 cars. The average number of rentals per airport branch per week is 1350.

¥	Branches in major cities:

There are 200 of these, each of which manages an average of 375 cars. The average number of rentals per major branch per week is 750.

¥	Branches in local agencies such as hotels or garages:

There are 700 of these, each of which manages an average of 80 cars. The average number of rentals per local agency per week is 165.

EU-Rent has 400 service depots for car maintenance and repairs. Each branch is served by a single service depot; a service depot will usually serve more than one branch.

The computer system keeps records of 500,000 customers and their rentals and of comments about bad experiences with customers which can be used to decide whether to approve a rental.

The EU-Rent company is characterised by the following business processes:

¥	Car rentals:

The process of renting cars to customers.

¥	Branch car pool management:

The process of managing the numbers of cars held by each branch.

¥	Management of car transfers between branches:

The process of managing the movement of cars between branches.

¥	Transfer of cars between branches:

The process of transferring cars between branches.

¥	Car maintenance:

The process of maintaining the cars by the service depots.

¥	Administration:

The process of maintaining basic information about the branches and service depots at head office.

## 9.2.	CurrentÊComputerÊSystemÊProblems

At the current time, EU-Rent is a moderately successful car rental business in 1000 locations across Europe, as described in the general EU-Rent description, but with two problems:

¥	Each branch and service depot has a local computer system based on PCs and a file server. The equipment is obsolete and limited in capacity (especially memory). Hardware failures i.e. screens, disk drives and power supplies etc. are increasingly frequent.

The application programs have been maintained over several years. Small memory in the PCs has necessitated intricate, complex programs which makes amendments progressively more difficult and expensive.

¥	Each location operates almost independently of others. Communication between locations is mainly by phone and fax and co-ordination is very variable. Sometimes, when a car is dropped off at a branch different from the pick-up branch, the drop-off branch will not inform the pick-up branch. Branch managers tend to co-operate in small groups and not to look for ÔspareÕ cars outside those groups. EU-Rent management feels that some capacity is wasted, but does not have reliable estimates of how much.

¥	Scheduling of service bookings in branch and service depot files is co-ordinated by faxes between branch and depot. Sometimes service bookings are not recorded in the branch files, and cars booked for servicing are rented. Service depots sometimes do not get to know that cars have been transferred to branches served by other depots until another depot requests service history.

¥	A copy of the customer blacklist is held at every branch. It should be updated every week from head office, but the logistics of updating the list with input from 1000 sources and sending out 1000 disks every week are beyond head officeÕs capability. Updates are in fact sent out about every four weeks.

## 9.3.	SeniorÊManagementÊDecisions

EU-Rent management has decided that a new information computer system is needed and that the information system as a whole shall be revised. It has been decided that the IS-adaptation is to be performed by an external supplier.

As a result of the IS-adaptation, EU-Rent's business activity is not expected to change significantly, i.e. locations, volume and pattern of rentals, staff are expected to remain about the same as at present. The new system is justified on two grounds:

¥	The current computer system cannot be kept going much longer.

¥	Better management of numbers of cars at branches and better co-ordination between branches is expected to increase utilisation of cars slightly i.e. the same volume of business should be supportable with fewer cars. Each car ties up about 8,000 ECUs in capital and loses about 3,000 ECUs in depreciation, so significant savings are possible from small reductions in numbers of cars needed.

The target domain of the EU-Rent IS-adaptation is the whole EU-Rent organisation. After the current computer system has been replaced, EU-Rent management wants to explore possibilities of using customer data from the hotel and airline systems for promotion of car rentals. A frequent userÕ incentive scheme is also under consideration.

Therefore, the target domain of the envisaged IS-adaptation is split into two sub-systems within one IS-adaptation:

¥	The Car Rental system;

which shall support the operation of the day to day car rental business.

¥	The Marketing system;

which shall support the incentive scheme.

# 10.	PreparationÊofÊtheÊCallÊforÊTender

This chapter shows how the customers contract and project authority perform the preparation of the Call for Tender. It describes the activities they perform, the decisions they make, including the rationales of the decisions, and the documents they produce.

## 10.1.	AssessmentÊofÊtheÊProblemÊSituation

The purpose here is to start the production of the call for tender. This is achieved by the production of the following elements of a Delivery Plan:

¥	How to prepare the Call for Tender transaction

¥	Final state profiles (a set of required deliverable profiles).

¥	Initial state profiles (a set of method deliverable profiles).

¥	Situational factors and risks (tables of factors and a list of risks).

### 10.1.1.	FinalÊStateÊProfile

At this stage, the desired final state profile is related to the final states of the two sub-systems:

¥	Car Rental system.

¥	Marketing system.

FinalÊstateÊofÊtheÊEU-RentÊIS-adaptationÊ(CarÊrentalÊsystem)

It was decided (See Section 9.3) that the final state of the Car Rental system should consist of the:

¥	New operational items in the final state information system.

¥	A specification describing the IS-properties of the final state information system.

The requirements to the new operational items are described in the initial state products.

¥	How to document deliverable profiles

The final state profile consists of the required deliverable profiles of the (see Figure 12 and the related explanation):

¥	New operational items.

¥	Specification of the final state information system.

Deliverable profile:

Final state of the EU-Rent IS-Adaptation (Car rental system).

1.	Description of States

1.1.		Development States: 
	-	D means detailed development state, i.e. high degree of 				decomposition and specialisation.

1.2.		Quality States: 
	-	QR means that a quality review must have been performed prior to 		the delivery. The review documentation must be complete.

2.	Captured Properties

2.1.		List of new operational items.

This list may be partially derived from the text in Section 9 and 14; 		it must be completed by the customer project authority.

2.2.		Specification of the final state Car Rental information system

Captured properties table: Figure 12.a.

Figure 12: Final state profile of the EU-Rent IS-adaptation 
(Car rental system) (Technical specification).

| Specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the final state Car Rental information system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊdataÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties | D | QR | Ã |  |  | Ã |  |

Figure 12.a: Captured properties table for the specification of the final state Car Rental information system. (Technical specification)

The rationale for requesting these IS-properties in the final state is:

¥	Work practice view:

These properties must be maintained during the lifetime of the IS-adaptation. This will ensure that the specification of the future work practices accurately reflects the tasks, actors, their responsibilities and the information resources needed at the end of the IS-adaptation. Secondly, it must be in a suitable condition to permit the traceability of the requirements (regarding all the work practices properties) as part of the approval of the final deliverables.

¥	Computer system data view:

These properties must be maintained during the lifetime of this IS-adaptation. This will ensure that the specification of the computer system data properties are accurate in order to support the development of the marketing system within any future IS-adaptation. Secondly, it must be in a suitable condition to permit the traceability of the requirements (regarding all the computer system data properties) as part of the approval of the final deliverables.

¥	Computer system architecture view:

These properties must be maintained during the lifetime of the IS-adaptation. This will ensure that the specification of the computer system accurately reflects the structure of and the processing units in the computer system at the end of the IS-adaptation. Secondly, it must be in a suitable condition to permit the traceability of the requirements (regarding all the computer system architecture properties) as part of the approval of the final deliverables.

FinalÊstateÊofÊtheÊEU-RentÊIS-adaptationÊ(MarketingÊsystem)

The EU-Corporation management have decided that the final state of the Marketing system shall consist of a prototype of the future Marketing system, plus the associated specifications and requirements statements.

The following IS-descriptions must be produced during the IS-project:

¥	Requirements to a future Marketing system.

¥	Specification of a future Marketing system.

¥	Prototype of a future Marketing system.

The final state profile regarding the Marketing IS-adaptation consists of the required deliverable profiles of those IS-descriptions (see Figure 13 and the related explanations).

Deliverable Profile:

Final state of the EU-Rent IS-Adaptation (Marketing system).

1.	Description of States

1.1.		Description of Development States: 
	-	D means "detailed", i.e. high degree of decomposition and 			specialisation.
	-	G means "global", i.e. not detailed.

1.2.		Description of Quality States: 
	-	QR means that a quality review must have been performed prior to 		the delivery. The review documentation must be complete.
	-	QU means reviewed and accepted by user representatives.

2.	Captured Properties

2.1.		Requirements to a future Marketing system.
		Captured properties table: Figure 13.a.

2.2.		Specification of a future Marketing system.
		Captured properties table: Figure 13.b.

2.3.		Prototype of a future Marketing system.
		Captured properties table: Figure 13.c.

Figure 13: Final state profile of the EU-Rent IS-adaptation 
(Marketing system). (Technical specification)

| Requirements to | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a future Marketing system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊinformationÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |
| ComputerÊsystemÊdataÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |
| ComputerÊsystemÊfunctionÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties and related non-functional properties | G | QR | Ã |  |  |  | Ã |

Figure 13.a: Captured properties table for the Requirements to a future Marketing system. (Technical specification)

The requirements statement must be developed for two purposes. Firstly, it should record all new requirements identified during the IS-adaptation; and secondly, it must be in a suitable condition to permit the traceability of the requirements (regarding all the IS-properties) within all the specifications and prototypes produced as part of the IS-adaptation.

All the main requirements should be described with full coverage, but a global development state is sufficient to support the decisions on the further development of the Marketing system in future IS-adaptations.

| Specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a future Marketing system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| All IS-properties | G | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊdataÊview |  |  |  |  |  |  |  |
| All IS-properties | G | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊfunctionÊview |  |  |  |  |  |  |  |
| All IS-properties | G | QR | Ã |  |  | Ã |  |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties | G | QR | Ã |  |  | Ã |  |

Figure 13.b: Captured properties table for the Specifications of a future Marketing system. (Technical specification)

The specification of a future Marketing system should support the further development of the Marketing system within any future IS-adaptation. The changes of the Marketing system are mainly concerned with an enhancement of the computer system and an efficient usage of a new version of the computer system. Therefore:

¥	A specification of all work practice properties and computer system properties must be produced and maintained during the lifetime of this IS-adaptation. The computer system data properties must be consistent with the computer system data properties of the Car Rental system.

¥	The specification should focus on the overall design of the Marketing computer system in order to make decisions on the overall design of efficient marketing work practices. This will also provide a flexibility in the detailed design of the work practices and the computer system. That means, a global development state is required.

¥	The specification must have full coverage and be semiformal to permit the traceability of the requirements as part of the approval of the final deliverables.

¥	A quality review must have been performed prior to delivery and the review documentation must be complete.

| Prototype of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a future Marketing system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Tasks | G | QU |  | Ã | Ã |  |  |
| Task rules | G | QU |  | Ã | Ã |  |  |
| Computerisation | G | QU |  | Ã | Ã |  |  |
| Task decomposition | G | QU |  | Ã | Ã |  |  |
| Information use and generation | G | QU |  | Ã | Ã |  |  |
| Dynamic Dependencies | G | QU |  | Ã | Ã |  |  |
| Triggering conditions | G | QU |  | Ã | Ã |  |  |
| Static human-computer interface | G | QU |  | Ã | Ã |  |  |
| Behaviour of the human-computer interface | G | QU |  | Ã | Ã |  |  |
| ComputerÊsystemÊfunctionÊview |  |  |  |  |  |  |  |
| Functions | G | QU |  | Ã | Ã |  |  |
| Input messages | G | QU |  | Ã | Ã |  |  |
| Triggering conditions | G | QU |  | Ã | Ã |  |  |
| Output messages | G | QU |  | Ã | Ã |  |  |
| Function rules | G | QU |  | Ã | Ã |  |  |
| Data access | G | QU |  | Ã | Ã |  |  |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| External Communication | G | QU |  | Ã | Ã |  |  |
| Locations | G | QU |  | Ã | Ã |  |  |
| Function distribution | G | QU |  | Ã | Ã |  |  |

Figure 13.c: Captured properties table for the prototype of a future Marketing system. (Technical specification)

The rationale for requesting these IS-properties in the final state is:

¥	The human-computer interface should be prototyped to assess whether the specification of the future Marketing system is appropriate for the development of a new Marketing system. Secondly, the prototype must be in a suitable condition to demonstrate the design of a future Marketing system to a broader audience.

¥	A global development state and partial coverage (representative subset) is sufficient to fulfil the above mentioned purpose.

### 10.1.2.	InitialÊStateÊProfile

At this stage, the initial state profile (Figure 14) consists of the method deliverable profile for the:

¥	Specification of the current Car Rental system.

¥	Requirements to a future Car Rental system.

¥	Specification of a future Car Rental system.

The properties of the current information system are described in textual form within the following initial state products:

¥	EU-Rent business description (See Section 9.1).

¥	Current EU-Rent computer system problems (see Section 9.2).

¥	EU-Rent branch and depot volumetric details (See Section 12.1).

¥	EU-Rent Operations (See Section 12.2).

The requirements to (and specifications of) a future information system are described in textual form within the above mentioned initial state products and augmented by the following initial state products:

¥	EU-Rent senior management decisions (see Section 9.3).

¥	EU-Rent information support (see Section 12.3).

The initial state profile for the Car rental system is given in Figure 14.

For the Marketing system, there is only an informal problem description.

Deliverable profile:

Initial state of the EU-Rent IS-adaptation.

1.	Description of States

1.1.		Description of Development States: 
	-	D means "detailed", i.e. high degree of decomposition and 			specialisation.
	-	G means "global", i.e. not detailed.

1.2.		Description of Quality States: 
	-	QP means that a peer group proof reading has been performed. 
	-	NQ means that no quality control has been performed.

2.	Captured Properties

2.1.		Existing specification of the current Car Rental system.
		Captured properties table: Figure 14.a.

2.2.		Existing requirements to the final state Car Rental system
		Captured properties table: Figure 14.b.

2.3.		Existing specification to the final state Car Rental system
		Captured properties table: Figure 14.c.

Figure 14: Initial state profile of the EU-Rent IS-adaptation.
(Technical specification)

| Existing specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the current Car Rental system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Actors | G | QP |  | Ã |  |  | Ã |
| Locations | G | QP |  | Ã |  |  | Ã |
| Communications | G | QP |  | Ã |  |  | Ã |
| Tasks | G | QP |  | Ã |  |  | Ã |
| Computerisation | G | QP |  | Ã |  |  | Ã |
| Performer | G | QP |  | Ã |  |  | Ã |
| Manager | G | QP |  | Ã |  |  | Ã |
| Triggering organisational events | G | QP |  | Ã |  |  | Ã |
| Triggering conditions | G | QP |  | Ã |  |  | Ã |
| Generated organisational events | G | QP |  | Ã |  |  | Ã |
| Task decomposition | G | QP |  | Ã |  |  | Ã |
| Dynamic dependencies | G | QP |  | Ã |  |  | Ã |
| Task rules | G | QP |  | Ã |  |  | Ã |
| Information use and generation | G | QP |  | Ã |  |  | Ã |
| Resources | G | QP |  | Ã |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| All IS-properties | G | NQ |  | Ã |  |  | Ã |

Figure 14.a: Captured properties table of the existing specification of the current Car Rental system. (Technical specification)

The information provided by the initial state products is:

¥	Work practice view:

The initial state products provide partial coverage of all the IS-properties of the work practice view except for the organisational structure, non-functional properties, and access needs and rights of the actors. Further details are required for several of the properties, such as task allocation to specific actors (performer and manager).

¥	Computer system architecture view:

The description of the computer system architecture view on the current computer system is in a poor state, since the current state documents address this area only in a very limited way. Details regarding the nature of the current computer system needs to be improved.

| Existing requirements to | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the final state Car Rental system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊinformationÊview |  |  |  |  |  |  |  |
| Information items | G | QP |  | Ã |  |  | Ã |
| Non-functional properties of information items | G | QP |  | Ã |  |  | Ã |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business processes | G | QP |  | Ã |  |  | Ã |
| Business rules | G | QP |  | Ã |  |  | Ã |
| Triggering conditions | G | QP |  | Ã |  |  | Ã |
| Information use and generation | G | QP |  | Ã |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Actors | G | QP |  | Ã |  |  | Ã |
| Locations | G | QP |  | Ã |  |  | Ã |
| Communications | G | QP |  | Ã |  |  | Ã |
| Tasks | G | QP |  | Ã |  |  | Ã |
| Computerisation | G | QP |  | Ã |  |  | Ã |
| Performer | G | QP |  | Ã |  |  | Ã |
| Manager | G | QP |  | Ã |  |  | Ã |
| Triggering organisational events | G | QP |  | Ã |  |  | Ã |
| Triggering conditions | G | QP |  | Ã |  |  | Ã |
| Generated organisational events | G | QP |  | Ã |  |  | Ã |
| Task decomposition | G | QP |  | Ã |  |  | Ã |
| Dynamic dependencies | G | QP |  | Ã |  |  | Ã |
| Task rules | G | QP |  | Ã |  |  | Ã |
| Information use and generation | G | QP |  | Ã |  |  | Ã |
| Resources | G | QP |  | Ã |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| Processing units | G | QP |  | Ã |  |  | Ã |
| Locations | G | QP |  | Ã |  |  | Ã |
| Data distribution | G | QP |  | Ã |  |  | Ã |
| Function distribution | G | QP |  | Ã |  |  | Ã |
| Non-functional properties | G | QP |  | Ã |  |  | Ã |

Figure 14.b: Captured properties table of the existing requirements to the final state Car Rental system. (Technical specification)

| Existing specification of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| the final state Car Rental system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| BusinessÊprocessÊview |  |  |  |  |  |  |  |
| Business processes | G | QP |  | Ã |  |  | Ã |
| Business rules | G | QP |  | Ã |  |  | Ã |
| Triggering conditions | G | QP |  | Ã |  |  | Ã |
| Information use and generation | G | QP |  | Ã |  |  | Ã |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Actors | G | QP |  | Ã |  |  | Ã |
| Locations | G | QP |  | Ã |  |  | Ã |
| Communications | G | QP |  | Ã |  |  | Ã |
| Tasks | G | QP |  | Ã |  |  | Ã |
| Computerisation | G | QP |  | Ã |  |  | Ã |
| Performer | G | QP |  | Ã |  |  | Ã |
| Manager | G | QP |  | Ã |  |  | Ã |
| Triggering organisational events | G | QP |  | Ã |  |  | Ã |
| Triggering conditions | G | QP |  | Ã |  |  | Ã |
| Generated organisational events | G | QP |  | Ã |  |  | Ã |
| Task decomposition | G | QP |  | Ã |  |  | Ã |
| Dynamic dependencies | G | QP |  | Ã |  |  | Ã |
| Task rules | G | QP |  | Ã |  |  | Ã |
| Information use and generation | G | QP |  | Ã |  |  | Ã |
| Resources | G | QP |  | Ã |  |  | Ã |

Figure 14.c: Captured properties table of the existing specification of the final state Car Rental system. (Technical specification)

The information provided by the initial state products is:

¥	Business process view:

The initial state products describe one new business process: management of cars based on data from the new computer system.

¥	Work practice view:

As for the specification of the current system, the initial state products provide partial coverage of all the IS-properties of the work practice view on the new system except for the organisational structure, non-functional properties, and access needs and rights of the actors. The specification of communications and computerisation in the current system is only partly relevant as a specification of the new information system, because of the change of the computer system. Further details are required for several of the properties, such as task allocation to specific actors (performer and manager).

### 10.1.3.	SituationalÊFactorsÊandÊRisks

For the further analysis the Car Rental system is decomposed into two sub-systems. The information system is thus decomposed in the following three sub-systems that are expected to have different situational factor values:

¥	Situational factors

Op:	Car rental operational system (no change of work practice planned)

Ma:	Car rental management system (little change of work practice 	possible)

Mk:	Marketing system.

The situational factor values determined by the customer are presented within Figure 15 and 16, one addressing the target domain and the other addressing the project domain.

| Target domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Information System | Heterogeneity of actors |  | medium |  | Attitude of actors | posi-tive |  |  |
|  | Size of target domain |  | medium |  | Ability of actors | high |  |  |
|  | Size of distribution |  |  | large | Stability of environment | high | med. (ma) |  |
|  | Complexity of information |  | medium |  | Formality of information | high (op) | med (ma) | low (mk) |
|  | Complexity of business processes |  | medium |  | Formality of business processes | high (op) | med (ma) | low (mk) |
|  |  |  |  |  | Stability of information and business processes | high (op) | med (ma) | low (mk) |
|  |  |  |  |  | Specificity of information system | low (mk) | med (ma) | high (op) |
|  |  |  |  |  | Understandability of existing system | high |  |  |
|  |  |  |  |  | Strategic importance |  |  | high |
|  |  |  |  |  | Importance of organisational changes | low |  |  |
|  |  |  |  |  | Availability, clarity & stability of requirements | high (op) | med (ma) | low (mk) |
|  |  |  |  |  | Quality of existing specifications |  |  | low |
| Computer System | Complexity of data |  | medium |  | Importance of technological changes |  |  | high |
|  | Complexity of functions |  | medium |  |  |  |  |  |
|  | Complexity of non-functional requirements |  |  | high |  |  |  |  |
|  | Number of replications of computer system |  |  | ma-ny |  |  |  |  |
|  | Complexity of target technology |  | medium |  | Novelty of target technology |  | medium |  |

Figure 15: Situational factor table for the EU-Rent target domain.
(customer view). (Technical specification)

| Project domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Task | Size of the Project |  |  | large | Novelty of IS-adaptation |  | med |  |
|  | Complexity of migration |  |  | large | Adequacy of schedules |  |  | tight |
|  |  |  |  |  | Adequacy of budget |  | nor-mal |  |
| Project Structure | Number of sub-contractors |  | ? |  | Dependency on sub-contractors |  | ? |  |
|  | Number of interfaces to other IS-adaptations | none |  |  | Dependency on other IS-adaptations | none |  |  |
|  |  |  |  |  | Formality of customer-supplier context |  | medium |  |
| Project Actors | Number of project actors | small |  |  | Capability of project team |  | medium |  |
| Project Technology | Complexity of develop-ment technology |  | med. (gen) | high (dist) | Novelty of develop-ment technology | low |  |  |
|  |  |  |  |  | Availability of appro-priate dev. technology | high |  |  |

Figure 16: Situational factor table for the EU-Rent project domain
(customer view). (Technical specification)

ComplexityÊandÊuncertainty

The situational factor values reveals that the main complexity that has to be managed in the project is:

C.1.	The size of distribution is large.

C.2.	The complexity of non-functional requirements is high.

C.3.	There are many replications of the computer system.

C.4.	The project size is large.

C.5.	The complexity of the migration is high.

C.6.	The complexity of the development technology is high regarding the 	distribution aspects.

The main uncertainty is related to:

U.1.	The importance of technological changes is high.

U.2.	-

U.3.	The quality of existing specifications is low.

U.4.	The specificity of the operational rental system is high.

U.5.	The global uncertainty regarding the Marketing system is high.

U.6.	The adequacy of the schedules is tight.

U.7.	The strategic importance is high.

Risks

That means, the following risks have to be reduced or contained:

¥	Risks related to uncertainty factors

R.1.	IS-adaptation not accepted by actors. (U.1)

R.2.	Uncertain or unfeasible requirements to the IS-adaptation 	(Operational system). (U.4)

R.3.	Uncertain and evolving requirements to the IS-adaptation (Marketing 	system). (U.5)

R.4.	Uncertain interfaces to other systems. (U.5)

R.5.	Developing wrong information system. (U.1, U.3)

R.6.	-

R.7.	Shortfalls in the non functional requirements. (U.1)

This is intensified by the complexity factors, especially C.2, C.5 and C.6.

R.8.	Unpredictable costs for the organisation. (U.1, U.7)

R.9.	Poor quality of the products, e.g. with bad commercial impact. 	(U.6)

R.10.	Business implications of IS-adaptation failure. (U.7)

R.11.	Unpredictable costs for the project. (U.3)

R.12.	Increased costs for the project. (U.6)

## 10.2.	DefinitionÊofÊaÊSequenceÊofÊIS-adaptations

After the assessment of the problem situation, the customer has evaluated the risks of the IS-adaptation and decided whether the procurement goal (the final state described in Section 10.1.1) should be achieved in one single IS-adaptation or not.

¥	How to identify and reduce risks in the tendering process

The two sub-systems, Car Rental and Marketing were envisaged separately.

For the Car Rental system, the final state is the typical final state "Installed information system". The initial state is close to the typical initial state "Problem description", but the scope addressed by the initial state is partial and should therefore be completed. A look at the critical combinations of initial and final states (See Customer Guide Section 3.1.1) showed that this combination was dangerous. However, the overall uncertainty associated with the Car Rental system is not high (see Section 10.1.3). It was then assumed that this uncertainty could be handled by an appropriate IS-adaptation strategy. Therefore, a single IS-adaptation was decided.

For the Marketing system, the final state is close to the typical final state "Computer system change study". The initial state is "Undocumented information system". A look at the critical combinations of initial and final states (See Customer Guide Section 3.1.1) showed that this combination was not dangerous. Therefore, a single IS-adaptation was decided.

These decisions have been revisited after having designed the delivery plan (see Section 10.5). At that time, the customer would have performed an elaboration of the IS-adaptation strategy, and a design of the sequence of decision points. The feasibility of the strategy and delivery plan would confirm the choice for the procurement strategy: one or several IS-adaptations.

## 10.3.	DefinitionÊofÊanÊIS-adaptationÊStrategy

The customer decision is to go for a procurement of an external bespoke development that can be either a tailored package or a bespoke development, depending on the supplier's proposal. Based on this decision we can now discuss the different options for sequence of IS-adaptations to achieve the overall goal of the procurement. The basis for this discussion is the planning of decision points under the assumption that the initial and final states are as described in Section 10.1.

The delivery plan is built on the identification of the situational factors and the risks performed in section 10.1.3. This assessment of the problem situation can now be used to choose the appropriate approaches (installation, construction, description, and project control approaches).

¥	How to define a strategy

### 10.3.1.	DevelopmentÊApproach

The change of the current information system can be divided into three parts according to the decomposition of the information system into the three sub-systems:

1.	Car rental operational system.

2.	Car rental management system.

3.	Marketing system.

The customer has observed that the requirements to the changes of these three sub-systems are different and therefore the IS-adaptation strategy should be different. The operational and management systems have the same functionality as in the existing system. However, the management system has a few additional functionalities. The uncertainty of the requirements to these sub-systems is certain to moderate and the complexity of the systems is moderate to complex. This indicates that a suitable installation approach is the incremental installation approach, i.e. the requirements statements and the specifications of the future systems should be frozen at a certain decision point and the installation should be divided into at least two parts:

1.	The operational sub-system and the necessary part of the management sub-system.

2.	The additional part of the management system.

It also indicates that a suitable description approach is an analytical and expert-driven description approach.

The situation related to the Marketing system is uncertain. It contains purely new functionalities and several interfaces to other information systems within the EU-Corporation (the hotel and airline systems). This change of the information system therefore requires an evolutionary installation approach together with a description approach based on an experimental and participatory description approach.

However, the main changes of the information system are the change of the hardware and system software of the computer system. It requires special attention to the design and installation of the hardware configuration and the system software architecture, including the communication software. The whole new hardware and system software will be installed together with the first part of the operational and management system. To do this, it is necessary to have an early decision point regarding the configuration of the hardware and system software. This decision could be based on prototypes simulating the critical aspects of the configuration. The testing of the application software should be combined with the testing of the hardware and system software.

### 10.3.2.	ProjectÊControlÊApproach

The project control approach to be followed contains the following aspects:

¥	Because of the tight schedules, the customer needs a formal development control with development plans and reports every three months.

¥	Because of the low quality of the existing specifications and the tight schedules, the customer needs the quality control to be particularly formal:

-	The supplier should describe their quality assurance organisation, the quality procedures and the quality plans. Together with all the target domain deliverables, the supplier should deliver quality reports with a description of the performed quality procedures.

-	The customer will hire external consultants to make the formal quality control of the deliverables.

¥	Because of the many replications of the computer system and the large distribution of the computer system, the supplier should build a formal configuration control system to control all the operational items. The customer should be responsible for the configuration management after the first installation.

### 10.3.3.	RiskÊManagement

After the choice of the general approaches, additional thought id given to the management of risks caused by complexity or uncertainty.

ManagementÊofÊcomplexity

The following additional elements of the IS-adaptation strategy derived from the actual complexity situational factors by use of the heuristics described in the Delivery Planning Guide:

¥	Management of complexity

=>	The migration from the current system should be done in steps regarding the geographical coverage, starting with a selected subset of locations and then adding the rest of the locations in steps. (All high complexity factors, but especially C.1, C.5 and C.6)

=>	The configuration control of the operational items should be very formal and maybe supported by a computer system. (C.3)

=>	If possible, the contract should be divided into several sub-contracts to manage the size of the total IS-project. (C.4)

=>	The planning of the migration should contain assessments of the need to develop intermediate interfaces to the existing system. (C.5)

ManagementÊofÊuncertainty

The following additional elements of the IS-adaptation strategy are derived from the actual uncertainty risks by use of the heuristics described in the Delivery Planning Guide:

¥	Management of uncertainty

R.1.	IS-adaptation not accepted by actors. (U.1)

=>	The current positive attitudes of the actors have to be maintained and maybe enhanced.

R.2.	Uncertain or unfeasible requirements to the IS-adaptation 	(Operational system). (U.4)

=>	It is necessary to utilise the fact that the understanding of the existing system is high and that the uncertainty regarding the Car rental operational system is low.

=>	It is necessary to focus on the production of the requirement statements and the specifications of the future system. The customer should assess whether it is better to improve the existing specifications before starting an open tendering process or the supplier should start the IS-project by producing some specifications.

R.3.	Uncertain and evolving requirements to the IS-adaptation (Marketing 	system). (U.5)

=>	It is necessary to take this into account when choosing the design approach and the formality of the configuration control of requirements in the production of the Marketing system.

R.4.	Uncertain interfaces to other systems. (U.5)

=>	This is not a big risk because there are only few simple interfaces to other systems.

R.5.	Developing wrong information system. (U.1, U.3)

=>	Again the conclusion is that it is necessary to focus on the production of the requirement statements and the specifications or prototypes of the future system. We need to focus especially on IS-descriptions that can be used to verify that the functionality in the future system will be as good as the functionality in the current system. The existing functionality in the Car rental operational system will not change, only the technology, the communications and the general management facilities will change.

R.6.	-

R.7.	Shortfalls in the non-functional requirements. (U.1)

This is intensified by the complexity factors, especially C.2, C.5 and C.6.

=>	The choice of hardware technology should take this risk into account. That means, the customer should choose safe and mature technology either before the start of the tendering process or very early in the IS-adaptation process. The supplier should demonstrate good knowledge about the technology with references to successful installation and usage of the technology. Especially the distribution and communication aspects should be in focus in the planning of the IS-adaptation.

=>	There should be focus on the traceability of the non-functional requirements.

=>	Prototypes of the future system should be evaluated from a performance and reliability point of view.

R.8.	Unpredictable costs for the organisation. (U.1, U.2, U.3, U.7)

=>	It is important to put focus on the cost calculations in the tender response and during the IS-project. The uncertainty regarding the cost calculations should be decreased as early as possible.

R.9.	Poor quality of the products, e.g. with bad commercial impact. 	(U.6)

=>	It is important to have a good quality assurance system. The operational items should be well tested before installation and the migration from the current system should be managed carefully. If it is possible, the migration should be done in small steps.

R.10.	Business implications of IS-adaptation failure. (U.7.)

=>	It is important to minimise the business implications of the introduction of the new system by ensuring that the current level of service is maintained at all times, and particularly during the period when cutting over to the new system. Again, if it is possible, the migration should be done in small steps.

For example, evaluate prototypes of the future system from a performance and reliability point of view (particularly when considering the future implementation of the Marketing system).

## 10.4.	DefinitionÊofÊDecisionÊPoints

The assessment of the problem situation has shown that the Car Rental system need not be treated as having two sub-systems. Therefore, the defines IS-adaptation considers the following sub-systems:

1.	Car Rental system.

2.	Marketing system.

For each group of operational items, the customer has defined the desired decision points based on the choice of IS-adaptation strategy and the heuristics in the Delivery Planning Guide. In the following, the chosen general approaches are summarised and the desired decision points are listed. The customer has sketched the envisaged decision points, thereby limiting the freedom of the suppliers concerning their proposals.

¥	How to define decision points

### 10.4.1.	IS-adaptationÊregardingÊtheÊCarÊRentalÊSystem

Approaches:

¥	Incremental installation with steps in geographical coverage.

¥	Analytical and expert-driven description.

¥	Incremental construction.

¥	Formal and frequent development, quality and configuration control.

DecisionÊpoints:

1.1.	Configuration of computer system: hardware and system software, 	including network architecture.

1.2.	Car Rental future work practices.

1.3.	Car Rental future computer system.

1.4.	Installation and test plans (detailed development plans).

1.5.	Installation of the first increment of the Car Rental system in the first 	locations.

1.6.	Total installation of the first increment of the Car Rental system.

1.7.	Installation of the total Car Rental system in the first locations.

1.8.	Total installation of the total Car Rental system.

### 10.4.2.	IS-adaptationÊregardingÊtheÊMarketingÊSystem

Approaches:

¥	Evolutionary installation with steps in geographical coverage.

¥	Experimental and participatory design.

¥	Evolutionary construction.

¥	Formal configuration control of requirements.

DecisionÊpoints:

For the Marketing system, the customer has not attempted to define the intermediate decision points. The suppliers are requested to make a proposal for decision points. Therefore, the only imposed decision point corresponds to the final delivery is:

2.1.	Marketing system prototype (and requirements statements and 	specifications).

### 10.4.3.	SequenceÊofÊDecisionÊPoints

Taking the dependencies between the decision points into account, the schedules of the decision points for the EU-Rent IS-adaptation is sketched in Figure 17.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Configuration of computer system (1.1) |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Car rental future work practices (1.2) |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Car rental future computer system (1.3) |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Installation and test plan (1.4) |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |
| 5. Installation of 1. part. in 1. locations (1.5) Marketing prototype (2.1) |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |
| 6. Total installation of 1. part (1.6) |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |
| 7. Installation of total system in 1.location (1.7) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 8. Total installation of total system (1.8) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure 17: The schedules of the decision points in the EU-Rent IS-adaptation.
(Technical specification)

Following this, the customer decides to describe each of the decision points in some detail. This includes the description of the deliverables to be exchanged at the decision points. An example of a decision point description is given below.

### 10.4.4.	DescriptionÊofÊaÊDecisionÊPoint

Figure 18 shows an example of a decision point description.

Decision point: 	3.	Car Rental future computer system.

1.1.	TargetÊdomainÊpurpose

¥	To select among options regarding the computer system architecture.

¥	To check consistency of the selected option with the requirements 	stated as part of the initial state products.

¥	To check consistency of the selected option with the work practices 	approved in decision point 2.

1.2.	ProjectÊdomainÊpurpose

To control the progress of the project and the plan for the future work.

2.	Deliverables
The following deliverables should support the above mentioned decisions:
¥	Requirements to the non-functional properties.
¥	Specification of the computer system architecture properties,
	with alternatives to choose from.
¥	Specification of relations between the work practice and the computer 	system architecture properties.
¥	Project plans and reports.

3.	RolesÊinvolved

¥	Customer roles:

-	Contract authority:	Marie-Louise Simenon.

-	Project authority:	Valerie Maurice.

-	IS-expertise: 		User representatives, IT staff.

-	QA-expertise:		The consultancy company.

¥	Supplier roles (to be completed by the supplier):

-	Contract authority: 	NN.

-	Project authority: 	NN.

-	IS-expertise: 		NN (Key project team members).

-	QA-expertise: 		NN (The QA responsible).

Annex A.	Required deliverable profile: Figure 19.

Figure 18: Description of decision point 3 in the EU-Rent IS-adaptation. (Technical specification)

Required deliverable profile

Decision point: 	3.	Car Rental future computer system.

1.	Description of States

1.1.		Development States: 
	-	D means detailed development state, i.e. high degree of 				decomposition and specialisation.

1.2.		Quality States: 
	-	QR means that a quality review must have been performed prior to 		the delivery. The review documentation must be complete.

2.	Captured Properties

2.1.		Non-functional properties.
		Captured properties table: Figure 19.a.

2.2.		Specification of the computer system architecture properties.
		Captured properties table: Figure 19.b.

2.3.		Specification of relations between the work practice and the 	computer system architecture properties.
		Captured properties table: Figure 19.c.

2.4.		Project plans and reports.
		Captured properties table: Figure 19.d.

Figure 19: Required deliverable profile of deliverables at decision point 3 in the EU-Rent IS-adaptation. (Technical specification)

| Non-functional properties of | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a future Car Rental computer system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| Costs | D | QR | Ã |  |  |  | Ã |
| Benefits | D | QR | Ã |  |  |  | Ã |
| Volumes | D | QR | Ã |  |  |  | Ã |
| Duration | D | QR | Ã |  |  |  | Ã |
| Frequency | D | QR | Ã |  |  |  | Ã |
| Efficiency | D | QR | Ã |  |  |  | Ã |
| Security | D | QR | Ã |  |  |  | Ã |
| Criticality | D | QR | Ã |  |  |  | Ã |
| Reliability | D | QR | Ã |  |  |  | Ã |
| Maintainability | D | QR | Ã |  |  |  | Ã |
| Portability | D | QR | Ã |  |  |  | Ã |

Figure 19.a: Captured properties table: Non-functional properties of 
a future Car Rental computer system. (Technical specification)

| Specification of the computer system architecture | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| properties of a future Car Rental computer system | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| Processing units | D | QR | Ã |  |  | Ã |  |
| Locations | D | QR | Ã |  |  | Ã |  |
| Data distribution | D | QR | Ã |  |  | Ã |  |
| Function distribution | D | QR | Ã |  |  | Ã |  |
| Structure | D | QR | Ã |  |  | Ã |  |
| External communications | D | QR | Ã |  |  | Ã |  |
| Internal communications | D | QR | Ã |  |  | Ã |  |
| Application software | D | QR | Ã |  |  | Ã |  |

Figure 19.b: Captured properties table: Specification of the computer system architecture properties of a future Car Rental system. (Technical specification)

| Specification of relations between the work practice | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| and the computer system architecture properties | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| WorkÊpracticeÊview |  |  |  |  |  |  |  |
| Actors | D | QR |  | Ã |  |  | Ã |
| Locations | D | QR |  | Ã |  |  | Ã |
| Communications | D | QR |  | Ã |  |  | Ã |
| Tasks | D | QR |  | Ã |  |  | Ã |
| Computerisation | D | QR |  | Ã |  |  | Ã |
| Performer | D | QR |  | Ã |  |  | Ã |
| Triggering organisational events | D | QR |  | Ã |  |  | Ã |
| Triggering conditions | D | QR |  | Ã |  |  | Ã |
| Generated organisational events | D | QR |  | Ã |  |  | Ã |
| Task decomposition | D | QR |  | Ã |  |  | Ã |
| Dynamic dependencies | D | QR |  | Ã |  |  | Ã |
| Task rules | D | QR |  | Ã |  |  | Ã |
| Information use and generation | D | QR |  | Ã |  |  | Ã |
| Resources | D | QR |  | Ã |  |  | Ã |
| ComputerÊsystemÊarchitectureÊview |  |  |  |  |  |  |  |
| Processing units | D | QR |  | Ã |  |  | Ã |
| Locations | D | QR |  | Ã |  |  | Ã |
| Data distribution | D | QR |  | Ã |  |  | Ã |
| Function distribution | D | QR |  | Ã |  |  | Ã |
| Structure | D | QR |  | Ã |  |  | Ã |
| External communications | D | QR |  | Ã |  |  | Ã |
| Internal communications | D | QR |  | Ã |  |  | Ã |
| Application software | D | QR |  | Ã |  |  | Ã |

Figure 19.c: Captured properties table: Specification of relations between the work practice and the computer system architecture properties of a future Car Rental system. (Technical specification)

| Project plans and reports (decision point 3) | Quality state |
| --- | --- |
| ProjectÊStatusÊReport |  |
| Deviations from the delivery plan | QR |
| New issues to the project | QR |
| DevelopmentÊReport |  |
| All project properties | QR |
| QualityÊAssuranceÊReport |  |
| All project properties | QR |
| ConfigurationÊManagementÊReport |  |
| All project properties | QR |
| DevelopmentÊPlan |  |
| All project properties | QR |
| QualityÊAssuranceÊPlan |  |
| All project properties | QR |
| ConfigurationÊManagementÊPlan |  |
| All project properties | QR |

Figure 19.d: Captured properties table of the project domain deliverable at decision point 3 in the EU-Rent IS-adaptation. (Technical specification)

## 10.5.	ConfirmationÊofÊtheÊSequenceÊofÊIS-adaptations

Based on the sequence of decision points described in Figure 17, two options for achieving the goal of the procurement can be analysed:

1.	The procurement goal is achieved in one single IS-adaptation, possibly with planned contract change control (at decision point 4 for example).

2. 	The procurement goal is achieved in a series of IS-adaptations, e.g.:

First IS-adaptation:

-	Initial state: Current state.

-	Desired final state: Deliverables at decision point 1-4: Configuration of computer system, Work practice model, Computer system architecture; and plans for future IS-adaptations.

Second IS-adaptation:

-	Initial state: Current state and deliverables at decision point 1-4.

-	Desired final state: Deliverables at decision point 5-6: Total installation of first increment of the Car Rental system; and plans for future IS-adaptations; prototype of the Marketing system.

Third IS-adaptation:

-	Initial state: The state after decision point 6: Total installation of first increment of the Car Rental system.

-	Desired final state: Deliverables at decision point 7-8: Total installation of the total Car Rental system.

In this case study scenario, the customer choice was a single IS-adaptation (see Section 10.2). The feasibility of the delivery plan had convinced the customer that this procurement strategy was manageable. In addition, a single IS-adaptation was considered to be faster than a series of IS-adaptations because of the overhead of their multiple tendering processes. This would help to cope with the tight schedules.

## 10.6.	TheÊCallÊforÊTender

Figure 20 represents the delivery plan that is issued as part of the Technical Specification of the Call for Tender document. It documents all the IS-adaptation requirements that have been defined within the preparation of the Call for Tender transaction.

Delivery plan:	The EU-Rent IS-adaptation

1.	Problem Situation
-	A summary of Section 9: The EU-Rent case study context.

1.1.		Starting Point: The initial state of the IS-adaptation
	-	A summary of Section 10.1.2: Initial state profile.

1.2.		Goal: The final state of the IS-adaptation
	-	A summary of Section 10.1.1: Final state profile.

1.3.		Appreciation of the Problem Situation
	-	A summary of Section 10.1.3: Situational factors and risks.

2.	IS-adaptation Strategy
-	A summary of Section 10.3: Definition of an IS-adaptation strategy.

2.1.		Approach to Change Situational Factors
	-	No approach is proposed.

2.2.		Development Approach
	-	Section 10.3.1: Development approach.

2.3.		Project Control Approach
	-	Section 10.3.2: Project control approach.

2.4.		Risk Management
	-	Section 10.3.3: Risk management.

3.	Decision Points
-	A summary of Section 10.4: Definition of decision points.
-	The schedules of the decision points: Figure 17.

Annex A: 	Initial State Profile

-	Figure 14.

Annex B: 	Final State Profile

-	Figures 12 and 13.

Annex C: 	Situational Factor Tables

-	Figures 15 and 16.

Annex D: 	Decision Point Descriptions

-	Figures 18 and 19 and similar for the other decision points.

Figure 20: Contents of a delivery plan for the EU-Rent IS-adaptation
(Technical specification)

# 11.	PreparationÊofÊaÊTenderÊResponse

The supplier senior management role had the call for tender document analysed with the purpose of getting enough knowledge to decide whether it is worth producing a tender response or not. This analysis consists of a fast and overall assessment of the problem situation, including a sketch of a Technical Proposal. In this case study, we assume that the supplier has taken the decision to produce a tender response. A working group to produce the tender response has been organised.

¥	How to prepare the tender Response transaction

The IS-adaptation requirements within the technical proposal should completely define the customer-supplier relationships in the production and completion processes of the IS-adaptation.

The main activities in the production of the tender response in which Euromethod can be used, are:

¥	Assessment of the problem situation.

¥	Amendment of the initial state products.

¥	Enhancing the delivery plan.

## 11.1.	AssessmentÊofÊtheÊProblemÊSituation

The Euromethod situational factors can be used to support the assessment of the problem situation. The delivery plan and the initial state products within the call for tender document was assessed for:

¥	How to assess a problem situation

¥	The customer's understanding of the initial state products by comparing them with the initial state profiles in the delivery plan. Are the profiles in line with the actual products delivered by the customer?

¥	The complexity and uncertainty of the problem situation by:

-	analysing the final state profiles and sketching some proposals for products to be delivered in line with the profiles and the company specific rules about operational item solutions and project methods, techniques and tools.

-	analysing, based on the company specific experiences, the requirements to the IS-adaptation strategy, the sequence of decision points and the required deliverable profiles.

-	making cost-benefit analysis from the supplier point of view.

¥	The risks by analysing the high complexity and high uncertainty factors, and sketch the possible approaches to reduce or contain the risks and manage the complexity.

SituationalÊfactors

In this case study, the supplier's assessment of the problem situation resulted in similar situational factor values to those of the customer, see Section 10.1.3. Additionally, the supplier assessed the complexity and uncertainty in relation to:

¥	Capability of the project actors and dependency on sub-contractors.

It could be necessary for the supplier to have sub-contractors regarding areas where knowledge or resources are insufficient.

The supplier decided to use sub-contractors with experience in the following areas:

-	Client/server technology.

-	Distributed database systems.

¥	Adequacy of schedules.

The supplier supposed:

-	To increase elapsed time.

-	Smaller increments.

-	A simple technical solution.

¥	Complexity and availability of the development technology.

This situational factor also lead to the decision to propose a simple solution, e.g. tailored standard packages.

In the tender response, the supplier illustrated that he had a good understanding of the customers situation and that he as supplier could successfully complete the IS-adaptation. The analysis of the situational factors was used to highlight the most important risks and explain how the risks can be reduced or contained.

## 11.2.	AmendmentÊofÊtheÊInitialÊStateÊProducts

From the profile of the initial state products (see Figure 14) and from the analysis of the products delivered from the customer as part of the call for tender document, the supplier concluded that the initial state products need to be enhanced in several areas:

¥	Requirements statements are required for:

-	The work practice properties, e.g. the human-computer interfaces and the operation of the computer system.

-	The computer system architecture properties, e.g. the distribution of data and functions.

-	The non-functional properties, e.g. the response time, the criticality of functions, the costs and the business benefits related to different parts of the future information system.

¥	Specifications are required for:

-	The computer system architecture, e.g. the technical architecture.

-	The non-functional properties, e.g. in relation to the proposed technical architecture.

These might also be decided in an early decision point.

## 11.3.	EnhancingÊtheÊDeliveryÊPlan

The enhancement of the delivery plan can be supported by Euromethod, as explained in the topic guides, e.g.

¥	Which changes should the supplier propose to the IS-adaptation strategy, the decision points and the required deliverables profiles - guidance is given in the Delivery Planning Guide [EM-2.3-DPG].

¥	How to define a strategy

¥	Which supplier method products can meet the customer's requirements and how should the supplier document that in method product profiles and method deliverable profiles related to the required deliverable profiles - guidance is given in the Method Bridging Guide.

¥	How to populate a Delivery Plan

In this case, the supplier made the enhancements described in the following sections.

### 11.3.1.	FinalÊStateÊProfile

The supplier then made the changes in the final state profile that he decided from the assessment of the problem situation, e.g. a reduction in the ambitions of the related products that are maintained when completing this IS-project, and a reduction in the ambitions of the operational items (e.g. no written manuals, only a simple on-line help system). The profile were documented in the same way as in the call for tender document. The changes were justified.

Additionally, the supplier described the operational items that would be delivered (this description was included as initial state products within the technical proposal of the tender response document).

The supplier showed how he intended to produce the required deliverables by associating method deliverable profiles and method product profiles to the final state profile and the required deliverable profiles of the decision points identified by the customer.

### 11.3.2.	InitialÊStateÊProfile

The initial state profile in the call for tender document was revised according to the enhancement of the initial state products, as explained in Section 11.3.1.

### 11.3.3.	DecisionÊPoints

On the basis of experience, business rules, methods, techniques and tools, and the recommendations given in the Method Bridging Guide and the Delivery Planning Guide, the supplier enhanced the decision points of the delivery plan as presented in the call for tender document.

¥	How to derive decision points

CarÊRentalÊsystem

¥	How to define decision points

As explained in Section 11.1, the supplier reached similar conclusions as the customer (see Section 10.3) regarding the situation analysis.

The supplier thus confirmed that the installation approach for the Car Rental system should be incremental with steps in the geographical coverage.

A similar analysis indicated that the most suitable construction approach was an incremental construction approach.

The Delivery Planning Guide proposes an example of sequence of decision points for such a combination of incremental construction approach and incremental installation approach. This example shows that the following decision point could be added before an installation of a part:

¥	Acceptance test of the part.

For the description approach, the supplier arrived also at the same conclusion as the customer (see Section 10.3) and selected an analytical and expert driven approach.

The Delivery Planning Guide proposes an example of sequence of decision points for an analytical and expert driven approach. Looking at the initial state profile (see Section 10.1.2) and the deficiencies of the initial state products (see Section 11.2), the supplier decided to add two decision points from the Delivery Planning Guide example. By doing that he hoped to get the endorsement of the customer on intermediate deliverables thereby minimising the risk to go into a wrong direction for the IS-adaptation. These two decision points are:

¥	Approve global work practice specifications.

¥	Approve global computer system specifications.

Using the same sources, the supplier detected that the detailed business information and business process views were not addressed in any decision point, although they were insufficiently covered in the initial state products. Therefore, he decided to enhance decision point 2: Car Rental work practices (of the customer delivery plan) to include them. This decision point becomes then:

¥	Approve detailed information system specifications.

The revision of the sequence of decision points is illustrated in Figure 21.

| Sub-system Decision point | Car Rental system |
| --- | --- |
| 1'. Global Car Rental work practices | * |
| 1'' Global Car Rental computer system | * |
| 1. Configuration of computer system | 1.1 |
| 2. Detailed Car Rental information system | 1.2 |
| 3. Detailed Car Rental computer system | 1.3 |
| 4. Installation and test plan | 1.4 |
| 5'. Acceptance test of the first part of the Car Rental system | * |
| 5. Installation of the first part in first locations | 1.5 |
| 6. Total installation of the first part | 1.6 |
| 7'. Acceptance test of the total Car Rental system | * |
| 7. Installation of the total system in the first locations. | 1.7 |
| 8. Total installation of the total Car Rental system. | 1.8 |

Figure 21: The sequence of decision points for the Car Rental system
 - the additional decision points are marked in italic. (Technical Proposal)

CustomerÊresponsibility

Examples of the customer responsibilities proposed by the supplier:

¥	Testing responsibility.

¥	Training of users before installation.

¥	Specification of help system.

¥	Conversion of current data.

¥	Preparing the offices for the installation of hardware.

¥	Feedback from the customer quality control and the customer test.

MarketingÊsystem

For the Marketing system, the customer has not proposed any decision point, thereby leaving the suppliers free to propose their solutions.

Our supplier has confirmed the situation analysis made by the customer (see Section 11.1). Therefore, the most appropriate strategy for the description of the Marketing system is experimental and participatory (see Section 10.3.2).

The Delivery Planning Guide proposes some typical sequence of decision points for such an approach, see example of decision points in Section 6.1.1 of the Delivery Planning Guide. The supplier decided that it was suitable for the situation and proposed this sequence within his delivery plan.

¥	How to define decision points

That sequence of decision points is illustrated in Figure 22.

| Sub-system Decision point | Marketing system |
| --- | --- |
| 2. Global and partly detailed work practices prototype | 2.1 |
| 2'. Global and partly detailed work practices specification | 2.2 |
| 3. Global and partly detailed computer system prototype | 2.3 |
| 4. Global and partly detailed computer system specification | 2.4 |
| 5'. Detailed work practices prototype | 2.5 |
| 5. Detailed computer system prototype | 2.6 |

Figure 22: The sequence of decision points for the Marketing system.
(Technical Proposal)

The numeric labels of the decision points correspond to the ones of the Car Rental system. The customer has imposed that the detailed computer system prototype be delivered in decision point 5. The supplier has considered that the global and partly detailed work practice prototype of the Marketing system could not be delivered before the detailed information system design of the Car Rental system (decision point 2), because of their dependencies. The supplier has also decided to minimise the number of decision points, therefore merging decisions on the Car Rental system and the Marketing system in the same points. This could be changed when scheduling the decision points.

The complete set of decision points with schedules is given in Figure 23. As stated above, the supplier supposed to increase the elapsed time.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1'. Global car rental work practices |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1''. Global car rental computer system |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Configuration of computer system (1.1) |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Detailed car rental information system(1.2) Global work practice prototype (marketing 2.1) |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3'. Global work practice spec. (marketing 2.2) |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Car rental future computer system (1.3) Global computer system prototype (marketing 2.3) |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Installation and test plan (1.4) Global computer system spec. (marketing 2.4) |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |
| 5'. Acceptance test of 1. part of car rental system. Detailed work practice prototype (marketing 2.5) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |
| 5. Installation of 1. part in 1. locations (1.5) Detailed computer system prototype (marketing 2.6) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |
| 6. Total installation of 1. part (1.6) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |
| 7' Acceptance test of total car rental system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 7. Installation of total system in 1.location (1.7) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |
| 8. Total installation of total system (1.8) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure 23: The schedules of the decision points in the EU-Rent IS-adaptation.
 - the additional decision points are marked in italic. (Technical Proposal)

### 11.3.4.	DeliveryÊPlan

The supplier described the decision points, and in particular the associated deliverable profiles. This is performed in the same way as in Section 10.3.4.

He then documented the delivery plan which is included in the Technical Proposal part of the tender response. The delivery plan proposed by the supplier is given in Figure 24.

Delivery plan:	The EU-Rent IS-adaptation

1.	Problem Situation
-	The supplier's understanding of the technical specification.

1.1.		Starting Point: The initial state of the IS-adaptation
	-	The supplier's understanding, see Sections 11.2 and 11.3.2.

1.2.		Goal: The final state of the IS-adaptation
	-	The supplier's understanding, see Section 11.3.1.

1.3.		Appreciation of the Problem Situation
	-	The supplier's understanding, see Section 11.1.

2.	IS-adaptation Strategy
-	The supplier's proposal based on the technical specification,
	see Section 11.3.3.

3.	Decision Points
-	A summary of Section 11.3.3: Decision points.
-	The schedules of the decision points: Figure 23.

Annex A: 	Initial State Profile

-	Revised Figure 14 (from the technical specification).

Annex B: 	Final State Profile
-	Revised Figures 12 and 13 (from the technical specification).

Annex C: 	Situational Factor Tables
-	Revised Figures 15 and 16 (from the technical specification).

Annex D: 	Decision Point Descriptions
-	Revised Figures 18 and 19 (from the technical specification) 
	and similar for the other decision points.

Figure 24: Contents of a delivery plan for the EU-Rent IS-adaptation
(Technical proposal)

# 12.	Initial State Products: EU-Rent Specifications

## 12.1.	EU-RentÊBranchÊandÊDepotÊVolumetricÊDetails

EU-Rent operates in many towns all over Europe, from 1000 branches of three types:

¥	Branches in major airports:

There are 100 of these, which have an average 700 cars. Airport branches stay open 16 hours per days, 7 days per week. Business is spread uniformly across the day. The average number of rentals per airport branch per week is 1350.

¥	Branches in major cities:

There are 200 of these, which have an average 350 cars. City branches stay open 11 hours per day, 6 days per week. Nearly all pickups take place between 8 am and 11 am. Nearly all returns take place between 4 pm and 7 pm. Bookings are spread evenly through the day. The average number of rentals per major branch per week is 750.

¥	Branches in local agencies such as hotels or garages:

There are 700 of these, which have an average 80 cars. Local branches follow the same usage pattern as major city branches. The average number of rentals per hotel or garage branch per week is 165.

EU-Rent has 400 service depots for car maintenance and repairs. Each branch is served by a single service depot; a service depot will usually serve more than one branch. Cars, which are classified in five groups, are kept for one year or 40,000 kilometres, whichever occurs first. A car would usually have 4 services during its life with EU-Rent.

The system keeps records of 500,000 customers and their rentals and of comments about bad experiences with customers which can be used to decide whether to approve a rental. Customers stay on the system until they have been inactive for ten years. A customer can have several reservations but only one rental at a time.

## 12.2.	EU-RentÊOperations

CarÊrentals

Each branch maintains local records of its cars, organised by car group.

Advance reservations are recorded with a reference, customer details, required car group, start of required rental and number of days of rental.

Booking clerks may reject some reservations. Reasons to reject would normally be based on past experience of the customer at the branch (such as late returns, bounced cheques, damage to car) or because the customer had been blacklisted by head office.

Reservations may be cancelled at any time until the car is picked up. The pick-up represents confirmation of the booking.

Reservations are recorded by car group. Each day, booking clerks look through the rentals due to start on the following day, look for available cars in each group and book a specific car for each reservation.

The branch manager must ensure that there are sufficient cars in each group to meet his reservation commitments each day. He may have to phone other branches and arrange transfers. In extremes a customer may be given a car in a group other than the one he reserved.

When a car is picked up for rental, the time is noted and the system produces a contract / invoice, with a copy for the customer to take away.

When a car is returned from rental, the time is noted, the customer pays and is given a receipt. Comments may be noted against the customer and/or the rental, and as a result, the customer might be marked as a bad risk. Bad risks are notified to head office. Head office maintains a list of bad risk customers, identified by driving licence numbers. This list is distributed to all branches.

A car rented from one branch of EU-Rent may be returned to any other branch. It is the responsibility of the renting branch to ensure that the car has been returned somewhere. If a car is returned to a different branch from the one that rented it ÒownershipÓ of the car is transferred to the new branch (this happens, but happens infrequently); the branch from which the car was rented is notified by telephone or fax.

A customer may walk in and request an immediate rental. If a suitable car is available a booking is made and a contract / invoice is produced as for an advance reservation.

CarÊpoolÊatÊbranch

A branch manager may add a car to the pool at the branch by purchasing it (the money comes from head office), or by arranging one to be transferred from another branch.

A branch manager may reduce the car pool by selling a car, or scheduling its transfer to another branch, as long as the car is located at the branch at that time and is not booked for rental or maintenance on the following day.

A car may be written off at any time, if authorised by the branch manager. If a written-off car is booked for rental the following day another car must be booked to replace it.

Only one rental or maintenance booking is allowed per car day. Rental and maintenance bookings may cover several days.

CarÊtransfersÊbetweenÊbranches

Cars tend to accumulate at some branches (Calais for example, fills up with cars hired by people whose own car has broken down on holiday). Every so often a branch manager will ring round other branches seeking to gain or lose a few cars.

When branch managers have reached an agreement over the telephone, the manager of the ÔsendingÕ branch will schedule each relevant car for transfer and hire a driver to transfer it to the ÔreceivingÕ branch. The system will send a notification of this to the manager of the ÔreceivingÕ branch.

A transfer may be cancelled at any time until the car is picked up. The pick-up represents confirmation of the scheduled transfer.

CarÊmovementsÊwithinÊEU-Rent

Drivers are hired to pick up the car from the branch for maintenance, or transfer to another branch. The pick-up of a car represents confirmation of the scheduled maintenance or transfer.

When a car is picked up for maintenance or transfer, the time is noted and the driver is given an authorisation. When a car is returned from maintenance or transfer, the time is noted and the driver is given a receipt.

In terms of ownership, this Transfer Pick Up event represents the loss of the car from the sending branch, and the gain of the car by the receiving branch.

CarÊmaintenance

Each service depot maintains local service records of cars owned by its branches. Maintenance scheduling requires co-ordination between the relevant branch manager and the depot manager, to ensure the service depot and branch records are in step.

When a car has done 10,000 km since its purchase or last service, the branch manager will normally book it in for service at the branchÕs service depot, as long as the car is free and the service depot has capacity for that day. If a service has not been arranged within 3 months of purchase or previous service, the service depot manager will book the car in for a service.

The branch manager talks with the manager of the service depot, and between them they find a date when the car is not booked for rental, and the service depot has time available to do the work. A branch manager or a depot manager may cancel a service booking at any time until the car is picked up. The pick-up of a car represents confirmation of the scheduled service.

Administration

At Head Office the administrator has a little work to do, maintaining basic information about the branches and service depots.

The administrator also has some responsibility for customer information, archiving dead customers, and entering a Customer Reinstatement event to clear a customer who has been marked as a bad risk.

Customers

Customers are identified by Driving Licence Number, so different branches can recognise and deal with the same customers.

CarÊgroups

Cars are classified into car groups. All cars in a group are of equivalent specification and have the same rental price.

LateÊreturns

To check that a car has been returned, the procedure is that every day one of the booking clerks looks through the rentals for rentals due to end yesterday, but for which no return has been noted.

Where a return has not been noted, the booking clerk first checks the compound to see if the car is there, and with other clerks to see if they forgot to note its return. If not then the clerk calls whatever telephone number the customer has supplied. If no answer, the clerk must ring around all the other branches to discover if the car has been returned there instead.

## 12.3.	EU-RentÊInformationÊSupport

SupportÊtheÊcarÊrentalÊbranches

Available Cars:	To see what cars are available to fill reservations that have not been assigned cars automatically and for walk-in rentals.

To see whether cars are available to fill other branchesÕ requests for transfers (this can also be used by a branch manager to enquire about cars at other branches).

Bookings for Car:	To ensure that there are no double bookings for car.

Branch Rentals for Day:	To identify what cars are needed for the following dayÕs rentals - provides input to assignment of cars to reservations.

Depot Capacity Available:	To see what dates are available for service bookings.

Late Returns for Branch:	To prompt the booking clerk to contact the customer and find out why the car has not been returned

Returns to Other Branches:	To let the branch manager know which cars have been lost from his branch, by being returned to other branches.

Scheduled Maintenance:	When a car is transferred, if there are service bookings for the car and the new branch is served by a different service depot, to let the branch manager know that he must cancel the service bookings and arrange equivalent bookings at the new service depot.

SupportÊtheÊEU-RentÊserviceÊdepots

Bookings for Car:	To see when cars can be booked for service.

Depot Capacity Available:	To see what dates are available for service bookings.

Car Maintenance History:	For reference when a car is being serviced.

Maintenance Schedule:	Services scheduled for the immediate future (coming week, month etc.) to support planning of work at depot.

SupportÊEU-RentÊheadÊoffice

Analysis of Car Movements:	Analysis of movement (and change of ownership) of cars by transfers and by rental returns to branches other than the renting branch - currently just monitoring the situation, but it may lead to additional business rules in the future.

Branch History:	Analysis of rentals and gains & losses of cars - input to decisions on whether to keep branch open, change staff levels, etc.

Car Group Usage:	Analysis of rentals and maintenance costs of car group - input to decisions on rental rates, how many cars to buy in each group.

Customer History:	Input to decisions on whether to suspend, reinstate, remove customer.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[92/50/EEC]	The EEC Service Directive: 
Council Directive 92/50/EEC of 18 June 1992 relating to the co-ordination of procedures for the award of public service contracts.

# Index

Call for Tender

preparation of a ~ transaction 16; 71

Contract Awarding

preparation of a ~ transaction 48

decision point

~ description 42; 95; 96

definition of ~s 40; 92; 105

sequence of ~s 40; 107; 108; 109

deliverable profile

required ~ 18; 43; 71; 96

delivery plan 67; 104

contents of a ~. 27; 45; 101; 110

final state

~ profile 17; 71; 105

typical ~ 24

initial state

~ product 19; 50; 60; 78

~ profile 78; 105

typical ~ 25

IS-adaptation

~ requirements 27; 44; 67

~ strategy 35; 88

construction approach 36

customer responsibility 107

description approach 88

installation approach 35; 88

management of complexity 37; 90

management of uncertainty 38; 90

project control approach 89

sequence of ~s 24; 99

IS-description 50; 60; 111

problem situation 13

assessment of a ~ 16; 28; 71; 102

risks 35; 86

management of ~ 37; 90

situational factor

~ table

project domain ~s 33; 85

target domain ~s 30; 84

complexity ~s 31; 34; 35; 86

uncertainty ~s 31; 34; 35; 86

Supplier Selection

preparation of a ~ transaction 46

target domain 29; 70

technical annex 48

technical proposal 28; 44

technical specification 27; 67

Tender Response

preparation of a ~ transaction 28; 102

view

business information ~ 22

business process ~ 23; 82

computer system architecture ~ 24; 73; 80

computer system data ~ 23; 73; 78

computer system function ~ 23; 78

work practice ~ 23; 73; 78; 80; 82

The assessment of costs and benefits is not part of the supplier's method which is purely an engineering method. However, the risk analysis (see Section 4.2.3. Risk Management) has indicated that an early investigation of costs was necessary, i.e. an early decision point regarding costs. Therefore, it has been added in decision point 1.