Euromethod
Customer Guide

EM-2.1-CG

__________________________________

Abstract

This Guide provides the guidance for Euromethod practitioners undertaking IS-adaptations from a customer perspective.

It explains how the Euromethod concepts defined in the EuromethodÊConcepts Manuals have to be used in order to support customers in performing the tendering process and the activities related to the production and completion processes of an IS-adaptation.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Customer Guide,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Guides Level. It makes use of the definitions in the Method Bridging Guide, the Delivery Planning Guide and Concepts Manuals and the Dictionary.

Contents of the Customer Guide

1.	Introduction	6

1.1.	Objectives	6

1.2.	TargetÊaudience	6

1.3.	Scope	7

1.4.	Style Considerations	8

1.5.	Entry Points	10

2.	What is an IS-Adaptation	12

2.1.	IS-adaptations and the Services Directive	12

2.2.	How are the SupplierÕs responsibilities described	16

2.3.	How is the CustomerÕs Involvement described	17

2.4.	How is the Customer-Supplier Relationship described	20

2.5.	Role Assignment in an IS-adaptation	22

3.	How to prepare the Call for Tender Transaction	28

3.1.	How to identify Risks in the Tendering Process	31

3.1.1.	Assessment of Initial and Final State	32

3.1.2.	Delivery Planning	42

3.2.	How to reduce Risks in the Tendering Process	45

3.2.1.	Amendment of the Initial State	46

3.2.2.	Change the Situational Factors	47

3.2.3.	ReducingÊtheÊExpectationsÊtoÊtheÊFinalÊState	48

4.	How to use Euromethod in the Tendering Process	49

4.1.	How to Initiate the Call for Tender Transaction	50

4.2.	How to Prepare for the Tender Response Transaction	52

4.3.	How to prepare for the Supplier Selection Transaction	53

4.4.	How to prepare the Contract Awarding Transaction	60

5.	How to use Euromethod in the Production Process	63

5.1.	Approval of Deliverables	64

5.2.	Approval of Project Status and Plan	70

5.3.	Contract Change Control	71

5.4	IS-adaptation Role Assignments in the Production Process	75

6.	How to use Euromethod in the Completion Process	76

6.1.	Approval of Final Deliverables	76

6.2.	Contract Completion	79

A.	Profiles of Typical Initial States	82

A.1.	Undocumented information system	82

A.1.1.	Description	82

A.1.2.	Profile	82

A.2.	Documented information system	83

A.2.1.	Description	83

A.2.2.	Profile	83

A.3.	Tested Information System	84

A.3.1.	Description	84

A.3.2.	Profile	84

A.4.	Detailed technical design	85

A.4.1.	Description	85

A.4.2.	Profile	85

A.5.	Detailed Business Design	86

A.5.1.	Description	86

A.5.2.	Profile	86

A.6.	Global Design	88

A.6.1.	Description	88

A.6.2.	Profile	88

A.7.	Problem Description	89

A.7.1.	Description	89

A.7.2.	Profile	89

B.	Profiles of Typical Final States	90

B.1.	Installed Information System	94

B.1.1.	Description	94

B.1.2.	Profile	94

B.2.	Tested Information System	96

B.2.1.	Description	96

B.2.2.	Profile	96

B.3.	Detailed Technical Design	97

B.3.1.	Description	97

B.3.2.	Profile	97

B.4.	Detailed Business Design	99

B.4.1.	Description	99

B.4.2.	Profile	99

B.5.	Information System Change study	101

B.5.1.	Description	101

B.5.2.	Profile	101

B.6.	Computer System Change study	103

B.6.1.	Description	103

B.6.2.	Profile	103

B.7.	Information System Documentation	105

B.7.1.	Description	105

B.7.2.	Profile	105

References	106

Index	107

# 1.	Introduction

## 1.1.	Objectives

The objectives of this Customer Guide are to:

¥	Provide guidance on how to apply the Euromethod concepts as a customer within the customer-supplier relationship found within an IS-adaptation. The guide supports the customer in bridging the cultural gap which frequently exists as part of this relationship. In particular, guidance will be provided to support the roles of customer contract authority and customer project authority.

¥	Provide guidance on applying the Euromethod concepts to both produce and assess the contractual products created during an IS-adaptation. That is, to provide guidance on how these concepts can be used by a customer to produce the IS-adaptation requirements during an IS-adaptation.

¥	Provide general guidance on how Euromethod interfaces with the day to day procurement and production process management activities performed by the customer.

¥	Provide guidance on how the customer should use the Euromethod concepts to support their work within each transaction, with particular emphasis on the deliverables to be exchanged and the decisions which must be made.

## 1.2.	TargetÊaudience

This guide is intended to be used by a customerÕs contract authority and project authority for IS-adaptations. These are the roles which:

¥	Hold the authority to make contractually binding arrangements with a supplier for a given procurement;

¥	Have the responsibility for managing the customer organisationÕs activities related to this procurement.

## 1.3.	Scope

The basic assumption for this guide is:

The management of the customer organisation have set out 
the goals of the procurement for which 
the contract and project authorities are responsible.

It is assumed that the decision on whether this goal will be achieved in a single IS-adaptation or in a series of IS-adaptations and all the decisions concerning the IS-adaptation is within the authority of this person or group of persons.

This guide assumes a context in which the following two elements are known:

¥	The starting point for the procurement of an information system, in terms of the state of the currently operational information system and the related documentation that is available.

¥	The business goal for the procurement of an information system, in terms of the changes to an operational information system and the related documentation that are required have been provisionally outlined.

The guide provides advice on:

¥	The necessity and options of splitting a procurement into a series of IS-adaptations or performing it within a single IS-adaptation.

¥	The planning of an individual IS-adaptation (in relation to the Delivery Planning Guide [EM-2.4-DPG]).

¥	The use of the Euromethod concepts in defining calls for tenders, contracts, deliverables, etc.

¥	The preparation of the individual transactions in an IS-adaptation.

## 1.4.	Style Considerations

The style in which the advice is presented in this guide, may at some points, look somewhat procedural and mechanistic. However, this does not mean that these ÒproceduresÓ have to be followed slavishly. Rather, they show what are prerequisites regarding the definition of, and decision making for, the production of certain IS-adaptation documents.

This guidance aims to help users of the guide to locate the answer to the problem they are currently addressing. In this way, the guide intends to help that person determine which step to take next, in order to provide the basis for a decision to be taken or in progressing some task.

The procedural style can also be used as a kind of checklist to avoid important activities and their dependencies being forgotten, but still allows activities which are considered to be irrelevant to be consciously omitted.

Layout and Symbols

Careful consideration has been given to the style of this guide to ensure that it makes reading easy, and thus has the ability to support the activities that Euromethod proposes. Each of the documentation features employed by this guide is now considered briefly.

Throughout the text of this guide a number of symbols are used that ease reading by giving graphical help for recognising the purpose of particular paragraphs.

Bullet Point Lists

These are used to emphasise enumerations. This can be used for several purposes:

¥	To highlight important terms; rather than hiding them in the text.

¥	To attribute additional information to terms; thus avoiding sentences that are too long and not well structured.

¥	To list topics that will be dealt with in subsequent sections.

Checklists

These are used to give direct support to the users of Euromethod.

There are some kind of question-answer checklists:

×	Are you just reading this guide to learn about the customer role?

=>	If so, the checklists provide you with some information.

×	Are you using this guide while performing a customer activity?

=>	If so, you should work through the checklists in order to achieve the correct results.

There are also checklist items that do not have a part prefixed with the arrow symbol. These just give you information on things to be considered in the customer's activities.

Some of the tables and matrices provided in the guide also serve as checklists. These are provided when they are more useful than the mechanism described above.

Reference Arrows

These appear in the left margin and indicate in which Euromethod Document and under which key words additional information and definitions on the topic discussed there can be found.

¥	Key word

¥	Key word

Reference to the other Euromethod Documents is also provided by using the document name in the text. This is especially the case, when the document as a whole is mentioned without reference to particular key words.

Reminder Notes

These are used to emphasise what should be kept in mind when reading the subsequent sections.

Remember: This section only gives a quick overview of the symbols used, not a detailed definition of a semantic of these symbols.

In those Reminder Notes that recall definitions the reference to the document that contains the definition is provided.

Highlight Boxes

Highlight boxes draw the readers attention to statements which are of general importance.

Knowing the symbols used eases using the guide.

Chapter Overview Sections

Special headers for the chapters which describe the preparation of customer-supplier transactions give a quick overview of the contents of the particular chapter. The contents of an overview section in this guide is:

| Purpose: | The objective of activities described in the chapter. |
| --- | --- |
| Activities: | List of the activities described in the chapter. |
| Results: | List of the results from the activities. |
| Concepts: | List of the Euromethod concepts used in the activities. |
| Checklists: | List of the checklists provided to support the activities. |
| Examples: | List of related Case Study examples. |

The example entry in each chapter overview section points to the appropriate chapters and sections in the Case Study document, where examples related to the presented guidance can be found.

Examples

Besides the case study examples that are references in the Chapter Headers, more general examples which are independent from the case study are used.

| Example | These example boxes are used for: ¥ Providing example information additional to the case studies. ¥ Small examples which serve to clarify points in the text. |
| --- | --- |

## 1.5.	Entry Points

This guide is intended to be used by both the contract authority and the project authority in the sense that the guidance provided is relevant to both of them. However, the perspective of the two roles is different.

¥	The point of view of the contract authority is:

ÒI have to ensure that the procurement results in a contract giving value for money and that the contract is effectively managed".

¥	The point of view of the project authority is:

ÒI have to ensure that the products are delivered to the required qualityÓ.

When reading the guides for the first time, it is advised that all the sections are read in the sequence in which they are presented.

Readers familiar with the guide can enter it from several points dependent upon their working situation within an IS-adaptation, i.e., depending upon the transaction that they are preparing for.

Thus their entry point to this guide can be:

¥	Chapter 3, to prepare for an IS-adaptation:

-	Production of a call for tender document.

¥	Chapter 4, to prepare for the transactions of the tendering process:

-	Issuing the call for tender.

-	Preparing the tender response transaction.

-	Preparing the supplier selection transaction.

-	Preparing the contract awarding transaction.

¥	Chapter 5, to prepare for the transactions of the production process:

-	Preparing an approval of deliverables transaction.

-	Preparing a approval of project status and plan transaction.

-	Preparing a contract change control transaction.

¥	Chapter 6, to prepare for the transactions of the completion process:

-	Preparing an approval of final deliverables transaction.

-	Preparing contract completion transaction.

# 2.	What is an IS-Adaptation

This chapter shows which parts of an IS-adaptation:~ contract can be formulated using Euromethod; and which Euromethod concepts are relevant for that purpose.

Remember: An IS-adaptation is any kind of modification (correction, enhancement, improvement, etc.) and automation of an information system; that is performed by a supplier for a customer in a contractual relationship 
[EM-4-ED].

A contract for an IS-adaptation must contain a precise description of the IS-adaptation in terms of what has to be delivered. Furthermore, it must define what the contribution of the contractual parties should be in the production of the delivered products.

Guidance on how to produce and execute an IS-adaptation contract and use the definitions is given to you in the following chapters. They describe how to use Euromethod in the tendering, production and completion processes respectively.

## 2.1.	IS-adaptations and the Services Directive

Remember: According to the Council Directive 92/50/EEC of 18 June 1992 (the Services Directive) a technical specification is defined as Òthe totality of the technical prescriptions contained in particular in the tender documents, defining the characteristics of a work, material, product or supply, which permits a work, a material, a product or a supply to be described in a manner that it fulfils the use for which it is intended by the contracting authority. [...]Ó [92/50/EEC]

The use of the term technical specification was first defined in the original Supplies Directive, 70/32/EEC. However, information systems were not covered until 1981. Consequently the term, technical specification was included within 92/50/EEC principally for historical reasons. The implication of this is that the term is not appropriate to completely address the need to define the requirements of IS-adaptations within tendering documentation. Indeed, the use of the term technical specification could create the wrong impression with Euromethod practitioners, since customers of IS-adaptations wish to provide requirements to suppliers which which will evntually be met by solution proposals, and the use of the term specification may suggest a solution. For this reason, although Euromethod supports the objectives of 92/50/EEC, Euromethod has defined its own terminology to support the technical prescriptions required by 92/50/EEC.

Euromethod supports the definition of an IS-adaptationÕs results and the planning of the IS-adaptation in terms of the deliveries to the customer which in the Euromethod terminology are called the IS-adaptation:~ requirements.

IS-adaptation requirements are part of all the documents exchanged in the tendering process.

Remember: In the Euromethod documents these are referred to as:

¥	The technical specification, in the call for tender of the customer;

¥	The technical proposal, in the tender response of the supplier;

¥	The technical annex, in the IS-adaptation:~ contract between the customer and supplier.

However, it should be noted that, in addition to the IS-adaptation requirements there is additional technical documentation required as part of the call for tender documentation. For example, in addition to the IS-adaptation requirements, you may provide information regarding the evaluation criteria which will be used in assessing the tender responses. Although this is referenced at the appropriate points within the Euromethod documentation, it is not supported in detail within the first version of Euromethod.

Euromethod facilitates a unified formulation of the IS-adaptation requirements in the tender documentation.

It does not address any other issues to be defined in IS-adaptation contracts; especially the financial and legal commitments.

Within this context, Euromethod defines the means to describe an IS-adaptation from the customer-supplier relationship point of view; and in particular provides the concepts and terminology needed to formulate IS-adaptation requirements (see Figure 1).

| Services Directive Terminology i.(i.e. IS-adaptation:~ requirements;) | Supporting Euromethod concepts |
| --- | --- |
| Defining the characteristics of a material, product or supply in a manner that it fulfils the use for which it is intended by the contracting authority. | This is supported by the concept of the final state of an IS-adaptation; which is based on the idea of characterising the result to be achieved through selecting properties of information systems that have to be specified or implemented. |
| Defining the characteristics of the work | This is supported by the concept of the delivery plan |

Figure 1: Euromethod support in formulating requirements for IS-adaptations.

The definition of technical specification in the Council Directive 92/50/EEC provides further detail in defining what the content of the technical prescriptions should be.

Remember: The Council Directive 92/50/EEC states:

ÒThese technical prescriptions shall include levels of quality, performance, safety or dimensions, including the requirements applicable to the material, the product or to the supply as regards quality assurance, terminology, symbols, testing and test methods, packaging, marking or labelling.Ó

The formulation of these issues is supported by the concepts defined in the deliverable model. Figure 2 provides an overview mapping of the relevant deliverable model concepts.

| Services Directive Terminology (i.e. IS-adaptation:~ requirements) | Supporting Euromethod concepts |
| --- | --- |
| Levels of quality, performance, safety or dimensions. | These are captured by the non-functional properties that can be defined as requirements of an information systems. |
| Requirements as regards quality assurance. | These are captured by the quality assurance plans and reports |
| Requirements as regards terminology. | This is supported through Euromethod as a whole as it defines a terminology for the tender documents. |
| Requirements as regards symbols. | The use and explanation of symbols and notations is supported through the method bridging capabilities of Euromethod |
| Requirements as regards testing and test methods | These are captured by the quality assurance plans and reports |

Figure 2: Euromethod support in formulating requirements for IS-adaptations.

Three types of procurement procedure are permitted within the Services Directive. These are the open, restricted and negotiated procedures.

From Figure 2, it can be seen that the definition of technical specification can be interpreted to permit the description of IS-adaptation:~ requirements. However, the negotiated procedure (See Article 11.2.c of the Services Directive) is regarded as the most flexible for information system procurements, since it does not demand the production of a technical specification. That is, it provides the customer with more flexibility in which to describe his business requirements within the call for tender.

When considering the procurement of information systems, generally the restricted and negotiated procedures are used.

All three procedures defined within the Services Directive may be undertaken using the Euromethod concepts.

The following sections consider how the three main issues of defining the IS-adaptation:~ requirements are addressed by the Euromethod concepts:

¥	Definition of the IS-adaptation result to be produced by the supplier,

¥	Definition of the customer involvement,

¥	Definition of the working relationship during the production of the IS-adaptation results.

This section has concentrated on the legal requirements which are applied to public procurement of information systems under the auspices of the Services Directive.

Remember:The Euromethod concepts and guidance are equally applicable within IS-adaptations:

¥	When the customer is in the private sector, as well as in the public sector.

¥	Performed within a single organisation and defined by an informal rather than formal contract (e.g. a Memorandum of Understanding).

## 2.2.	How are the SupplierÕs responsibilities described

The IS-adaptation results that have to be produced are defined by the final state of the IS-adaptation within the technical annex of an IS-adaptation:~ contract. The final state of an IS-adaptation contains:

¥	The final state information system (That is, a set of operational items providing enhanced functionality or performance).

¥	The operational items of a future information system that are produced as a result of this IS-adaptation, but which are not yet installed as part of the operational information system.

¥	The IS-descriptions that are produced as a result of this IS-adaptation and which the customer wants to use after the conclusion of this IS-adaptation. These IS-descriptions will address either:

-	The final state information system.

-	A future information system version.

¥	Plans for future IS-adaptations that are produced as part of this IS-adaptation.

It is this description of the final state that contains the core of the supplier's responsibilities within a proposed IS-adaptation.

| Example | The Euromethod definition of the final state of an IS-adaptation allows the definition of any kind of IS-adaptation. Examples of frequently encountered kinds of IS-adaptation are: - Development projects, which are mainly concerned with adding new operational items rather than replacing existing ones. - Maintenance projects, which are mainly concerned with the replacement of operational items rather than adding new ones. - Design projects, which are not changing the operational items installed in the information system, but produce IS-descriptions of a future information system. - Reverse engineering projects, which are not changing the operational items installed in the information system, but produce IS-descriptions of this information system. - Study projects like information system change study project. |
| --- | --- |

In some circumstances, a supplier may perform more than one IS-adaptation on behalf of a customer. In this instance, the supplier may help the customer to identify and plan for the technical dependencies within the project plans; and then manage these dependencies during the production and completion processes.

## 2.3.	How is the CustomerÕs Involvement described

The customer's involvement in an IS-adaptation depends on the nature of a particular IS-adaptation, and the activities involved in both contracting that IS-adaptation out to a supplier, and then participating in the customer-supplier transactions defined within the delivery plan. In addition, the customer may well participate in more informal relationships, such as providing operational expertise to the supplier's project authority.

In this way, the customerÕs involvement in the tendering process depends on:

¥	The IS-descriptions and operational items that must be made available to the supplier in order to facilitate the production of the desired results, as defined by the final state description.

¥	IS-descriptions

¥	Operational items

The customer's involvement in the production and completion processes is described in terms of:

¥	The products (e.g. packages, or existing data) that have to be fed into the production process

¥	Managing the dependencies between all the IS-adaptations that are currently proceeding,

¥	Planning the customer's involvement in terms of the human resources and materials that are required.

And last, but not least, the customer has to participate in the production process by:

¥	Taking their responsibility within the customer-supplier relationship and the decisions on the direction of the IS-adaptation being made. This responsibility may vary from an IS-adaptation to another: the customer may wish to take the overall control of the project or to give more or less control to the supplier.

That is, the customer's involvement is not limited to the provision of the initial state products.
The customer also participates in the production process by providing people and materials to the production process.

The decisions that the customer has to take, and thus their relationship with the supplier in terms of the customer-supplier transactions to be performed, is defined within the delivery plan, which is described in the following section.

These last points are very important within the context of Euromethod.
This is because Euromethod assumes that a customer makes informed decisions on the direction of the IS-adaptation.

However, it is recognised that there are other conceivable models of customer-supplier relationships!

| Example | In practice, a customer may avoid any responsibility for the technical direction taken by the IS-adaptation, thereby placing the entire risk for the IS-adaptation in the supplier's hands |
| --- | --- |

This is the customer's choice and the supplier must define how they intend to handle these differences to Euromethod proposed approach.

The initial state of an IS-adaptation and thus the products that have to be fed into and considered during the production process are defined in terms of:

¥	The initial state information system, i.e. the operational items contained in the operational information system at the beginning of the production process;

¥	The operational items of the future information system version that are available to the production process (they are constructed but not yet installed as part of the operational information system).

¥	And the IS-adaptation requirements i.e.

-	The IS-descriptions that are available and relevant to the production process. These can include both IS-descriptions of the initial state information system and IS-descriptions of the future information system version;

-	The delivery plan;

-	Possibly project plans (development plan, quality assurance plan, configuration management plan) for the IS-adaptation.

| Example | Examples of documentation related to the information system that can be input to an IS-adaptation are: - The design of the currently operational information system - The design of a planned successor version of the information system - Manuals (of application software, system software, hardware) - Documented observations of problems with the currently operating information system - Statements of business goals the successor version must support - The IS-strategy definition of the customer organisation etc. |
| --- | --- |

## 2.4.	How is the Customer-Supplier Relationship described

As mentioned above, the customer-supplier relationship with your chosen supplier during the production process of the IS-adaptation is described within the delivery plan.

¥	Delivery plan

¥	Decision point

This relationship is described by means of the following concepts:

¥	The decisions that must be made throughout the production, and completion processes including:

-	The target domain deliverables that are required to support each of the decisions to be taken.

¥	Target domain

¥	Project domain

-	The project domain deliverables that are required to support each of the decisions to be taken.

¥	The decision points sequence.

¥	The planning of the project domain issues for the phases between the decision points.

Customer-supplier transactions take place at decision points during the IS-adaptationÕs production and completion processes. In the course of these transactions the supplier delivers the deliverables, as defined in the delivery plan, to you. The customer must subsequently make the required decision about them.

The deliverables required for each of the transactions defined at the decision points, the initial state and the final state of an IS-adaptation have to be characterised by required deliverable profiles which are based upon the deliverable model.

Deliverables are described by required deliverable profiles.

A required deliverable profile defines the properties 
that have to be covered by a deliverable.

Guidance on the interpretation of the different types of Euromethod profiles is given within the Method Bridging Guide.

¥	Method Product Profiles

¥	Method Deliverable Profiles

¥	Required Deliverable Profiles

At the beginning of the production process (or when required during the production process), the products that constitute the initial state of the IS-adaptation have to be provided (that is, the existing products that match the profiles of the initial state definition) by the customer.

The deliverables which match the required deliverable profiles are produced during the production process. These are then delivered, as defined by the delivery plan, in order for you to make the decision within the appropriate customer-supplier transaction at a decision point (see FigureÊ3).

Figure 3: Euromethod support for tendering documents.

## 2.5.	Role Assignment in an IS-adaptation

It is important to appreciate the conceptual difference that exists between these IS-adaptation roles and the organisational roles found within your organisation, when using the Euromethod role concepts within an IS-adaptation. That is, unlike organisational roles which are usually long in duration, stable for some time, and applied to everything that role does within the organisation; IS-adaptation roles only exist within the context of a single IS-adaptation.

The IS-adaptation roles defined in Euromethod are:

¥	Contract Authority;

¥	Role Concepts

¥	Project Authority;

¥	Operational Expertise;

¥	Organisational Authority.

IS-adaptation roles represent authorities and responsibilities, and
the skills and knowledge provided to a single IS-adaptation.

In an IS-adaptation, each role may be performed by a single person or a group of people. A single person can also perform several roles.

| Example | ¥ A "project director" managing the supplier's work may perform the project authority role and at the same time provide operational expertise to the work. .¥ Operational expertise is generally provided by a group of people e.g. the project team. |
| --- | --- |

Lastly, it should be noted that IS-adaptation roles are not directly comparable to the role definitions found within development methods.

In defining an IS-adaptation and in performing the customer-supplier transactions, it is necessary to assign the IS-adaptation roles to people in your organisation. The rest of this section provides guidance on how this can be achieved and then monitored within an IS-adaptation.

IS-adaptation roles place requirements upon the organisational roles and the skill set of the people they are assigned to. In deciding whether a person within your organisation is appropriate  for a certain IS-adaptation role the following checklists should be followed.

General issues to be resolved for every role assignment is:

×	Should the role assignment be for the whole IS-adaptation or should it change at defined points?

-	Does the move from the tendering process to the production process require a change in the role assignments?

-	Should the role assignments be the same for every decision point or are changes necessary due to the decisions that have to be made?

×	Are the selected persons available to perform all the activities related to their involvement in the IS-adaptation?

Assigning the Contract Authority

Remember: A contract authority  is the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation contract. 
It is not necessary, or necessarily desirable that the same person acts as the contracting authority for every transaction within a given IS-adaptation.

A person is normally assigned the role of contract authority by a member of the organisation's senior management.

When assigning the contract authority role to a person the following apply:

×	The person must have the necessary authority within the organisation for signing contractual documents.

×	The person must have the necessary budgetary authority to manage a contract.

Besides these prerequisites, some questions concerning the skills of the person be nominated for contract authority may be asked, e.g.:

×	Is the person able to define appropriate tendering strategies?

×	Is the person suitably skilled in customer-supplier relationships?

×	Is the person a skilled and experienced negotiator?

When using the checklists, it is important to recall that the customer is managing the business risk associated with the IS-adaptation, while the supplier is managing the technical risk.

Assigning the Project Authority

Remember: A project authority  is the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation project. 
It is not necessary, or necessarily desirable that the same person acts as the project authority for every transaction within a given IS-adaptation.

The constraint put on the organisational role of the person being assigned the project authority role is:

×	The person should have a proven record of managing projects within the customer organisation.

Furthermore, when assigning the project authority role to a person the following questions apply:

×	Is the person suitably skilled in customer-supplier relationships?

×	Does the person have the necessary leadership skills?

×	Does the person have the necessary bid management and technical skills, if he/she has to be involved in the tendering process?

×	Does the person have the necessary technical skills for the production and completion processes, if he/she has to be involved in the production process?

Selecting people to provide Operational Expertise

Remember: An operational expertise role is the role of a person or persons performing a development task or acting as an opinion maker based upon their expertise, skills or knowledge with regard to a specific IS-adaptation topic.

A person is normally assigned to provide operational expertise by the project authority in performing the delivery planning for an IS-adaptation.

In selecting the  people to perform the activities required under the management of the .i.project authority, the following question should be answered:

×	Does the person have the necessary business, technical or user skills to perform the tasks required of the operational expertise role as required by the IS-adaptation requirements?

At the end of this exercise, you will have established who in your organisation has the required expertise to undertake particular responsibilities within the IS-adaptation and is currently available.

Identifying the Organisational Authorities

Remember: An organisational authority is the role of a person or persons with the power to resolve or conclude an open issue with regard to the strategic requirements of the organisation.

Decisions made by a contract authority may be influenced by an organisational authority within the organisation, such as the senior customer , the financial authority or legal authority etc. The implication of this is that, in some circumstances, a decision can be imposed upon the contract authority by one of these organisational authorities.

In identifying the organisation authorities which have a stake in the progress of the IS-adaptation, the following should be considered:

×	Is the IS-adaptation important on a strategic point of view ?

=> If the answer is yes, then your senior management's view is important.

×	Is the IS-adaptation important on a financial point of view ?

=> If the answer is yes, then your financial authority's view is important.

×	Is the IS-adaptation affected by legal arrangements such as the EU directives or EU/GATT trade agreements ?

=> If the answer is yes, then your legal authority's view is important.

×	Are certain legal aspects of the contract regarding this IS-adaptation critical ?

=> In this situation, your legal authority's view is important.

×	Are the quality management requirements defined and being adhered to?

=> If this is the issue, your QM-Authority's view is important.

Completing the mapping of the IS-adaptation roles

Once the IS-adaptation assignments have been established, you are in a position to complete the mapping to the decision point descriptions found within a delivery plan. The following checklist is an aid to ensuring that all the decision point descriptions are complete from the IS-adaptation roles perspective:

¥	Document delivery plan

×	Have you decided what IS-adaptation roles are required for all the decision point descriptions?

×	Have you decided what level of resourcing will be required for each IS-adaptation role in each transaction within the decision point descriptions?

# 3.	How to prepare the Call for Tender Transaction

| Purpose: | The purpose of the preparation of a call for tender transaction is to produce a call for tender document that can be used to initiate an IS-adaptation. |
| --- | --- |
| Activities: | Besides documenting the IS-adaptation requirements in the call for tender, activities have to be performed to identify the risks associated with the envisaged IS-adaptation, and to reduce these risks. |
| Results: | The result of these activities is a definition of IS-adaptation requirements within the call for tender taking into account decisions to reduce risks. |
| Concepts: | ¥ Delivery plan, initial state, final state, sequence of decision points. ¥ Typical initial and final states. ¥ Problem situation assessment, delivery planning |
| Examples: | For examples, you are referred to the following Case Study chapters [EM-2.5-CS]: ¥ Chapter 3 - Preparation of a Call for Tender (for NAS) ¥ Chapter 10 - Preparation of a Call for Tender (for Eu-Rent) |

The previous chapter introduced the capabilities of Euromethod in defining IS-adaptation requirements. The next chapters look at the process of producing such a definition of requirements. This chapter describes the support Euromethod can give in preparing for a tendering process. The following chapter will look at the preparation of each of the customer-supplier transactions in the tendering process. It describes the support Euromethod can give during a tendering process.

In the course of these two chapters, you will see how the definition of the IS-adaptation evolves, including a discussion of the decisions which have to be taken before and during the tendering process.

Remember: The tendering process of an IS-adaptation starts with the issuing of a call for tender and lasts until the signing of the contract for this IS-adaptation with the chosen supplier. [EM-3.1-TM]

If the IS-adaptation:~ requirements have been defined using Euromethod within either a call for tender, tender response or IS-adaptation contract's technical annex, they consist of:

¥	The IS-descriptions that are available and relevant to the production process. These can include both IS-descriptions of the initial state information system and IS-descriptions of the future information system version;

¥	The delivery plan;

¥	The project plans (development plan, quality assurance plan, configuration management plan) for the IS-adaptation, if applicable.

Document evolution

These definitions are not produced in a single step, but undergo an evolution during the preparation for the IS-adaptation and the IS-adaptationÕs tendering process.

The description of the delivery plan for the production process including the description of the initial and final state of the IS-adaptation evolves throughout the tendering process and is finally fixed in the IS-adaptation contract.

This means that once a decision has been made to go out to tender, which includes the decision on what the final goal of the procurement is; your organisation has to perform a number of activities to facilitate the tendering process of the envisaged IS-adaptation. These activities include:

¥	The preparation and production of a call for tender document.

¥	The initiation and execution of a tendering process;:

-	The issue of a call for tender.

-	The receipt and evaluation of the tender responses.

-	The selection of a supplier.

-	The production and signing of an IS-adaptation:~ contract.

The preparation of a call for tender produces the document which is exchanged in the call for tender transaction, thereby initiating the envisaged IS-adaptation.

Procurement goals and call for tender activities

The preparation of a call for tender involves two indispensable activities:

¥	It must describe what products are to be produced during the IS-adaptation in order to meet the business requirements;

this will be the first version of the final state required deliverable profile.

¥	It must describe which products will have to be provided as input to the IS-adaptation, in order to express the business requirements;

this will be the first version of the initial state required deliverable profile.

The first is the formulation of the procurement goal that was decided by your organisationÕs senior management or of the intermediate goal selected, in the situation where there shall be several IS-adaptations.

Basically, these two descriptions together with the dates on which you intend to start the production process and terminate the completion process of the IS-adaptation are the information you have to provide in your call for tender to allow potential suppliers to provide a tender response.

But, there is a crucial decision you have to make in the preparation of the call for tender.

Before issuing a call for tender you have to decide
whether to achieve the goal of the procurement in

¥	a single IS-adaptation or

¥	a series of IS-adaptations.

This decision can be influenced in two ways:

1.	You may be constrained by the internal rules of your organisation to go for a certain series of IS-adaptations (e.g. budget limitations etc.).

2.	Your decision depends on the way you want to handle the risks associated with the particular procurement.

If you decide, or are constrained, to perform a series of IS-adaptations you can handle the tendering of each of them by describing each IS-adaptation that you envisage in terms of its delivery plan, and in particular the initial and final states defined by the delivery plan. In this case, the initial state of a subsequent IS-adaptation can generally be derived directly from the final state of the previous one. This scenario is represented in Figure 4.

Figure 4: Reaching a procurement goal.

If you are not constrained by a pre-defined sequence of IS-adaptations, or have to choose between several possible pre-defined options then the following sections provide some assistance in making your decision.

## 3.1.	How to identify Risks in the Tendering Process

Euromethod provides you with two means to assess risks associated to the IS-adaptation that you are about to undertake. These are:

¥	Assessment of the combination of the initial and final state of the envisaged IS-adaptation based on patterns of typical initial and final states of IS-adaptations.

¥	Assessment of the problem situation based on the Strategy Model and the Delivery Planning Guide.

The first gives you a very rough, but quick indication as to whether it is advisable to split the envisaged IS-adaptation into several IS-adaptations, while the latter helps you to define the strategy for the IS-adaptation under consideration.

That is, the second approach is more detailed, since it provides more elaborate indications, and also requires a bigger analysis effort. Nevertheless, this should not be regarded as simply an overhead and extra work, as most of the exerciseÕs results can be re-used later in the evaluation of the tender responses and some of it must be done at that time anyway. It may also prevent the occurrence of some undesired consequences within the IS-adaptation. Furthermore, this list of risks identified in the analysis of the problem situation can be revisited at other decision points during the IS-adaptation to assess whether the likelihood or consequences have changed.

### 3.1.1.	Assessment of Initial and Final State

Although every individual IS-adaptation tackles an individual problem and is thus unique, a set of typical initial and final states can be recognised:

¥	The notion of typical final states recognises that there are certain combinations of products which generally appear as final states of IS-adaptations. This is because in their totality they provide a useful result to a customer.

¥	The notion of typical initial states recognises that there are certain combinations of a customerÕs information system and its related IS-descriptions which can generally be encountered at the start of an IS-adaptation.

These typical initial and final states are listed in Figure 5. Short descriptions of each typical initial and final state are provided subsequent to this section. The profiles describing the typical initial and final states can be found in the annexes of this guide.

Take note!	Typical initial and final states only give examples of start and end points of IS-adaptations. They do not recommend a sequence of decision points inside a single IS-adaptation. For this reason the expression Òtypical initial and final statesÓ is always used and any abbreviation of this expression is avoided since it might convey the wrong impression.

General experience shows that some combinations of initial and final states tend to result in projects that are difficult to control. This is mainly because the initial state is not elaborated enough to reduce the uncertainties to be resolved in progressing towards the final state.

You can use these facts as a guide on how and whether to split your envisaged IS-adaptation into several IS-adaptations.

To use the typical initial and final states you have to do the following:

1.	Position the descriptions of your envisaged IS-adaptationÕs initial and final state against the appropriate combination of typical initial and final states provided by Euromethod.

2.	Check whether these typical initial and final state types constitute any of the non advisable combinations.

If this is the case you have identified a potential risk in your envisaged IS-adaptation. The section ÒHow to reduce risks in the tendering processÓ will give you some options and advice on what to do in this case.

In any case, you can take a closer look at your situation by performing a situation analysis, either to confirm your view that the envisaged IS-adaptation will be manageable, or to find out more detail about the risks associated with your choice.

¥	situation analysis

The table in Figure 5 shows from which initial states the progression to the different final states is generally achieved in a single IS-adaptation, and for which ones splitting the IS-adaptation or explicit contract change control should be considered.

The table represents an assessment of the uncertainties, for example related to feasibility or cost, that are associated with an IS-adaptation, and which have to be managed while progressing from the initial to the final state.

Some of the typical initial and final states consist of similar combinations of deliverables. In this case the same name is given to the typical initial state and the typical final state.

Such typical initial and final states provide points where an IS-adaptation could be split into two subsequent IS-adaptations; the first one ending with the typical final state and the second one resuming with the typical initial state.

| Final State Initial State |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Undocumented Information System | Ã | Ã | Ã | ! | ! | ! | ! |
| Documented Information System | Ã | Ã | Ã | ! | ! | ! | ! |
| Problem Description | - | Ã | Ã | Ã | ! | ! | ! |
| Global Design | - | Ã | Ã | Ã | Ã | ! | ! |
| Detailed Business Design | - | - | - | Ã | Ã | Ã | Ã |
| Detailed Technical Design | - | - | - | - | Ã | Ã | Ã |
| Tested Information System | - | - | - | - | - | Ã | Ã |
| Key: | Ã ! - | Generally a single IS-adaptation. Splitting the IS-adaptation or explicit contract change control should be considered. Invalid combination. |  |  |  |  |  |

Figure 5: Combinations of initial and final states.

Analysing your envisaged IS-adaptation by matching the initial and final state against the typical initial and final states defined by Euromethod, gives you a first impression of risks associated with your IS-adaptations.

| Example: | In Germany, a set of standard regulations, the BVB (Òbesondere VertragsbedingungenÓ), is used in IS-adaptation contracts. These distinguish between IS-adaptation contracts for: ¥ ÒPlanungÓ (Planning): These support contracts with final states up to Detailed Business Design [BVB-Planung]. ¥ ÒErstellungÓ (Production): These support contracts with final states from Detailed Technical Design to Installed Information System [BVB-Erstellung]. With these two types of contracts some of the critical combinations cannot occur any more. |
| --- | --- |

This is not an absolute judgement, but only an initial sign. There can always be particular situational factors which can alter that judgement.

For example:

¥	An IS-adaptation starting with Problem Description and ending with Installed Information System may well be manageable although the table characterises these as a critical combination; for example if the target domain is very small or the requirements to the information system are well known. (The NAS Case Study [EM-2.5-CS] is an example of such a situation.)

¥	An IS-adaptation starting with Detailed Business Design and ending with Detailed Technical Design, which is marked as being generally manageable, may be very difficult to manage just because the project situation is very difficult; for example because of a big number of sub-contracts, resistance against the acceptance of the IS-adaptation, external interfaces, etc.

Anyhow, in case of doubt, a proper situation analysis is indispensable to elicit the risks associated with an IS-adaptation; and to define the suitable strategy to reduce these risks.

The Typical Final States

The typical final states are:

¥	Information system documentation.

¥	Information system change study.

¥	Computer system change study.

¥	Detailed business design.

¥	Detailed technical design.

¥	Tested information system.

¥	Installed information system.

The following text gives short descriptions of the typical final states. More elaborate descriptions and the deliverable profiles of the typical final states are provided in Annex B; which is intended to be a reference you can use when positioning an envisaged IS-adaptation against the typical final states:

Remember: A requirements statement defines an essential condition that the information system under consideration has to satisfy.

Thus a target domain deliverable stating requirements of the considered information system, is a deliverable that defines conditions for a set of IS-properties that the specification of these IS-properties must cover.

A specification is a product that provides a definitive description of an information system for the purpose of developing or validating it.

Thus a target domain deliverable which provides a specification of the considered information system, is a deliverable that defines a set of IS-properties of this information system.

A prototype is an operational trial model suitable for evaluating an information system specification or for better understanding or determination of requirements.

Thus a prototype is a target domain deliverable which is an operational system that reflects a set of IS-properties. [EM-3.2-DM]

¥	An information system documentation typically results in:

-	Detailed specifications of the work practices and the computer system architecture of the current operational information system.

-	Detailed requirements statements for the work practices and the computer system architecture, showing to which requirements the current operational information system was built.

This typical final state is mostly encountered in situations where the documentation of an old and poorly documented computer system is to be brought to a status where it can serve as useful input to subsequent IS-adaptations. Another purpose for having such an IS-adaptation is to resolve uncertainties that result from poor knowledge of the existing computer or information system; and that are a significant risk to other IS-adaptations.

¥	An information system change study typically results in options for:

-	Global specifications and/or prototypes of the business processes, the business information and work practice views.

-	Global requirements statements for the business processes and information and for the work practices and computer system architecture views.

¥	A computer system change study typically results in options for:

-	Global specifications and/or prototypes of the work practices and the computer system architecture and related global specifications of the business processes and the business information.

-	Global requirements statements for the work practices and computer system architecture and the business processes and information.

These two typical final states are generally applied in situations where the envisaged IS-adaptation is intended to provide documentation for decision support, for example for changes of business practices or investments in computer system hardware or system software. The current operational information system is left unchanged. It should be noted that these two typical final states serve similar purposes and it is possible to have a final state which is in fact a combination of the two.

¥	An IS-adaptation achieving a detailed business design typically results in:

-	Detailed specifications (and/or prototypes) and requirements statements of the business information view, business process view and work practices view of a new information system version.

-	Global specifications (and/or prototypes) and requirements statements for the computer system data, functions and architecture, illustrating the feasibility of the detailed business design.

¥	An IS-adaptation achieving a detailed technical design typically results in:

-	Detailed specifications and/or prototypes of the work practices and the computer system data, functions and architecture of a new information system version.

-	Detailed requirements statements for the work practices and the computer system data, functions and architecture, relating the requirements to the specifications.

IS-adaptations that result in a final state similar to one of the previous two typical final states leave the current operational information system unchanged but provide the input documents to possible subsequent IS-adaptations. In doing this they also represent typical initial states of IS-adaptations; and thus provide you with a guide on possible points for splitting an IS-adaptation into several.

¥	An IS-adaptation achieving a tested information system typically results in:

-	Operational items of a new information system version, which can replace some or all the operational items of the currently operational information system.

-	Detailed specifications of the work practices and the computer system architecture of the new information system version.

-	Detailed requirements statements for the work practices and the computer system architecture, relating the requirements to the new information system version .

Again the current operational information system remains unchanged. The new version is tested and only needs installation in the target domain. Such a final state is typically encountered, when e.g. the installation of the computer system is so complex that it should be handled as a separate IS-adaptation, or when the organisational changes to the target domain are such that the customer wants to perform these internally.

¥	An IS-adaptation achieving an installed information system typically results in:

-	A new operational information system version, where some or all the operational items are replaced by new ones.

-	Detailed specifications of the work practices and the computer system architecture of the new operational information system version.

-	Detailed requirements statements for the work practices and the computer system architecture, relating the requirements to the new operational information system version.

IS-adaptations having a final state similar to this typical final state, are IS-adaptations where the current operational information system is actually changed into a new installed version. Additionally, the design documentation of the new information system version is produced.

All of the typical final states may include delivery and project plans for subsequent IS-adaptations. As mentioned above, descriptions of the typical final states in terms of the views of the deliverable model are provided in Annex B.

The Typical Initial States

The typical initial states are:

¥	Undocumented information system.

¥	Documented information system.

¥	Problem description.

¥	Global design.

¥	Detailed business design.

¥	Detailed technical design.

¥	Tested information system.

The following text gives short descriptions of these typical initial states. More elaborate descriptions and the deliverable profiles of the typical initial states are provided in Annex A; which is intended to be a reference which can be used when positioning an envisaged IS-adaptation against the typical initial states.

All the typical initial states include the current operational information system, and thus its operational items. They will include a delivery plan and may include project plans for the envisaged IS-adaptation.

Remember: A requirements statement defines an essential condition that the information system under consideration has to satisfy.

Thus a target domain deliverable stating requirements to the considered information system, is a deliverable that defines conditions for a set of IS-properties that the specification of these IS-properties must cover.

A specification is a product that provides a definitive description of an information system for the purpose of developing or validating it.

Thus a target domain deliverable which provides a specification of the considered information system, is a deliverable that defines a set of IS-properties of this information system.

A prototype is an operational trial model suitable for evaluating an information system specification or for better understanding or determination of requirements.

Thus a prototype is a target domain deliverable which is an operational system that reflects a set of IS-properties. [EM-3.2-DM]

¥	For an IS-adaptation starting from an undocumented information system, the initial state typically consists of:

-	The current operational information system version, without any supporting documentation; or

-	A version of the current operational information system documentation which is either rudimentary, or of poor quality; or

-	Documentation which is no longer consistent with the current operational information system version.

Such an initial state can occur, if over a period of time changes to the operational system have been made without keeping track of these changes.

¥	For an IS-adaptation starting from a documented information system, the initial state typically consists of:

-	Detailed specifications of the work practices and the computer system architectureof the current operational information system.

-	Detailed requirements statements for the work practices and the computer system architecture, to which the current operational information system was built.

-	Operational items.

Such an initial state typically occurs if an IS-adaptation is the successor to an IS-adaptation with a final state similar to Installed Information System or Information System Documentation.

¥	For an IS-adaptation starting from a problem description, the initial state typically consists of:

-	Global specifications of the business processes and the business information and work practice views of the current operational information system.

-	Global requirements statements for the business processes and information and for the work practices and computer system architecture views of the future information system.

¥	For an IS-adaptation starting from a global design, the initial state typically consists of:

-	Global specifications and/or prototypes of the work practices and the computer system architecture and related global specifications of the business processes and the business information of the future information system.

-	Global requirements statements for the work practices and computer system architecture and the business processes and information views of the future information system.

The initial states like the previous two typical initial states are generally encountered, if the envisaged IS-adaptation is a successor to an IS-adaptation which had a final state similar to Computer System Change Study or Information System Change Study respectively.

¥	For an IS-adaptation starting from a detailed business design, the initial state typically consists of:

-	Detailed specifications (and/or prototypes) and requirements statements of the business information, business processes and work practices of a new information system version.

-	Global specifications (and/or prototypes) and requirements statements for the computer system data, functions and architecture, illustrating the feasibility of the detailed business design.

¥	For an IS-adaptation starting from a detailed technical design, the initial state typically consists of:

-	Detailed specifications and/or prototypes of the work practices and the computer system data, functions and architecture of a new information system version.

-	Detailed requirements statements for the work practices and the computer system data, functions and architecture, to which the design was built.

¥	For an IS-adaptation starting from a tested information system, the initial state typically consists of:

-	The operational items that constitute the new information system version.

-	Detailed requirements statements for the work practices and the computer system architecture, to which the new information system version was built.

-	Detailed specifications of the work practices and the computer system architectureof the new information system version.

Such an initial state typically occurs if an IS-adaptation is the successor to an IS-adaptation where a new information system version was constructed but not installed, for example because the installation in itself is complex and difficult to achieve..

### 3.1.2.	Delivery Planning

In order to analyse the potential risks associated with an envisaged IS-adaptation based on the Delivery Planning Guide you have to:

¥	Produce an additional document, the situational factor:~s table, which provides a description of the situation and IS-adaptation in terms of the situational factors.

¥	Assess Problem Situation

¥	Produce a provisional delivery plan for your envisaged IS-adaptation.

Like the initial and final state descriptions these documents will evolve throughout the tendering process. Indeed, later on the situational factors table will play a role in evaluating the technical proposals of the tender responses and the final version of the delivery plan will become part of the IS-adaptation contract.

In preparing the call for tender transaction, you can use these two products to review your envisaged IS-adaptation before issuing the call for tender. A review of the envisaged IS-adaptation can result in changes to a straight forward tendering of the procurement goal within a single IS-adaptation:

¥	The delivery planning may reveal that the initial state is not sufficient for the production of a tender response.

¥	The description of the project situation might reveal that it bears risks that your organisation does not want to take.

In each of these cases you can take actions before issuing or producing the call for tender which allow improvement of the organisational situation. Options for these actions are described later in the section ÒHow to reduce the risks in the tendering processÓ. As mentioned earlier, it should be remembered that the list of risks identified in the analysis of the problem situation can be revisited at other decision points during the IS-adaptation to assess whether the likelihood or consequences have changed.

The necessary inputs for this initial version of the delivery plan (sometimes thought of as a provisional delivery plan) are:

¥	The description of the initial state of the IS-adaptation, documented by a set of deliverable profiles.

¥	The description of the final state of the IS-adaptation, documented by a required deliverable profile.

¥	The description of the project situation, documented by a situational factors table including the textual description which supports the choice of each situational factor:~ value.

How to describe a problem situation in terms of situational factors is defined in the Delivery Planning Guide [EM-2.3-DPG]. There you will find all the information necessary to interpret and document your organisational situation in the IS-adaptation in terms of the situational factors defined in the strategy model.

¥	Assess Problem Situation

This guide also tells you how to produce a delivery plan based on the three products listed above. All the information is provided on how to use the strategy model for determining a strategy for the IS-adaptation and how to use the deliverable model and the transaction model to produce a delivery plan that implements that strategy.

¥	Delivery planning

The review of the tendering process by means of a provisional delivery plan assumes that:

If you cannot plan a project now

you may not be able to control it in the future.

Assessment of delivery planning results

Thus, the exercise of producing a provisional delivery plan can have two results:

1.	It can succeed, in the sense that it results in a delivery plan that has been completed in sufficient detail to define the deliveries needed throughout the whole production process up to the final delivery within the completion process.

In this instance, the delivery plan is an indicator that the envisaged IS-adaptation is of a manageable size and can be performed without major risks. Furthermore, a call for tender can be produced and issued based on the existing documentation.

2.	It can fail, in the sense that it results in a delivery plan that does not define the deliveries up to the end of the production process. In this case, it is most likely, that the delivery plan contains a contract change control transaction after which no further deliveries could be planned.

This is an indicator that for you, from your customer perspective, the envisaged IS-adaptation is currently not of a manageable size, and that the risks associated with the project situation do not allow you to manage the complexity and uncertainty associated with the IS-adaptation in question. In this case, there is a significant risk in issuing a call for tender based on the existing information.

Whenever such a situation occurs, corrective action should be considered in order to minimise the risks associated with the characteristics of this particular IS-adaptation.

Associated risks

Examples of risks that are associated with the tendering process of an IS-adaptation, for which the production process cannot be planned are:

¥	No supplier answers the call for tender, because the supplier organisations consider the IS-adaptation as, for example, unfeasible or too risky financially.

¥	The costs associated to the IS-adaptation proposals offered in tender responses are very high, because the suppliers have had to incorporate a large contingency within the plans to cover the calculated financial risks.

¥	The production process of the IS-adaptation will result in failure because the IS-adaptation was unfeasible in the first instance.

¥	The cost of the IS-adaptation will be uncontrollable.

The likelihood of these risks occurring can, in part, be offset by undertaking business practices commonly associated with the tendering process. For example, the supplier can obtain clarification regarding the IS-adaptation:~ requirements within the call for tender by questioning the customer. These responses can be used to facilitate the production of a technical proposal within the tender response which at least partially offsets the observed risks.

## 3.2.	How to reduce Risks in the Tendering Process

As there are three parameters that determine the characteristics of an IS-adaptation, the initial state, the final state and the problem situation, each of these parameters offers the potential of improving the characteristics of an IS-adaptation.i.risk;

Thus, the basic options for corrective action are:

¥	The initial state is amended.

¥	The problem situation is altered.

¥	The expectations of the final state are reduced.

Besides these options, there is still the possibility of not taking any action and to issue a call for tender based on the existing information.

The rationale for such a decision is that the risk of not receiving any tender responses or too expensive ones is considered to be low. You can therefore assume that the technical problems associated with the IS-adaptation are solvable for suppliers that have the necessary knowledge and experience.

### 3.2.1.	Amendment of the Initial State

If it is considered that the initial state, as it is currently defined, is not sufficient to perform the IS-adaptation because it introduces unmanageable uncertainties into the process, you can consider how to improve the initial state to the point where these uncertainties are resolved and the IS-adaptation becomes feasible and manageable.

This amendment to the initial state can be achieved in different ways:

¥	You can identify and provide additional available documentation that can serve as input to the IS-adaptation.

¥	If no suitable documentation exists you can internally (possibly assisted through consultancy) produce the documentation that is required for a sufficient initial state.

¥	If your organisation is not able to perform that task (for example, because of resource or capability limitations) the decision can be made to have it done in an IS-adaptation, that is performed prior to the currently envisaged one.

In this case the envisaged IS-adaptation is split into sequential IS-adaptations:

¥	A first, that establishes the required initial state based on the documentation currently constituting the initial state.

¥	A second, that produces the desired final state based on the, by then available, required initial state.

This actually demonstrates how a procurement can be decomposed into a series of IS-adaptations.

You can use the typical initial and final states to define the interfaces between the different IS-adaptations.

Complex IS-adaptation scenarios

Another way of enhancing the initial state of your envisaged IS-adaptation before issuing the call for tender is to get information from potential suppliers beforehand. These more complex exercises, however, can be viewed as a tendering process, where iterations of the customer-supplier transactions are introduced. The following examples illustrate these more complex tendering scenarios:

| Examples: | ¥ Prior to the issue of the call for tender, different suppliers may be contacted with "requests for information" by the customer. Thus, this informal iteration consists of a call for tender and a tender response transaction prior to the issue of the call for tender for the envisaged IS-adaptation. ¥ In response to a provisional call for tender, a shortlist of suppliers can be produced based upon an evaluation of their outline IS-adaptation proposals (thereby also reducing the costs incurred by suppliers who, based on their proposals, are unlikely to be awarded the contract). In this instance, the tendering process consists of an iteration of a call for tender, a tender response and a supplier selection transaction prior to the issue of the call for tender for the envisaged IS-adaptation. |
| --- | --- |

Repeating transactions with potential suppliers provide you with additional documentation concerning your envisaged IS-adaptation. Consequently, the initial state of the IS-adaptation is enhanced; possibly enough to make the envisaged IS-adaptation manageable. Whether you follow a single pass through the tendering process, or whether you define a tendering approach which resembles the complex examples outlined within the Transaction Model, you should try to present business requirements, rather than any specification or solution oriented documentation to the supplier.

¥	Tendering Process

### 3.2.2.	Change the Situational Factors

If it is considered that the risks associated with the currently envisaged IS-adaptation do not result from an insufficient initial state, but are caused by the project situation of the envisaged IS-adaptation, the decision can be made to improve this situation.

To define the necessary corrective action a situation analysis, documented in a situational factor:~s table, is required.

In the analysis of the situation you will find situational factors whose s indicate a high uncertainty or complexity in your envisaged IS-adaptation.

You will not be able to change some of these factors, because they are inherent to the problem you want to solve with the envisaged IS-adaptation. Nevertheless, for other factors you may have the opportunity to change them for the better.

The explanations that support the values given to the situational factors can indicate such opportunities of improvement.

¥Change individual situational factors

| Example: | ¥ Training of the people who will be involved in the IS-adaptation as information system actors, if their capability or motivation is considered to be low. ¥ Use of external consultancy, if the information system actorÕs capability is considered to be low, and improvement cannot be achieved. |
| --- | --- |

### 3.2.3.	ReducingÊtheÊExpectationsÊtoÊtheÊFinalÊState

Reducing the scope of the final state is not really an option for alteration within the authority of the contract authority. The IS-adaptation was launched in order to achieve a certain business goal which will not be met if the final state is reduced. Any change to this must therefore be handled at senior management level within the organisation.

This means, that if all other means of reducing the risk or uncertainty of the IS-adaptation fail, this probably requires a review of the IS-strategy and a decision at the senior management level to revise the procurement goals.

# 4.	How to use Euromethod in the Tendering Process

| Purpose: | The purpose of the tendering process is to find a supplier who will produce the deliverables that satisfy the IS-adaptation requirements; and establish an IS-adaptation contract with this supplier. |
| --- | --- |
| Activities: | To achieve this, the IS-adaptation must be initiated by issuing the call for tender and the customer-supplier transactions of the tendering process must be prepared and performed. |
| Results: | At the end of this process there will be an IS-adaptation contract with the chosen supplier, in which the IS-adaptation requirements that are consistent with the customerÕs business needs and that can be met by the suppliers deliverables are defined. |
| Concepts: | ¥ Open, restricted, negotiated tender. ¥ Delivery plan, initial state, final state, sequence of decision points. ¥ Customer-supplier transaction. ¥ Situation analysis, delivery planning |
| Checklists: | ¥ Composition of a tender evaluation team |
| Examples: | For examples see the following sections of the case studies [EM-2.5-CS]: ¥ Chapter 6 - Preparation of the Supplier Selection (for NAS) ¥ Chapter 7 - Preparation of the Contract Awarding (for NAS) |

The previous chapter described the preparation of a call for tender, that is, it described the Euromethod support prior to the initiation of a tendering process.

This chapter will look at the preparation of each of the customer-supplier transactions within the tendering process, that is, it describes the support Euromethod can give during a tendering process. Nevertheless, you should not forget that familiar customer-relationship practices will continue, in parallel with the Euromethod supported activities such as ongoing customer-supplier question and answer sessions. For example, the supplier can obtain clarification regarding the IS-adaptation:~ requirements within the call for tender by questioning you and receiving the responses in the normal way. These responses can be used to facilitate the production of a technical proposal within the tender response.

In the course of this chapter, you will see how the definition of the IS-adaptation evolves from the description given in the call for tender to the finalised definition in the IS-adaptation contract, which includes a discussion of the decisions which have to be taken during the tendering process.

Remember: The tendering process of an IS-adaptation starts with the issuing of a call for tender and lasts until the signing of the contract for this IS-adaptation with the chosen supplier. [EM-3.1-TM]

This means, that once the call for tender has been produced (and the decision to go out to tender is still valid), your organisation has to perform a number of activities to facilitate the tendering process of the envisaged IS-adaptation. These activities include:

¥	The issue of the call for tender.

¥	The receipt and evaluation of the tender responses.

¥	The selection of a supplier.

¥	The production and signing of an IS-adaptation:~ contract.

All these activities involve the production of documents which are exchanged as part of customer-supplier transactions. The documents which are provided support the required decision making.

## 4.1.	How to Initiate the Call for Tender Transaction

Goal:

To initiate a process resulting in an adaptation of the target domain information system by an external supplier.

Remember: That the customer:

¥	Decides on the tendering strategy to follow and how to implement the appropriate rules, e.g. the Services Directive [92/50/EEC].

¥	Places the advertisement in the European Journal (where appropriate) or in professional business journals and newspapers.

¥	Provides copies of the IS-adaptation:~ requirements to the interested supplier organisations [EM-3.1-TM].

The call for tender transaction is initiated after you have taken the decision to undertake the IS-adaptation based on the call for tender document produced beforehand.

Placement of an advertisement

You must place an advertisement in the European Journal when:

¥	Your organisation resides within the European Union, and

¥	Is subject to the European rules regarding public procurement of services, and

¥	The value of the procurement (in this case, the IS-adaptation), or aggregation of procurements, is above the EC/GATT threshold.

In this situation, supplier organisations who are interested in the proposed IS-adaptation may request further information regarding the IS-adaptation.

Providing copies of the IS-adaptation requirements

You should then provide copies of the IS-adaptation:~ requirements with respect to this call for tender to:

¥	Either, interested supplier organisations.

¥	Or, a shortlist of supplier organisations who conform to a pre-defined set of criteria (e.g. ISO 9001 certification).

The IS-adaptation:~ requirements consist of the first versions of all or some part of the following:

¥	The descriptions available for the IS-production:

-	IS-descriptions of the initial state information system.

-	IS-descriptions of a future information system.

¥	A delivery plan.

¥	The plans available for project management (i.e. the development, quality assurance, and configuration management plans).

The IS-adaptation:~ requirements will be supplemented by additional technical data, as required by the Standards Decision [87/95/EEC], as well as documentation regarding the tender evaluation criteria.

Where a restricted or negotiated tender is pursued, the process will be more simple, since you will only provide the IS-adaptation requirements to each supplier participating in the tendering process.

## 4.2.	How to Prepare for the Tender Response Transaction

Goal:

To receive several appropriate, competitive, technical proposals in order to subsequently select the best, most cost effective solution.

In terms of pushing forward the evolution of the delivery plan and the descriptions of the initial and final state of the IS-adaptation, there is nothing to do in the preparation of the tender response transactions; it is now up to the potential suppliers to do that in their tender responses.

During this time, you have to be ready to answer any questions that suppliers may have concerning your IS-adaptation requirements. You have to choose an approach for answering these questions. Examples of such approaches are:

¥	To answer questions individually to the enquiring potential supplier.

¥	To distribute all the answers you give on a particular question to all known potential suppliers.

¥	To distribute all the questions received and all the answers given to all known potential suppliers.

Whichever mode you choose, if your organisation is subject to the rules within the Services Directive [92/50/EEC], you must ensure that you are in line with its requirements.

Anyhow, it is important to notice that

With the tender response the delivery plan, including the initial and final state descriptions should have evolved to a state where they completely define the customer-supplier relationship in the production process of the IS-adaptation.

The tender response transaction requires far greater involvement from the supplier. The guidance regarding the activities that the supplier must perform in the preparation of the tender response transaction can be found in the Supplier Guide

¥	Tender Response

## 4.3.	How to prepare for the Supplier Selection Transaction

Goal:

To select the best, most cost-effective technical solution proposal.

Remember: That the customer:

¥	Performs the tender evaluations.

¥	Asks for additional clarification and explanation on aspects of a supplier's technical proposal.

¥	Decides which suppliers are to be short listed or selected based upon the results of the tender evaluations, and subsequently inform them.

¥	Informs rejected suppliers why they have not been short-listed or selected and distributes the tender evaluation results regarding their technical proposal when requested.[EM-3.1-TM]

The call for tender issued always provides a closing date for the receipt of the tender responses. This date corresponds with the completion of the tender response transaction and the initiation of the tender evaluation activity, which will result in the supplier selection transaction, and thus the notification of a supplier's selection or rejection within this tendering process.

The transaction itself consists of the decision on which a supplier is selected on the basis of the tender evaluations. There are two main decisions that have to be taken in this transaction. Firstly, which proposals effectively meet the IS-adaptation requirements (and in particular, any of those which are mandatory).This decision includes an assessment of the financial standing and technical capability of the supplier, which will be kept up to date during the entire tendering process. Secondly, you must assess which of the compliant suppliers offers the most economically advantageous solution to the IS-adaptation requirements.

The transaction is concluded by awarding the IS-adaptation to one or more of the participating supplier organisations and terminating this relationship with those supplier organisations that have not been chosen on this occasion.

In more complex tendering processes, the supplier selection transaction is the point at which a number of suppliers might be short listed, based on their initial technical proposals.

In addition to the IS-adaptation requirements, the evaluation criteria will have been determined and documented.

The evaluation of a tender response involves an evaluation of the:

¥	content of the tender response itself and

¥	responding supplier organisation.

That is, the complete set of evaluation criteria used will assess supplier organisations both organisationally and for the IS-adaptation itself. The following aspects are generally undertaken within the evaluation:

¥	The broad suitability of an organisation is commonly controlled within the call for tender ("Tenders are invited from organisations meeting the following characteristics, EN 29000-registered, capitalisation of 1MECU, etc....."), or may be covered by the presence of a supplier on your qualified supplier list. Often, the capability of the organisational processes will be assessed using such means as criteria derived from the process capability and evaluation specifications now available.

¥	At the project level, the supplier will be assessed by the customer's tender evaluation team using evaluation criteria, including criteria based upon the concepts and guidelines provided by Euromethod.

Euromethod gives support in the assessment of a proposed IS-adaptation;
it does not support the assessment of supplier organisations.
The evaluation model must be derived from other sources.

Evaluation criteria can address such diverse issues as money, system life costs, risks and sensitivity issues, all of which will be incorporated within a single agreed evaluation model. In practice, particular care should be given to the weighting of the evaluation criteria used to assess the tender responses i.e. what is the value of something? Although Euromethod does not support this activity, it is of singular importance in performing the assessments of the proposed final state, supplier understanding of the problem situation and the proposed delivery plan.

Euromethod supports the supplier selection by providing the means for the:

¥	Re-assessment of the situational factor values and re-assessment of the final state.

¥	Assessment of the suitability of the supplier's technical proposal.

Set-up of the tender evaluation team

The design and make-up of the tender evaluation team is not directly supported by Euromethod. However, the following checklist might be useful:

×	What is the operational expertise, and organisational authority requirements required within the tender evaluation team?

×	Should you choose to have a single team which addresses the entire content of each tender response?

×	Should you split the tender evaluation team up into areas of interest at the start of supplier selection? For example, separate consideration could be given to the:

×	Commercial capability of the supplier.

×	Operational use of the proposed final state of the considered system.

×	Capability of the technical design and its likely performance.

×	Business benefits (measured against organisational business model).

×	Awareness of the end-user benefits.

×	Have you assessed the tender evaluation team's experience in terms of participating in a tendering process of this size and complexity ?

×	What actions can you take to mitigate any risks involved?

Indeed, it will not always be possible for all the authors of the call for tender to be available during the tender evaluation. In these circumstances, care should be taken to ensure that their expertise is on-hand to your tender evaluation team. This is necessary to ensure that your evaluation team (by having an understanding of the problem situation, and delivery plan requirements which are as close as possible to that of the original team) perform their task successfully.

Re-assessment of the situational factor values

During the call for tender, the situational factors were used by the customer to develop an understanding of the problem situation. However, there is commonly a period of several months between the initial work undertaken to develop the technical specifications within the call for tender; and the time when the tender responses are to be evaluated. It is therefore necessary to undertake a re-assessment of the situational factor values now. Value changes can come about because of several reasons:

¥	You may now have a better understanding of the problem situation; for example, either as a result of further in-house discussions after the call for tender, or as a result of a "request for information" from potential suppliers.

¥	Incorrect analysis of a particular situational factor at the time of the original problem situation analysis.

¥	A change in the problem situation itself; for example, a corporation might decide to increase the number of interfaces between the information systems of subsidiary companies.

Particular attention should be paid to any events within the organisation which might have some implications on the adequacy of the project budget and schedules.

This re-assessment of the situational factor values allows your tender evaluation team to fully re-acquaint themselves with details of the problem situation and clarify, for the purposes of the tender evaluation, what the major risks are; and in turn, provide a pointer to whether a particular supplier has produced a suitable technical proposal.

Re-assessment of the final state

As with the problem situation, the final state was defined by you based on the knowledge available regarding what was wanted in terms of the operational items and IS-descriptions required. However, as with the re-assessment of the problem situation, the period of time between the initial work undertaken to develop the IS-adaptation:~ requirements within the call for tender; and the evaluation of the technical proposals, can result in an enhancement of your understanding of what you want in the final state. It is therefore advisable to undertake a re-assessment of the final state now and refine it if necessary.

The final state can be revised by either:

¥	Detailing and clarifying the specification of the operational items required.

¥	Re-defining what IS-descriptions must be maintained.

¥	Re-defining the requirements needed for intermediate deliverables e.g. no quality assurance needed for these.

These revisions can come about because of the following reasons:

¥	As with the problem situation, a better understanding of the required final state may be acquired; for example based on further in-house discussions, or as a result of a request for information from potential suppliers.

¥	Changes or enhancements to the technical architecture endorsed by your organisation.

¥	A change in the problem situation itself. For example, a corporation could decide to reduce the budget available for the IS-adaptation, which in turn might result in a reduction of the quality requirements with regard to the intermediate deliverables.

Assessment of the suitability of a supplier's technical proposal

The assessment of a supplier's technical proposal consists of three separate elements. Firstly, an assessment is made of the supplier's understanding of the problem situation. Secondly, an assessment is made of the delivery plan provided within the technical proposal, and lastly an interpretation of the deliverables within the technical proposal made.

AssessmentÊofÊtheÊsupplier'sÊunderstandingÊofÊthe problemÊsituation

During the tender response, the supplier developed their understanding of the problem situation based on the knowledge supplied within the IS-adaptation:~ requirements in the call for tender. As a preliminary step to assessing the supplier's technical proposal, an assessment of the supplier's understanding of the problem situation can be made based on the following questions:

×	Does the supplier's analysis of the problem situation make sense overall?

×	Is the supplier's analysis of the problem situation argumented and justified?

×	Is the supporting evidence provided for any aspect of the supplier's assessment coherent and in line with your current understanding of the problem situation?

×	Does any aspect of the supplier's assessment reflect a significant misunderstanding of the problem situation?

×	Do you, on reflection, agree with those aspects of the supplier's assessment which are different from your own?

×	Are any aspects within the supplier's response incompatible with any changes that have occurred in your understanding of the problem situation?

Assessment ofÊtheÊdeliveryÊplanÊproposedÊinÊa technicalÊproposal

The exercise of evaluating the adequacy and suitability of a delivery plan is very similar to the exercise of identifying the risks associated with the IS-adaptation at the time of the call for tender preparation.

Again the problem situation assessment (which has just been re-assessed) and the delivery plan are the central documents. But now you are also considering:

¥	Assess Delivery Plan

¥	The strategy options selected by the supplier;

represented in the delivery plan of the tender response.

¥	The justification for these options ;

formulated in terms of situational factors, risks and strategy options as described in the Delivery Planning Guide.

Your responsibility is to check:

×	Whether the strategy options resulting from the analysis of the problem situation are correct.

×	Whether you will be able to perform your role as defined in the delivery plan.

×	Whether you believe that the supplier can execute their role.

Again, together with your organisationÕs weighting system this evaluation contributes to the evaluation of the tender response.

Interpretation ofÊtheÊdeliverablesÊproposedÊinÊa technicalÊproposal

In addition to making a judgement regarding the strategy and decision points defined within the delivery plan, you must also make a judgement regarding the suitability of the deliverables proposed in the technical proposal, Euromethod supports the concepts defined in the deliverable model, in combination with the method bridging guidance.

For every deliverable that is proposed by the supplier, a method bridge containing a product glossary describes how the elements in the IS-development method used by the supplier are used to express the IS-properties of the deliverable.

But beware;

The use of Euromethod does not make a thorough analysis and understanding of the proposed deliverables obsolete.

You can use the views, IS-properties and project properties as an informal evaluation framework in which to record your perception of how well each required IS-property is covered by the final state of the IS-adaptation. When used together with your weightings regarding the importance of, IS-properties and project properties, you have a tool that helps you in the comparison of the tender responses.

As part of the detailed tender evaluation process discussed above, a list of issues may be identified regarding the production process of the selected or short listed suppliers. For each issue identified, a proposed corrective action and required timescales for completion may be defined.

Lastly, as mentioned above, once the supplier has been selected, those customers who are subject to the rules of the Services Directive, must provide a debriefing to all those suppliers who request it explaining why they were not short-listed or selected.

## 4.4.	How to prepare the Contract Awarding Transaction

Goal:

To award a contract consistent with the current IS-adaptation requirements which is likely to secure the best value for money from the project budget.

Remember: That the customer:

¥	Identifies the strengths and weaknesses of the selected technical proposal

¥	Introduces the customer organisation's contractual concerns into the negotiation procedure.

¥	Obtains the best value for money possible from the project budget.

¥	Decides if the customer organisation's interests are still met by the selected supplier and proposed contract.

¥	Provides an impact analysis with respect to a proposed change and produces the technical proposal change request

¥	Reviews the final version of the delivery and project plans.[EM-3.1-TM]

In the preparation of the contract awarding transaction nothing new, in terms of Euromethod support, happens. Contract awarding involves the supplier and yourself negotiating on what the final form of the technical annex shall be and is concluded either with the formal signing of the contract or with the withdrawal by either party from the contractual process. The negotiations are characterised by the consideration of the known technical, financial, management and quality issues, and is performed within the legal contract framework.

In some IS-adaptation situations, draft contracts will have been prepared and discussed with each shortlisted supplier at an earlier stage within the tendering process, for example prior to the supplier selection transaction. However, contract awarding corresponds to the time when the complete technical annex, containing the contract version of the delivery plan is finalised.

Refinement of the IS-adaptation requirements

Each negotiation undertaken is characterised by the need for clarification of, or requests for change to, the technical proposal. Requests for change may come from both the customer and the supplier.

In some legal environments any negotiations after supplier selection may be completely forbidden.
In this situation, ; the delivery plan including the final and initial state descriptions in the technical proposal become part of the IS-adaptation:~ contract directly.

Where it is appropriate, the refined technical proposal can be augmented in all or some of the following ways:

¥	By incorporating the results of the contractual negotiations regarding the technical annex.

¥	By undertaking detailed delivery and project planning activities such as:

-	Refining the sequence of decision points.

-	Identifying deliverables and detailed bridging to an IS-development method.

-	Performing any relevant additional mappings to further methods or techniques.

-	Defining the interface between the IS-development method and the additional mappings to further methods or techniques.

-	IS-project resourcing.

¥	By including details of any corrective actions required within the process to be used in the IS-adaptation.

That is, during the detailed tender evaluation process, the customer organisation identified a list of issues regarding the proposed processes of the selected or shortlisted suppliers. Each of these issues may now be considered for inclusion within the technical annex.

Signing of the contract

By the end of contract awarding the version of the delivery plan proposed in the selected technical proposal has become the contract version of the delivery plan, and is included within the technical annex of the contract. On reaching this point, the transaction is formally concluded with the signing of the contract by the contractual parties.

# 5.	How to use Euromethod in the Production Process

| Purpose: | The purpose of the production process is to receive the deliverables that meet the IS-adaptation requirements stated in the contract. |
| --- | --- |
| Activities: | In order to facilitate this the customer-supplier transactions defined in the delivery plan must be performed and the related decisions made. This encompasses the monitoring and approval of the progress made by the supplier and the monitoring and review of the planning of the production process. |
| Results: | As the result of these activities the final state of the IS-adaptation is achieved. This means the products the customer wants to use in the future are delivered and a new version of the information system is installed, if this was part of the contract. |
| Concepts: | ¥ Delivery plan, initial state, final state, sequence of decision points. |
| Checklists: | ¥ Preparation for delivery checklist. ¥ Recording experiences checklist. ¥ Need for contract change control checklist. |
| Examples: | For examples see the following sections of the case studies [EM-2.5-CS]: ¥ Chapter 8 - Detailed NAS Requirements Specifications |

In passing from the tendering process to the production process your responsibility in the IS-adaptation also changes from driving the process to one of controlling a process driven by your supplier. That is, while you were primarily pushing forward the tendering process, you are primarily monitoring the production and completion processes driven by the supplier.

In the production process, transactions are started by the exchange of products between the customer and supplier (which may be target domain deliverables, project domain deliverables or change control requests), and are terminated when the required decision has been made.

This chapter looks at the support that Euromethod can provide in the preparation of your participation within these production transactions.

Remember: The production and completion processes of an IS-adaptation are defined by an IS-adaptation:~ contract.

All customer-supplier transactions of the production and completion processes are defined and scheduled within the delivery plan of the IS-adaptation. [EM-3.1-TM]

## 5.1.	Approval of Deliverables

Goal:

To control the deliverables, which at this point, are consistent with the objective that the final deliverables will fit into the organisation and address the objectives identified within the IS-adaptation requirements in the contract.

Remember: That the customer:

¥	Receives the deliverables.

¥	Performs the deliverable assessment procedure.

¥	Approves, conditionally approves or rejects the deliverables.
[EM-3.1-TM]

Euromethod supports the description of a decision point, and in particular, the purpose of a decision point. Consequently, when a set of deliverables is delivered, it has already been clearly defined within the delivery plan what the technical and managerial purposes are for the relevant decision point, what the roles are that are required and thus what the goals of the customer-supplier interaction within the transaction are. In this way, far greater visibility of the decision involved in the approval of deliverables  is achieved.

¥	Define decision points

More information on decision point descriptions can be found in the Delivery Planning Guide.

Each decision point has been identified and jointly agreed by the supplier and yourself as part of the preparation of the delivery plan.

In addition, it has been determined which i.method product;s were required in order to meet the requirements of each decision point within the production and completion processes.

This was achieved by matching the product profiles for the IS-development method until all of the aspects needed by the required deliverable profile had been completely addressed i.e. its purpose, the appropriate deliverable and quality states needed, the IS-properties covered etc. This was recorded within method deliverable profiles.

¥	Method product profiles

Product glossary

It is the decision point description; within the delivery plan which now determines what must be done at an approval of deliverables decision point.

Making the resources available

Before making the decision however, it must be decided what roles are needed and what amount of resourcing of them is required to help you within the internal deliverable assessment procedure. The transaction model describes the different types of operational expertise and defines their responsibilities. The resources used within the internal evaluation will be independently defined from the decision point descriptions, but should not conflict with the resource requirements in the decision point description.

Validation of the deliverables

On receiving a delivery of deliverables at a decision point, it must be decided if these method products are in a state to be approved. You must therefore review:

¥	The associated decision point description,

¥	The method deliverable profiles,

¥	And in particular, review the state of each method products to see whether they address the IS-adaptation:~ requirements for this decision point and thus satisfactorily support the decision to be made.

The control of the content of the method products and hence the decision to approve the deliverables should be based on your completion of the following checklist:

×	Has the purpose of the method product been fully achieved to meet the requirements of this decision point?

×	Is the system (either the current or future) considered by the method products consistent with that specified in the decision point description?

×	Do the delivered method products cover all of the views required to satisfy the requirements of the decision point description?

×	Do the method products consider all of the properties (IS-properties, project properties and non-functional properties) required to satisfy the requirements of the decision point description?

×	Is the development state of the method products consistent with that specified in the decision point description?

×	Is the quality state of the method products consistent with that specified in the decision point description?

×	Is the deliverable scope of the method products consistent with that specified in the decision point description?

×	Does the method product developed correspond with the product glossary specified in the supplier's method product profile for the decision point?

¥	Method product profiles

Product glossary

×	Have all the rules for internal consistency of the method product been observed?

×	Has the method product developed demonstrated the supplier's claims about its suitability in this situation?

In the situation where the decision point description includes operational items, you should check the following:

×	Do all the operational items have the required functionality?

×	Does the system fulfil the IS-adaptation requirements?

These last two items should have been tested by the supplier prior to delivery. It is now your responsibility to undertake the acceptance testing.

Within the supplier's method deliverable profiles, it will have been specified what internal consistency rules are required for each product to address the decision point description.

Where appropriate, these consistency rules should now form part of the quality review criteria prior to the approval of the method products. That is, the method products should be reviewed for consistency in those circumstances where they are needed to support the decision to be met using these deliverables.

¥	Consistency rules

| Example: | One of the Euromethod consistency rules is that every data item within a data model should appear in at least one computerised function. One of the consistency checks within the quality review for the data model of the future system considered earlier could be to see if every data item is considered within at least one computerised function. [EM-3.2-DM] |
| --- | --- |

Making the decision

Once prepared, the decision made on receipt of some deliverables is split into two parts. Firstly, it must be decided, on the basis of the deliverables, whether the IS-adaptation is still on course, and therefore whether the IS-adaptation is still on target to reach the required final state. Secondly, the technical content of the method products must be assessed to judge their accuracy in this business context.

| Example: | A customer approves a data model of the future computer system: ¥ If, based on this data model, the customer is confident that the IS-adaptation is still on target. ¥ If it is felt that data model contains all of the data which must be included within the future computer system to satisfy the business need. That is, the customer is deciding on the completeness of the method product [EM-3.2-DM]. |
| --- | --- |

Delivering by the customer

Occasionally, there will be a need for the customer to make a delivery to the supplier. Examples of this are the provision of the target domain hardware, or the packages upon which the IS-adaptation will be based. In these circumstances, an approval of deliverables transaction can be planned. In the situation where the delivery is not made to the suppliers satisfaction, and this has implications on the project's progress, the supplier may call for a contract change control transaction to take place.

In this instance, the Euromethod concepts regard the supplier as a customer and vice versa.

Rework of Deliverables

In a normal project situation, the supplier submits his deliverables to a decision point for approval by the customer, expecting them to be approved. However, this may not happen! Indeed, in the real world of live projects, the reasons are myriad why a deliverable may not be delivered entirely to its intended requirements. It may result from shortfalls in either the customer or supplier organisations. Examples which would result in rework are:

¥	The deliverables did not conform with the IS-adaptation requirements.

¥	Rapidly changing circumstances within the customer organisation were insufficiently taken into account and resulted in the deliverables reflecting an obsolete problem situation.

The Delivery Planning Guide explains how you can avoid the risk of this occurring by developing delivery plans which are sensitive to a given project situation and which are therefore adaptable to the production situations that will be encountered. For example, a problem situation in which the requirements are evolving rapidly can be handled by the use of a delivery plan developed upon an experimental description approach and an evolutionary construction approach.

¥	General approaches

Unfortunately as mentioned above, while it is best avoided, deliverable rework is going to be unavoidable in some circumstances and new approval of deliverables and approval of project status and plan transactions have to be introduced into the delivery plan. This requires that you:

¥	Ensure that the delivery of the deliverables was the one that you wanted.

¥	Assess, with your supplier, the impact of delays and resourcing problems on the production process.

¥	Make changes to the project plans.

The control of the content of the reworked method products and hence the decision to approve should be based on the same checklist used when the deliverables were originally submitted. Where appropriate, the consistency rules should also be reconsidered where they are needed to support the decision to be made.

Rework acceptance

The decision made in this situation is once again split into two parts:

¥	Firstly, it has to be decided whether the IS-adaptation is back on course, and thus whether the IS-adaptation is back on target to deliver the required future system.

¥	Secondly, the technical content of the reworked method products has to be assessed.

From our earlier example, do you now believe that the data model of the future computer system contains all of the business information which must be included within the future system?

Recording experiences for use in future IS-adaptations.

Since Euromethod offers the means to clarify the delivery process, and therefore the decision making associated with each class of method products, it provides an ideal framework in which to capture decision making experiences. In particular, it facilitates the recording of what is necessary in a deliverable containing a particular method product to support a particular decision, and conversely what is not necessary. You therefore have the means to use your own observations to help tailor the decision making process to meet the demands of future IS-adaptations. Consequently, the specification of the required deliverables within future production processes can be improved.

For each approval of deliverables decision point, you should consider the following checklist:

×	What parts of the deliverable (and thus its constituent method products) were observed as facilitating the customer's decision making process?

×	Were any concepts in the deliverable not observed as facilitating the customer's decision making process?

×	Were all of the requirements of the decision point description equally well supported by the deliverable?

×	For those aspects of the decision point description which were not well supported by the deliverable, what must be done in future to provide a better quality product ?

As stated earlier, rework is expensive. It eats into your project schedules, your budget and finally your profit. This review framework can be applied to re-worked deliverables in the same way as it was applied to the originally submitted deliverables. Indeed, it is suggested that for each approval of deliverables decision point, you should reuse the experiences checklist introduced earlier.

## 5.2.	Approval of Project Status and Plan

Goal:

To ensure the IS-adaptation feasibility by uncovering risks and defining preventative actions to prevent them i.e. to protect the project investment.

Remember: That the customer:

¥	Receives the deliverables regarding a project status and plan review.

¥	Decides on the scale of problems and business risks.

¥	Represents the customer organisation at the project status and plan review.

¥	Determines whether a contract change control transaction is necessary from the customer point of view.[EM-3.1-TM]

A transaction of this type is performed by both parties but is approved by the customer alone. In this transaction, project domain deliverables covering topics such as management reporting, assessments of project risks, feasibility and quality and proposals for risk resolution, re-planning and resource allocation are evaluated. Based on the evaluation of the reports, contract change control may be triggered if necessary.

¥	Project Domain Deliverables

The purpose of introducing a transaction of this type into the delivery plan is:

¥	The assessment of the impact of delays and resourcing problems on the production process.

¥	The co-operative decision on corrective actions, i.e.

-	Changes to the delivery plan.

-	Changes to the project plans.

Remember: The planning of the IS-adaptation is determined by the sequence and schedule of the customer-supplier transactions.

Therefore, the decision to be made in transactions of this type is whether to:

¥	Continue the production process with the existing plans,

¥	Approve changed plans for the further production process,

¥	Trigger a contract change control transaction.

The Delivery Planning Guide can be used in the assessment of the impact of particular problems.

¥	Assess Delivery Plan

Assessing the problem situation

The problems in an IS-adaptation can now be analysed by assessing the problem situation; and may lead to situational factor values that differ from the initial ones, which were established before the problems occurred.

Based on the new analysis of the problem situation, the initial conclusions about the IS-adaptation can then be checked to see whether the strategy chosen remains valid; and thus whether it is safe to tackle the problems with slight changes to plans. For example:

¥	Postponing of deliveries.

¥	Changes to the project plans; e.g.

-	New resource planning,

-	Changes in management procedures,

etc.

Performing corrective actions and complementary initiatives

A further characteristic of this transaction is that, on the basis of the project reports, you can identify a number of corrective actions which could be performed by the supplier organisation in order to improve its processes. In this way, the approval of project status and plan transaction may lead to the instigation of a process improvement programme to run in parallel with the IS-adaptation. However, all process improvement issues will be handled outside of the Euromethod concepts.

## 5.3.	Contract Change Control

Goal:

Where customer requirements to the IS-adaptation have developed from those defined within the contract, they need to be documented within the project process as part of a controlled change process to ensure an up to date technical annex in the contract.

Remember: That the customer:

¥	Determines the technical implications to the customer organisation of any proposed changes to the technical annex.

¥	Introduces the customer organisation's contractual concerns into the contract change control.

¥	Detects whether the IS-adaptation requirements defined in the technical annex are not being met by the supplier, and whether this corresponds to a breach of contract.

¥	Obtains the best value for money possible for the project spend.
[EM-3.1-TM]

The contract change control transaction addresses the situation in which changes to the technical annex of the contract are identified and processed.

In some legal environments no re-negotiation of the contract is permitted.
In this situation, the contractual descriptions of the final and initial state and the delivery plan are fixed for the duration of the IS-adaptation.

The transaction is concluded when the new version of the technical annex containing the changes is approved. Changes to the body of the contract, which contains the legal and financial provisions of the contract are not addressed by this transaction.

The contractual change control process
must be outlined within the contract.

General usage of contract change control

Contract change control may be either planned within the delivery plan, or be triggered during the production or completion processes. It may be triggered by either the supplier, or by yourself when technical or planning risks that are not handled clearly within the technical annex of the existing contract are detected. Contract change control often follows an assessment of either some deliverables, or of the project itself, in which changes to the technical annex are identified which reduce a threat to the project's outcome.

As mentioned above, contract change control  consists of the agreement of both contractual parties to changes to the technical annex. The nature of these changes is often that, they act as a minor amendment or clarification of a previously stated requirement. In the large majority of cases the changes made as part of the contract change control do not have a substantial impact upon the content and intention of the contract. It simply records the advances in the understanding of the contractual goals and requirements.

The following checklist identifies situations in which a contract change control transaction may be needed:

×	Does some aspect of the technical annex require some further clarification?

×	Has part of the production process resulted in the need for some enhancement or updating of the IS-adaptation requirements?

×	Are some of the specifications provided in the technical annex no longer applicable to the IS-adaptation and should they be removed to avoid confusion?

Based on your experience, further examples are likely to be identified.

Examples of the changes that can be made are:

¥	Perform a new analysis of the problem situation and check whether the initial conclusions about the IS-adaptation:~ strategy are still valid.

Based on this analysis, you should make changes to the plans. For example:

¥	Postpone some of the deliveries defined within the delivery plan.

¥	Redefine responsibilities within the delivery plan.

¥	Introduce additional decision points.

¥	Make changes to the project plans; e.g.

-	New resource planning,

-	Changes in management procedures, etc.

Contract change control and re-negotiation of the contract

In some circumstances, major technical changes may be involved which require radical changes to the plans and the contract itself. In this circumstance, the contract change control transaction is used to manage the technical changes to the technical annex. However, all re-negotiation of contract issues will be handled outside of the Euromethod concepts, using normal business practices.

Remember: The Services Directive states that if a customer fundamentally changes their requirement, then they must re-advertise. [92/50/EEC]

The likely scenarios in which this may occur are:

¥	The customer detects that the IS-adaptation requirements stated in the technical annex are no longer in line with the business objectives, and thus wants to change the technical annex in order to ensure the system needed is obtained.

¥	The customer detects that the IS-adaptation requirements are not being met by the supplier.

¥	The supplier detects that the real customer expectations are not consistent with the stated IS-adaptation requirements, and thus wants a significant change of the technical annex in order to avoid risks to the acceptance of the work.

¥	The supplier discovers that the system development is not feasible.

Contract change control and contract completion

In each of the following situations the performance of one of the contractual partners is found to be damaging to the progress of the IS-adaptation:

¥	The supplier's performance is thought to be partially or wholly unsatisfactory in meeting the objectives of the IS-adaptation. Consequently, the customer may require that the supplier is removed from the IS-adaptation.

¥	One of the contractual parties is found to be in breach of the contract.

In these circumstances, which are comparatively rare, contract change control allied to a re-negotiation of the contract may not be enough to salvage the project, and contract completion; could be invoked as part of the cancellation of the IS-adaptation.

From this it can be seen that in terms of the Euromethod support provided to the IS-adaptation no new concepts are introduced to the contract change control transaction. Contract change control is simply a review of the existing Euromethod supported products to obtain a better functioning project, and consequently an improvement in the customer-supplier relationship. More information can be found in the Delivery Planning Guide.

¥	Assess Delivery Plan

## 5.4	IS-adaptation Role Assignments in the Production Process

Once the delivery plan has been incorporated within the technical annex of the contract, it is necessary to monitor whether the IS-adaptation role requirements as defined within the delivery plan are being adhered to, both in terms of the people that you are able to assign to the production and completion processes at a particular time, but also in terms of what resources the supplier is assigning to the appropriate parts of the IS-adaptation.

Further information on this can be found within the Delivery Planning Guide.

# 6.	How to use Euromethod in the Completion Process

| Purpose: | The purpose of the completion process is to confirm that the final state of the IS-adaptation is achieved and to terminate the IS-adaptation. |
| --- | --- |
| Activities: | This involves final acceptance of the received deliverables and resolution of all other issues related to the IS-adaptation. |
| Results: | As the result the IS-adaptation terminates, and the customer has the products that meet the IS-adaptation requirements in hand. |
| Concepts: | ¥ Delivery plan, initial state, final state, sequence of decision points. |
| Checklists: | ¥ Preparation for delivery checklist. ¥ Recording experiences checklist. |

## 6.1.	Approval of Final Deliverables

Goal:

To obtain the final deliverables that represent an acceptable response to both the contractual IS-adaptation requirements and the expectations in the organisation; in order that the on-going process of effecting an improvement in the organisation's business practices can be achieved.

Remember: That the customer:

¥	Receives the final deliverables

¥	Undertakes an internal assessment of the final deliverables via the organisation's deliverable assessment procedure.

¥	Approves, conditionally approves or rejects the final deliverables.
[EM-3.1-TM]

Euromethod supports the description of a decision point, and in particular, the purpose of a decision point. In this way, there really is no distinction between the final delivery and those which have preceded it in the production process. That is, the technical support to the decision point concerning the approval of final deliverables is defined within the final state profiles within the delivery plan. Thus, when the final deliverables are delivered, it has already been defined within the delivery plan what the technical and managerial objectives are, and thus what the goals of the customer-supplier interaction are. In this way, greater visibility of the decision to be taken is achieved.

More information on decision point descriptions can be found in the Delivery Planning Guide.

¥	Define decision points

As part of the supplier's preparation of the delivery plan, it was identified which of their method products were required in order to meet the requirements of the final state of the IS-adaptation. As you will now recall, this was achieved by matching their method's product profiles until they had completely addressed all of the aspects required by the final state profile i.e. its purpose, the appropriate deliverable and quality states needed, the IS-properties covered etc.

Validation of the deliverables

On receiving the final deliverables, you must decide if they are acceptable, and in the case of operational items successfully tested and installed within the target domain. You must therefore review:

×	The final state profile,

×	The method deliverable profiles,

×	And in particular, review the state of each method products to see whether they address your requirements for final state and thus satisfactorily support the final state decision process,

×	The results of the tests on the operational items.

The control of the content of the method products and hence the decision to approve should be based on the completion of the same checklist as was used in the approval of deliverables transactions, with the following minor changes:

×	The term decision point should always be read as final state within the checklist items.

×	All the IS-adaptation deliverables must be viewed in the context of the final state.

Consistency checking is identical for the final deliverables as for any other delivery within the production process.

Making the decision

The decision made on receipt of the final deliverables is split into the following parts. Firstly, you decide on the basis of the final delivery, whether the IS-adaptation:~ requirements have been achieved. Secondly, the technical content of the deliverables is assessed. For example if you, as the customer, decide whether a business design is in a suitable state for it to provide the specification of the future system, you are in fact making a decision on the quality of the method products.

Deliverable non-acceptance can be caused either because of the poor specification of the requirements in the first instance, the poor quality of the deliverables, or by the expectation gap that frequently exists between customers and suppliers.

Recording project experiences

Euromethod provides a framework to capture experiences and record what is necessary in a method product to support the decision making process. This framework can be applied to final deliverables in the same way as it was applied to any other deliverables. However, it is most common that this review is incorporated within the end-project review performed as part of the contract completion.

## 6.2.	Contract Completion

Goal:

To ensure that all outstanding technical and commercial transactions regarding this IS-adaptation contract have been satisfactorily concluded.

Remember: That the customer:

¥	Closes the contractual relationship with the supplier, keeping in mind the business implications of the residual technical and commercial tasks and records all the important IS-adaptation experiences.[EM-3.1-TM]

As the customer, the contract completion transaction is essentially an administrative transaction in which you ensure that all the transactions regarding the IS-adaptation have been satisfactorily completed.

Scheduled Completion

You should aim to work co-operatively with your supplier, in order to phase out all the technical, management and financial aspects of the IS-adaptation in a controlled manner.

When contract completion occurs after the acceptance of the final deliverables, it is performed in the scheduled manner. 
It thus represents the normal termination sequence for an IS-adaptation.

Unscheduled completion

As mentioned in the section regarding contract change control, contract completion can also occur in an unplanned fashion.

When contract completion occurs in an unplanned fashion, 
it is performed in a triggered manner. 
It thus represents the abnormal termination sequence for an IS-adaptation.

Technical and commercial completion

In completing the contract completion, you should check that all the following checklist items have been satisfactorily concluded:

¥	Technical aspects:

Examples of the outstanding results are:

-	Have all the operational items amended in line with the results of the acceptance test suite been provided by the supplier to ensure the smooth running of the operational system ?

-	Has any previously outstanding planning information regarding future IS-adaptations under consideration been made available to both parties?

-	Has all the quality review documentation been completed and provided to you?

-	Has all the user documentation been finalised and delivered to you?

¥	Commercial aspects:

Examples of possible outstanding commercial aspects are:

-	Have all the sub-contracts been honoured?

-	Have all the invoices been issued to the appropriate organisations?

-	Have all the cost statements been submitted?

Managing dependencies with other transactions

It is common that the contract completion can run in parallel with one or more transactions. For example, you may choose to initiate further contractual negotiations (or perhaps issue a new call for tender) to address the post-contractual relationship i.e. the undertaking of a new IS-adaptation or finalising the maintenance or warranty service. A second example is the case of an abnormal termination to an IS-adaptation. In this instance, the execution of this transaction may occur in parallel with that of contract re-negotiation.

You should pay attention to managing these interfaces to provide a consistent and manageable relationship with the supplier.

Recording experiences for use in future IS-adaptations.

What are the lessons from this IS-adaptation that must be absorbed in future IS-adaptations?

Euromethod provides a framework to capture experiences for both the target and project domains and subsequently record what is necessary in order to support the decision making process demanded within complex customer-supplier relationships.

This framework can be applied within contract completion to address the entire IS-adaptation, in the same way as it has been applied to the target and project domain transactions individually. Once again, you have the means to use your own observations to help you place your requirements on future production processes, and so address better the demands of the decision making process within future IS-adaptations.

Furthermore, you have the additional opportunity within the contract completion transaction to perform a synthesis of the entire customer-supplier relationship, and thus build up a feeling for what constitutes best practice in this complex area.

Your objective is to learn from your experiences.
Support the decision process in future IS-adaptations.
Avoid the risk of receiving either the wrong, or poor quality adapted information systems.

In performing this end-project review you can reuse the earlier experiences checklist to consider the lessons to be learnt (See Section 5.1) for each decision point and production phase within the production process.

# A.	Profiles of Typical Initial States

## A.1.	Undocumented information system

### A.1.1.	Description

The IS-adaptation starts with an operational information system for which no or only very limited documentation is available.

### A.1.2.	Profile

As no IS-descriptions are available, only the operational items in the current operational information system constitute the initial state.

#### 1.	OperationalÊItems

¥	Hardware.

¥	System Software.

¥	Application software.

¥	User and operator manuals, work instructions.

¥	Data.

## A.2.	Documented information system

### A.2.1.	Description

The IS-adaptation starts with an operational information system for which the complete or most of the design documentation is available; e.g. from the IS-adaptation in which the system was produced or from an IS-adaptation in which this documentation was produced for the currently operational information system.

### A.2.2.	Profile

#### 1.	SpecificationÊofÊCurrentÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊCurrentÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

#### 3.	OperationalÊItems

¥	Hardware.

¥	System Software.

¥	Application software.

¥	User and operator manuals, work instructions.

¥	Data.

## A.3.	Tested Information System

### A.3.1.	Description

The IS-adaptation starts with a set of operational items which have been tested. For these, the design documentation is available from the IS-adaptation in which the new version was produced.

### A.3.2.	Profile

#### 1.	SpecificationÊofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

#### 3.	OperationalÊItems

¥	Hardware s.

¥	System .

¥	Application .

¥	Data instances.

¥	User .

¥	Work , job descriptions.

¥	E, migration programmes.

## A.4.	Detailed technical design

### A.4.1.	Description

The IS-adaptation starts from a design of the future information system (including possibly prototypes) where all the computer system views are specified in detail.

### A.4.2.	Profile

#### 1.	Specification / prototypeÊofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

## A.5.	Detailed Business Design

### A.5.1.	Description

The IS-adaptation starts from a design of the future information system (including possibly prototypes) where the business information and process views and the work practice view are specified in detail but no or only a draft design of the future computer system is available.

### A.5.2.	Profile

#### 1.	Specification / prototypeÊofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

## A.6.	Global Design

### A.6.1.	Description

The IS-adaptation starts with a semi-formal description (and possibly prototypes) of the future information system and an informal description of the requirements to a future information system.

### A.6.2.	Profile

#### 1.	Specification / prototypeÊofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

## A.7.	Problem Description

### A.7.1.	Description

The IS-adaptation starts from an well established statement of what the requirements to the future information system are.

### A.7.2.	Profile

#### 1.	SpecificationÊofÊCurrentÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  |  | Ã |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

# B.	Profiles of Typical Final States

The typical final states are final states that are frequently encountered in practice because they provide a useful result to the customer, allowing them to make a major decision regarding their information system. However, the typical states should only be considered as examples, and IS-adaptations may depart from them.

The following text and tables summarise the main differences within these final states and provide justifications for them.

Three classes of final states are considered:

¥	Final states characterised by new operational items.

¥	Final states characterised by documents on a future information system.

¥	Final states characterised by documents on the current information system.

The following abbreviations are used.

D means: detailed.

G means: global.

WP means: Work Practice View

CSA means: Computer System Architecture View

ISV means: the three Information System Views

CSV means: the three Computer System Views

Final states characterised by new operational items

| Final state | Operatio-nal item | Views Requir. | Views Spec. | Views Proto. | Develop. state | Scope |
| --- | --- | --- | --- | --- | --- | --- |
| Installed IS | yes | WP, CSA | WP, CSA |  | D | Full |
| Tested IS | yes | WP, CSA | WP, CSA |  | D | Full |

These two final states are different because in one case the new information system version is operational and in the other it is not. In both cases, the final state contains the documentation which is needed for possible future IS-adaptations, i.e. the detailed requirement statements and specifications of the work practice and computer system architecture views with full scope. The other views are more abstract and, although necessary for making certain decisions, they are not required as a documentation of the information system because they can be derived from the work practice and computer system architecture views, when needed.

The representation language for the specifications is semi-formal (formal is also valid) whenever possible.

Final states characterised by documents on a future information system

| Final state | Operatio-nal item | Views Requir. | Views Spec. | Views Proto. | Develop. state | Scope |
| --- | --- | --- | --- | --- | --- | --- |
| Detailed technical design | no | WP, CSV | WP, CSV | WP, CSV | D | Full |
| Detailed business design | no | ISV, CSV | ISV, CSV | ISV, CSV | D G | Full |
| Comput system change study | no | ISV, CSA | ISV, CSA | ISV, CSA | G | Full |
| Informat system change study | no | ISV, CSA | ISV, | ISV, | G | Full |

As shown in the above table, from the information system change study up to the detailed technical design, there is a shift of emphasis from the IS to the computer system and from global views to detailed ones.

The scope is full.

The representation language for the specifications is semi-formal (when possible).

The two change studies support investment decisions and they only require global views. The computer system change study contains global specifications of the computer system architecture to be able to make decisions on the hardware and software investments, in addition to the changes in business information, business processes and work practices.

The two detailed designs must support design decisions. The detailed business design includes detailed views on the information system and only global views on the computer system, in order to support decisions on the information system. The detailed technical design contains detailed work practice view and detailed views on the computer system to support decisions on the computer system.

Final states characterised by documents on the current information system

| Final state | Operatio-nal item | Views Requir. | Views Spec. | Views Proto. | Develop. state | Scope |
| --- | --- | --- | --- | --- | --- | --- |
| IS documentation | no | WP, CSA | WP, CSA |  | D | Full |

As for the tested or installed IS, this final state contains the documentation which is needed for possible future IS-adaptations, i.e. the detailed requirement statements and specifications of the work practice and computer system architecture views with full scope. The other views are more abstract and, although necessary for making certain decisions, they are not required as a documentation of the information system because they can be derived from the work practice and computer system architecture views, when required.

The representation language for the specifications is semi-formal (formal is also valid) whenever possible.

## B.1.	Installed Information System

### B.1.1.	Description

The typical final state Òinstalled information systemÓ characterises an IS-adaptation that achieves both the installation of a new operational information system, together with the related design documentation. This could mean, for example:

¥	Replacing the computer system by a successor version without changing any manual procedures and work instructions.

¥	Changing the manual procedures in the information system and adaptation of the computer system to the changed work practices.

¥	Automation of a previously purely manual information system by installation of a new computer system and adapted manual procedures and work instructions.

¥	Changes to subsets of the manual procedures and the computer system.

As mentioned in the general description of the typical final states, this is the only typical final state of an IS-adaptation where the current operational information system is actually changed.

### B.1.2.	Profile

#### 1.	SpecificationÊofÊFinalÊStateÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFinalÊStateÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

In these profiles:

"D" means Detailed: a high degree of decomposition and specialisation.

"G" means Global: not detailed.

#### 3.	OperationalÊItems

¥	Hardware.

¥	System Software.

¥	Application software.

¥	User and operator manuals and work instructions.

¥	Data.

#### 4.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.2.	Tested Information System

### B.2.1.	Description

The typical final state Òtested information systemÓ characterises an IS-adaptation that achieves the construction of a new version of the information system, together with the related design documentation, but does not actually install that system in the target domain.

This is particularly the case if the installation of the new version is of such big complexity that the customer wants to handle it as a separate IS-adaptation.

### B.2.2.	Profile

#### 1.	SpecificationÊofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

#### 3.	OperationalÊItems

¥	Application software.

¥	User and operator manuals, and work instructions.

#### 4.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.3.	Detailed Technical Design

### B.3.1.	Description

The typical final state Òdetailed technical designÓ characterises an IS-adaptation that produces a design of a future information system version where all the computer system views and the work practice view are specified in detail. Prototypes may complement or substitute for the specifications.

This is particularly the case if the customer wants to have the opportunity to have the successor version of his information system constructed and installed by a supplier different from the one who produced the detailed technical design, or just regulated by a separate contract.

### B.3.2.	Profile

#### 1.	SpecificationÊ/ prototype ofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

#### 3.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.4.	Detailed Business Design

### B.4.1.	Description

The typical final state Òdetailed business designÓ characterises an IS-adaptation that achieves a design of the future information system where the business information and process views and the work practice view are specified in detail but nothing or only global requirements and specifications of the computer system views of the future information system version are produced. Prototypes may complement or substitute for the specifications.

This is particularly the case if the customer wants to have the opportunity to have the technical design, construction and installation of the successor version of his information system to be produced by a supplier or suppliers different from the one who produced the detailed business design, or just regulated by a separate contract.

### B.4.2.	Profile

#### 1.	SpecificationÊ/ prototype ofÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system data view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system function view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

#### 3.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.5.	Information System Change study

### B.5.1.	Description

The typical final state Òinformation system change studyÓ characterises an IS-adaptation that produces options for a global statement of the requirements a future information system has to fulfil, together with options for a global specification of the information system views. Prototypes may complement or substitute for the specifications. Additionally, global requirements statements in terms of the computer system architecture view are provided to facilitate the assessment of the feasibility, technical impact, cost, etc. of the information system specification options. These generally serve as a basis for strategic decisions on the change of business processes or work practices, for example organisational changes in the information system or changes in the tasks of the actors.

For this typical final state it is important to recognise that several options of the specification of the future information system can be delivered. Each of which demonstrates how the specific option of fulfilling the stated requirements impacts on costs, benefits, development efforts etc.

### B.5.2.	Profile

#### 1.	SpecificationÊ/ prototype ofÊFutureÊInformationÊSystem Options

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  |  | Ã |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

The decisions that are made based on the result of an information system change study generally include a decision regarding the investment in new technical infrastructure. Therefore, information related to the requirements to the computer system architecture which shall support the envisaged changes in the work practices is required.

Deliverables capturing the other computer system views, although probably produced for deriving the computer system architecture, are not part of the final state since they are generally no longer needed after the IS-adaptation. Firstly, they are not required for the decision mentioned above. Secondly, they become obsolete as soon as the information system views are being designed in more detail in the future IS-adaptation, so that there is no need to keep them up to date in the current one.

#### 3.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.6.	Computer System Change study

### B.6.1.	Description

The typical final state Òcomputer system change studyÓ characterises an IS-adaptation that produces a global statement of the requirements a future information system has to fulfil, together with a global specification of the information system views. Additionally, and of particular interest, a statement of requirements in terms of the computer system architecture view and several options for a global specification of this view are provided. These generally serve as a basis for strategic decisions on the acquisition of information technology products. Prototypes may complement or substitute for the specifications.

For this typical final state it is important to recognise that several options of the specification of the future information systemÕs work practice and computer system architecture view can be delivered. Each of which demonstrates how the specific option of fulfilling the stated requirements impacts on the work practices and the costs, benefits, development efforts, etc. of different computer system architectures.

### B.6.2.	Profile

#### 1.	SpecificationÊ/ prototype ofÊFutureÊInformationÊSystem Options

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | G |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊFutureÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Business information view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Business processes view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | G |  | Ã |  |  |  | Ã |

For similar reasons as described for the information system change study, no deliverables related to the computer system function view and the computer system data view are included in this typical final state.

#### 3.	Optionally

Delivery and project plans for subsequent IS-adaptations.

## B.7.	Information System Documentation

### B.7.1.	Description

The typical final state Òinformation system documentationÓ characterises an IS-adaptation that produces the design documentation of the currently operational information system where some or all of the information system views are specified without changing the operational system or producing IS-descriptions of a future version.

### B.7.2.	Profile

#### 1.	SpecificationÊofÊCurrentÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qua. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties | D |  | Ã |  |  | Ã |  |

#### 2.	RequirementsÊtoÊCurrentÊInformationÊSystem

|  | State |  | Scope |  | Formality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dev. | Qual. | full | partial | formal | semi-formal | informal |
| Work practice view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |
| Computer system architecture view |  |  |  |  |  |  |  |
| all IS-properties + relevant non-functional properties | D |  | Ã |  |  |  | Ã |

#### 3.	Optionally

Delivery and project plans for subsequent IS-adaptations.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[87/95/EEC]	Standards Decision

[92/50/EEC]	Council Directive 92/50/EEC of 18 June 1992 relating to the co-ordination of procedures for the award of public service contracts

# Index

application software 20, 84

approval of deliverables 64, 68, 69

approval of final deliverables 77

approval of project status and plan 68, 71

authority 24

business information view 37, 42

business process view 37, 42

call for tender 13, 15, 29, 30, 43, 44, 47, 50, 51, 53, 56

completion process 12, 18, 20, 30, 63, 64, 65

computer system architecture view 37, 39, 40, 42

computer system data view 38, 42

computer system function view 38, 42

computerised function 67

configuration management plan 19, 29

consistency 66, 68

construction approach 68

contract authority 24

contract awarding 61

contract change control 44, 71, 73

contract completion 79, 81

cost 45

decision point 20, 24, 59, 64, 66, 77

decision point description 27, 66, 69

deliverable profile 36, 39, 43

deliverable scope 66

deliverable state 65

delivery plan 19, 20, 27, 29, 39, 43, 44, 52, 53, 55, 58, 59, 65, 70, 75, 77

description approach 68

development plan 19, 29

development state 66

educational courses 84

Euromethod concepts 12, 16

final state 16, 17, 21, 33, 43, 55, 57

~ computer system change study 36, 103

~ detailed business design 36, 99

~ detailed technical design 36, 97

~ information system change study 36, 101

~ information system documentation 36, 105

~ installed information system 36, 94

~ tested information system 36, 96

final state information system 17

financial authority 26

hardware device 84

initial state 19, 21, 30, 33, 43

~ detailed business design 39

~ detailed technical design 39

~ documented information system 39

~ global design 39

~ problem description 39

~ tested information system 39

~ undocumented information system 39

initial state information system 19, 29, 51

IS-adaptation 12

~ contract 12, 13, 16, 30, 50, 62, 64

~ requirements 13, 15, 16, 29, 45, 50, 51, 52, 57, 58, 65, 78

~ strategy 73

IS-description 18, 19, 29, 51, 57

IS-development method 59, 65

IS-production 51

IS-properties 59, 60, 66

key role

contract authority 23, 24, 48

operational expertise 23

organisational authority 23

project authority 23

legal authority 26

method deliverable profile 65, 66, 78

method product 66, 69

method product profile 66

migration programme 84

non-functional properties 66

Operational expertise 23, 25, 55, 65

operational item 16, 18, 19, 38, 57, 66, 77, 80

organisational authority 26, 55

problem situation 45, 55, 58, 59, 73

procurement 7

product 36, 40

product glossary 59, 66

production process 12, 18, 19, 20, 29, 30, 44, 53, 63, 64, 65

project authority 25

project domain 20, 81

project domain deliverable 20, 70

project management 52

project plan 19, 29, 39, 68, 70

project properties 60, 66

project report 71

prototype 36, 40

quality assurance plan 19, 29

quality requirements 58

quality state 65, 66

required deliverable profile 21, 30, 43, 65

requirement 36, 40

requirements statement 36, 37, 38, 39, 40, 42

responsibility 18

risk 31

role concepts 22

senior management 26, 30, 48

Services Directive 74

situation analysis 48

situational factor 35, 42, 55, 59, 71

~ value 43, 48

~s table 42, 48

specification 36, 37, 38, 39, 40, 42, 73

strategy options 59

supplier selection 54, 55, 56

system software 20, 84

target domain 77, 81

target domain deliverable 20

technical annex 13, 16, 29, 62

technical proposal 13, 45, 50, 55, 58, 59, 62

technical specification 12, 13, 56

tender response 13, 29, 30, 50, 52, 53, 54, 58

tendering process 13, 28, 29, 47, 50, 54, 63

typical final state 32, 37, 39

typical initial state 32, 38

user and operator manuals 84

view 39

work instructions 84

work practice view 37, 39, 40, 42

Customer Guide Document History

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 221193 | Being developed | MG | Initial draft of D.3.2 | MF, MG, MP, NA |
| 261193 | Being developed | MP | Update of the table of contents for control-board review. | MF, MG, MP, NA |
| 291193 | Being developed | MP | Update of the table of contents for control-board review. | MF, MG, MP, NA, control-board |
| 011293 | Being developed | MP | First version of the chapter ÒHow to use Euromethod in the tendering process?Ó | NA, MP |
| 081293 | Being developed | MP | First step towards an integration of the use of the role concepts | MF, MG, MP, NA, LM |
| 200194 | Being developed | MP | Further development based on the EMPMB presentation |  |
| 020294 | Being developed | MP | Tendering process restructured to emphasise the idea of Òinternal preparation of a transactionÓ vs. Òthe actual transactionÓ. Remarks from MG incorporated | MF, MG, NA, MP, LM, S.West |
| 010394 | Being developed | MP, MG | Decisions from technical meeting of the 10. February incorporated (ÒIS-adaptation requirements and proposalÓ, Òtechnical annexÓ). Further development of all sections. | MF, MG, MP, |
| 020394 | Being developed | MP, MG | Enhanced sections on improvement of project situation and enhancement of initial state. Text on the use of term technical specification introduced. | MF, MG, MP, NA, S.West |
| 040394 | Being developed | MP | Text on critical combinations of initial and final states added. | MF, MG, MP, NA |
| 070394 | Under-L3-review |  | L2-comments from MF received, but not yet incorporated. | Project Team & Review Group |
| 250394 | Under-L3-review | MG | All L3 and Project Team review comments included. Steve Wests comments also taken into full consideration and included. Consistency with Supplier Guide checked. |  |
| 050494 | Delivered | MG |  | EC |
| 170694 | Under-L3-review | MG | EMPMB comments included | Review Group |
| 300694 | Delivered | MF |  | EC |

If these roles do not have the complete authority for these decisions, but are constrained by organisational authorities, the guidance helps the contract and project authority to support and advise the decision making of these higher organisational authorities.

The operational items of a future information system which have not been installed as part of the current operational information system at this time, may then be subject to a separate IS-adaptation. This IS-adaptation would cover the transition from the current information system version to a new version which contains those operational items. This may be appropriate in certain situations, e.g. where the services of a separate supplier skilled in managing organisational change may be required.

In this section, the word person may mean individual or group of individuals.

However, in some legal environments it has to be fixed in the Call for Tender or in the Tender Response.

The typical inital and final states do not have the same names because there is a major difference in the content of the related deliverables.

A Change Study generally presents a set of different options for solving a problem.

A Global Design or a Problem Description represent one chosen option to be pursued in the IS-adaptation.

Thus, although they address the same deliverable types and properties, these typical initial states generally consist of a subset of the deliverables from the typical final states. They are therefore not entirely similar.

The customer decides the level of detail of this version of the delivery plan. This version could only contain the initial and final state descriptions. But it could also contain the description of a strategy and even a sequence of decision points. This sequence may be more or less elaborated.

In restricted and negotiated tendering procedures, the supplier organisations may already have been evaluated. In this case, that evaluation will simply be refined now. In open tendering procedures, this will be the first opportunity to evaluate a supplier.

In those contractual situations in which no negotiation is allowed, and in which the tender response can not be adopted as the basis of a contract, the only option available is to repeat the entire tendering process.

Installed means: the information system is operational in the target domain. In order to achieve this the new organisation must be in place, the new computer system must work correctly and the human actors must be trained in the new work practies.