# appendix B
generic risk management plan

## SAMPLE RISK MANAGEMENT PLAN

### Preface

DoDD 5000.1 requires that “PMs and other acquisition managers shall continually assess program risks” and that they “shall develop a contracting approach appropriate to the type of system being acquired.”  Further, DoD 5000.2-R states that “The PM  shall establish a risk management program…to identify and control performance, cost, and schedule risks.”  Although the need for a risk management program and a risk management process are addressed throughout this regulation, there is no requirement for a formal risk management plan (RMP). However, Program Managers (PMs) have found such a plan necessary to focus properly on the assessment and handling of program risk, a core acquisition management issue that Milestone Decision Authorities (MDAs) “must rigorously address at appropriate milestones before making program decisions.”

Attached is a sample format and RMP that is a compilation of several good risk plans and the results of the DoD Risk Management Working Group Study.  It represents the types of information and considerations that a plan, tailored to a specific program, might contain.  The sample is, admittedly, more useful for an ACAT I or II program; however, ACAT III and IV programs may also use it as a guide to write a tailored plan to meet their program needs.  A sample plan for these programs is being written and will be available in the future.  The DoD Acquisition Deskbook, Section 2.5.2, has general guidance and advice in all areas of risk management.  Section 2.5.2.4 of the Deskbook contains information concerning the development of a risk management plan.

There is a danger in providing a sample document.  First of all, because it is written as a guide for a general audience, it does not satisfy all of the needs of any particular program.  Second, there is the possibility that some prospective user will simply adopt the plan as written, despite the fact that it does not fit his or her program.  We discourage this.

The reason for providing this example is to give PMs and their staffs a starting point for their own planning process.  It should stimulate thought about what has to be done and give some ideas on how to begin writing a plan.  The sample plan contains more information than most program offices should need. Few PMs have the resources for a dedicated risk management effort as depicted in the plan.  The key to using the sample plan is to keep things simple and tailor the plan to suit your needs, focusing on the management of risk in the key critical areas of your program.

The italicized text reflects the outline of a risk management plan found in the DoD Acquisition Deskbook section 2.5.2.4, Figure 2.5.2.4-2.

## Sample Format for Risk Management Plan

INTRODUCTION.  This section should address the purpose and objective of the plan, and provide a brief summary of the program, to include the approach being used to manage the program, and the acquisition strategy.

PROGRAM SUMMARY.  This section contains a brief description of the program, including the acquisition strategy and the program management approach.  The acquisition strategy should address its linkage to the risk management strategy.

DEFINITIONS.  Definitions used by the program office should be consistent with DoD definitions for ease of understanding and consistency.  However, the DoD definitions allow program managers flexibility in constructing their risk management programs.  Therefore, each program’s risk management plan may include definitions that expand the DoD definitions to fit its particular needs.  For example, each plan should include, among other things, definitions for the ratings used for technical, schedule and cost risk.  (Discussion of risk rating is contained in Acquisition Deskbook Section 2.5.2.1.)

RISK MANAGEMENT STRATEGY AND APPROACH.  Provide an overview of the risk management approach, to include the status of the risk management effort to date, and a description of the program risk management strategy.  See Acquisition Deskbook Sections 2.5.2.1 and 2.5.2.3.

ORGANIZATION.  Describe the risk management organization of the program office and list the responsibilities of each of the risk management participants.  See Acquisition Deskbook Section 2.5.2.3.

RISK MANAGEMENT PROCESS AND PROCEDURES.  Describe the program risk management process to be employed; i.e., risk planning, assessment, handling, monitoring and documentation, and a basic explanation of these components.  See Acquisition Deskbook Section 2521.  Also provide application guidance for each of the risk management functions in the process.  If possible, the guidance should be as general as possible to allow the program’s risk management organization (e.g., IPTs) flexibility in managing the program risk, yet specific enough to ensure a common and coordinated approach to risk management.  It should address how the information associated with each element of the risk management process will be documented and made available to all participants in the process, and how risks will be tracked, to include the identification of specific metrics if possible.

RISK PLANNING.  This section describes the risk planning process and provides guidance on how it will be accomplished, and the relationship between continuous risk planning and this RMP.  Guidance on updates of the RMP and the approval process to be followed should also be included.  See Section 2.5.2.1 of the Deskbook for information on risk planning.

RISK ASSESSMENT. This section of the plan describes the assessment process and procedures for examining the critical risk areas and processes to identify and document the associated risks.  It also summarizes the analyses process for each of the risk areas leading to the determination of a risk rating.  This rating is a reflection of the potential impact of the risk in terms of its variance from known Best Practices or probability of occurrence, its consequence, and its relationship to other risk areas or processes.  This section may include:

- Overview and scope of the assessment process

- Sources of information

- Information to be reported and formats

- Description of how risk information is retained

- Assessment techniques and tools (see Section 2.5.2.4 of the Deskbook)

RISK HANDLING.  This section describes the procedures that can be used to determine and evaluate various risk handling options, and identifies tools that can assist in implementing the risk handling process.  It also provides guidance on the use of the various handling options for  specific risks.

RISK MONITORING.  This section describes the process and procedures that will be followed to monitor the status of the various risk events identified.  It should provide criteria for the selection of risks to be reported on, and the frequency of reporting.  Guidance on the selection of metrics should also be included.

RISK MANAGEMENT INFORMATION SYSTEM, DOCUMENTATION AND REPORTS.  This section describes the MIS structure, rules, and procedures that will be used to document the results of the risk management process.  It also identifies the risk management documentation and reports that will be prepared; specifies the format and frequency of the reports; and assigns responsibility for their preparation.

## SAMPLE RISK MANAGEMENT PLAN FOR THE XYZ PROGRAM

## 1.0	INTRODUCTION

## 1.1	Purpose

This Risk Management Plan (RMP) presents the process for implementing proactive risk management as part of the overall management of the XYZ program.  Risk management is a program management tool to assess and mitigate events that might adversely impact the program thereby increasing the likelihood of success.  This RMP will:

- Serve as a basis for identifying alternatives to achieve cost, schedule, and performance goals,

- Assist in making decisions on budget and funding priorities,

- Provide risk information for Milestone decisions, and

- Allow monitoring the health of the program as it proceeds.

The RMP describes methods for identifying, analyzing, prioritizing, and tracking risk drivers; developing risk-handling plans; and planning for adequate resources to handle risk.  It assigns specific responsibilities for the management of risk and prescribes the documenting, monitoring, and reporting processes to be followed.

This is the second edition of the Risk Management Plan for the XYZ program.  The initial plan concentrated on tasks leading to Milestone I (Phase 0); this plan concentrates on the tasks leading to Milestone II (Phase I).  Subsequent updates to this RMP will shift focus to the later acquisition phases.  There are changes in every area of the plan; they include refinement of the risk identification process.  The PMO Risk Management Coordinator has been identified and training of IPT members has commenced.

## 1.2	Program Summary

The XYZ program was initiated in response to Mission Need Statement (MNS) XXX, dated DD-MM-YYYY and Operational Requirements Document (ORD), dated DD-MM-YYYY.  It is required to support the fundamental objective of U.S. defense policy as stated in Defense Planning Guidance (DPG) and the National Military Strategy.  The XYZ system is based on the need for an integrated combat system to link battlefield decision makers.  The XYZ mission areas are: (Delineate applicable areas).

The XYZ program will develop and procure 120 advanced platforms to replace the aging ABC platforms currently in the inventory.  In order to meet force structure objectives, the XYZ system must reach Initial Operational Capability (IOC) (four platforms) by FY-07.  The program is commencing an eight-year EMD phase that will be followed by a five-year procurement phase.  The objectives of the EMD phase are to (discuss the specific objectives of this phase).  The program has Congressional interest and is restricted to a Research and Development funding ceiling of $300 million.

### 1.2.1	System Description

The XYZ will be an affordable, yet capable, platform taking advantage of technological simplification and advancements.  The XYZ integrated Combat System includes all non-propulsion electronics and weapons.  Subsystems provide capabilities in combat control, electronic warfare support measures (ESM), defensive warfare, navigation, radar, interior communications, monitoring, data transfer, tactical support device, exterior communications, and Identification Friend or Foe (IFF).  Weapons systems are to be provided by the program offices that are responsible for their development.  The Mechanical, and Electrical (M&E) system comprises. ...  The Combat System, M&E systems, and subsystems provide the XYZ system with the capability and connectivity to accomplish the broad range of missions defined in the MNS and ORD.

### 1.2.2	Acquisition Strategy

The XYZ program initial strategy is to contract with one prime contractor in Program Definition/Risk Reduction (PDRR) for development of two prototype systems for test and design validation.  Due to the technical complexity of achieving the performance levels of the power generation systems, the prime will use two sub-contractors for the engine development and down select to one producer prior to low rate initial production, which is scheduled for FY-04.  Various organizations, such as the Government Research Laboratory will be funded to provide experts for assessment of specific areas of risk.  The program has exit criteria, included in the list of Critical Program Attributes in Annex A, that must be met before progressing to the next phase.

### 1.2.3	Program Management Approach

The XYZ program is managed using the IPPD concept, with program integrated product teams (PIPTs) established largely along the hierarchy of the product work breakdown structure (WBS).  There are also cost-performance and test Working IPTs (WIPTs) established for vertical coordination up the chain of command.  The PM chairs a program integrating IPT (IIPT) that addresses issues that are not resolved at the WIPT level.

## 1.3	Definitions

### 1.3.1	Risk

Risk is a measure of the inability to achieve overall program objectives within defined cost, schedule, and technical constraints and has two components: (1) the probability of failing to achieve a particular outcome and (2) the consequences of failing to achieve that outcome.  For processes, risk is a measure of the difference between actual performance of a process and the known best practice for performing that process.

### 1.3.2	Risk Event

Risk e and those events within the XYZ program that, if they go wrong, could result in problems in the development, production, and fielding of the system.  Risk events should be defined to a level such that the risk and causes are understandable and can be accurately assessed in terms of likelihood/probability and consequence to establish the level of risk.  For processes, risk events are assessed in terms of process variance from known best practices and potential consequences of the variance.

### 1.3.3	Technical Risk

This is the risk associated with the evolution of the design and the production of the XYZ system affecting the level of performance necessary to meet the operational requirements.  The contractor’s and subcontractors’ design, test, and production processes (process risk) influence the technical risk and the nature of the product as depicted in the various levels of the Work Breakdown Structure (product risk).

### 1.3.4	Cost Risk

This is the risk associated with the ability of the program to achieve its life-cycle cost objectives.  Two risk areas bearing on cost are (1) the risk that the cost estimates and objectives are accurate and reasonable and (2) the risk that program execution will not meet the cost objectives as a result of a failure to mitigate technical risks.

### 1.3.5	Schedule Risk

These risks are those associated with the adequacy of the time estimated and allocated for the development, production, and fielding of the system.  Two risk areas bearing on schedule risk are (1) the risk that the schedule estimates and objectives are realistic and reasonable and (2) the risk that program execution will fall short of the schedule objectives as a result of failure to mitigate technical risks.

### 1.3.6	Risk Ratings

This is the value that is given to a risk event (or the program overall) based on the analysis of the likelihood/probability and consequences of the event.  For the XYZ program, risk ratings of Low, Moderate, or High will be assigned based on the following criteria.  See Section 3.3.2 for guidance on determining likelihood and consequences.  When rating process variance from best practices, there is no rating of likelihood/probability, rather the level would be a measure of the variance from best practices (see Paragraph 3.3.2.3).

- Low Risk:  Has little or no potential for increase in cost, disruption of schedule, or degradation of performance.  Actions within the scope of the planned program and normal management attention should result in controlling acceptable risk.

- Moderate Risk:  May cause some increase in cost, disruption of schedule, or degradation of performance.  Special action and management attention may be required to control acceptable risk.

- High Risk:  Likely to cause significant increase in cost, disruption of schedule, or degradation of performance.  Significant additional action and high priority management attention will be required to control acceptable risk.

### 1.3.7	Independent Risk Assessor

An independent risk assessor is a person who is not in the management chain or directly involved in performing the tasks being assessed.  Use of independent risk assessors is a valid technique to ensure that all risk areas are identified and that the consequence and likelihood/probability (or process variance) are properly understood.  The technique can be used at different program levels, e.g., Program Office, Service Field Activities, Contractors, etc.  The Program Manager will approve the use of independent assessors, as needed.

### 1.3.8	Templates and Best Practices

A “template” is a disciplined approach for the application of critical engineering and manufacturing processes that are essential to the success of most programs.  DoD 4245.7-M, Transition from Development to Production  Solving the Risk Equation, provides a number of such templates.  For each template process described in DoD 4245.7-M, a Best Practice Information is described in NAVSO P-6071.  These documents outline the ideal or low risk approach and thus serve as a baseline from which risk for some XYZ processes can be assessed.

### 1.3.9	Metrics

There are measures used to indicate progress or achievement.

### 1.3.10	Critical Program Attributes

Critical Program Attributes are performance, cost, and schedule properties or values that are vital to the success of the program.  They are derived from various sources, such as the Acquisition Program Baseline, exit criteria for the next program phase, Key Performance Parameters, test plans, the judgment of program experts, etc.  The XYZ program will track these attributes to determine the progress in achieving the final required value.  See Annex A for a list of the XYZ Critical Program Attributes.

## 2.0	RISK MANAGEMENT

## 2.1	General Approach and Status

DoD Directive 5000.1 states:  “Risks must be well understood, and risk management approaches developed, before decision authorities can authorize a program to proceed into the next phase of the acquisition process.”  This policy is implemented in DoD Regulation 5000.2-R, with more detailed guidance provided in the individual Service regulation.  The Defense Acquisition Deskbook (Section 2.5.2) provides additional guidance, advice, and wisdom on the management of risk.  Figure 2-1 shows how the XYZ program risk management fits into the phases and milestones of the acquisition process.

Figure 2.1.  Risk Management and the Acquisition Process

The XYZ program will use a centrally developed risk management strategy throughout the acquisition process and decentralized risk planning, assessment, handling, and monitoring.  XYZ risk management is applicable to all acquisition functional areas.

The results of the Concept Exploration Phase of the program identified potential risk events and the Acquisition Strategy reflects the program’s risk-handling approach.  Overall, the risk of the XYZ program for Milestone I was assessed as moderate, but acceptable.  Moderate risk functional areas were threat, manufacturing, cost, funding, and schedule.  The remaining functional areas of technology, design and engineering (hardware and software), support, (schedule) concurrency, human systems integration, and environmental impact were assessed as low risk.

## 2.2	Risk Management Strategy

The basic risk management strategy is intended to identify critical areas and risk events, both technical and non-technical, and take necessary action to handle them before they can become problems, causing serious cost, schedule, or performance impacts.  This program will make extensive use of modeling and simulation, technology demonstrations, and prototype testing to handle risk.

Risk management will be accomplished using the integrated Government-Contractor IPT organization.  These IPTs will use a structured assessment approach to identify and analyze those processes and products that are critical to meeting the program objectives.  They will then develop risk-handling options to mitigate the risks and monitor the effectiveness of the selected handling options.  Key to the success of the risk management effort is the identification of the resources required to implement the developed risk-handling options.

Risk information will be captured by the IPTs in a risk management information system (RMIS) using a standard Risk Information Form (RIF).  The RMIS will provide standard reports, and is capable of preparing ad hoc tailored reports.  See Annex B for a description of the RMIS and RIF.

Risk information will be included in all program reviews, and as new information becomes available, the PMO and contractor will conduct additional reviews to ascertain if new risks exist.  The goal is to be continuously looking to the future for areas that may severely impact the program.

## 2.3	Organization

The risk organization for the XYZ program is shown in Figure 2-2.  This is not a separate organization, but rather shows how risk is integrated into the program’s existing organization and shows risk relationships among members of the program team.

Figure 2-2.  XYZ Risk Management Organization

### 2.3.1	Risk Management Coordinator

The Risk Management Coordinator, the XYZ Technology Assessment and R&D Manager, is overall coordinator of the Risk Management Program.  The Risk Management Coordinator is responsible for:

- Maintaining this Risk Management Plan

- Maintaining the Risk Management Data Base

- Briefing the PM on the status of XYZ program risk

- Tracking efforts to reduce moderate and high risk to acceptable levels

- Providing risk management training

- Facilitating risk assessments and

- Preparing risk briefings, reports, and documents required for Program Reviews and the acquisition Milestone decision processes.

### 2.3.2	Program Integrating Integrated Product Team (PIIPT)

The PIIPT is responsible for complying with the DoD risk management policy and for structuring an efficient and useful XYZ risk management approach.  The Program Manager is the Chair of the PIIPT.  The PIIPT membership may be adjusted but is initially established as the chairs of the Program IPTs, designated sub-tier IPTs, and the Heads of PMO Functional Offices.

### 2.3.3	PIPTs

The program IPTs are responsible for implementing risk management tasks per this plan.  This includes the following responsibilities:

- Review and recommend to the Risk Management Coordinator changes on the overall risk management approach based on lessons learned.

- Quarterly, or as directed, update the program risk assessments made during 
Phase I.

- Review and be prepared to justify the risk assessments made and the risk mitigation plans proposed.

- Report risk to the Risk Management Coordinator via Risk Information Forms (RIFs).

- Ensure that risk is a consideration at each Program and Design Review.

- Ensure Design/Build Team responsibilities incorporate appropriate risk management tasks.

### 2.3.4	XYZ Independent Risk Assessors

Independent Assessors made a significant contribution to the XYZ Milestone I risk assessments.  The use of independent assessments as a means of ensuring that all risk areas are identified will continue, when necessary.

### 2.3.5	Other Risk Assessment Responsibilities

The Risk Assessment responsibilities of other Systems Command codes, Service Field Activities, Design/Build Teams, and Contractors will be as described in Memoranda of Agreement (MOAs), Memoranda of Understanding (MOUs), Systems Command Tasking, or contracts.  This RMP should be used as a guide for XYZ risk management efforts.

### 2.3.6	User Participation

The Requirements Organization (specific code) is the focal point for providing the Program Executive Officer or the Project Manager with user identified risk assessments.

### 2.3.7	Risk Training

The key to the success of the risk efforts is the degree to which all members of the team, both Government and contractor are properly trained.  The XYZ Program Office will provide risk training, or assign members to training classes, during acquisition Phases I and II.  Key personnel with XYZ management or assessment responsibilities are required to attend.  All members of the team will receive, at a minimum, basic risk management training.  XYZ sponsored training is planned to be presented according to the schedule provided in Annex x (not provided).

## 3.0	RISK MANAGEMENT PROCESS AND PROCEDURES

## 3.1	OVERVIEW

This section describes XYZ program’s risk management process and provides an overview of the XYZ risk management approach.  The Defense Acquisition Deskbook defines risk management as “the act or practice of controlling risk.  It includes risk planning, assessing risk areas, developing risk-handling options, monitoring risks to determine how risks have changed, and documenting the overall risk management program.”  Figure 3-1 shows, in general terms, the overall risk management process that will be followed in the XYZ program.  This process follows DoD and Service policies and guidelines and  incorporates ideas found in other sources.  Each of the risk management functions shown in Figure 3-1 is discussed in the following paragraphs, along with specific procedures for executing them.

Figure 3-1.  The Risk Management Process

## 3.2	RISK PLANNING

### 3.2.1	rocess

Risk planning consists of the up-front activities necessary to execute a successful risk management program.  It is an integral part of normal program planning and management.  The planning should address each of the other risk management functions, resulting in an organized and thorough approach to assess, handle, and monitor risks.  It should also assign responsibilities for specific risk management actions and establish risk reporting and documentation requirements.  This RMP serves as the basis for all detailed risk planning, which must be continuous.

### 3.2.2	rocedures

3.2.2.1  Responsibilities.  Each IPT is responsible for conducting risk planning, using this RMP as the basis.  The planning will cover all aspects of risk management to include assessment, handling options, and monitoring of risk mitigation activities. The Program Risk Management Coordinator will monitor the planning activities of the IPTs to ensure that they are consistent with this RMP and that appropriate revisions to this plan are made when required to reflect significant changes resulting from the IPT planning efforts.

Each person involved in the design, production, operation, support, and eventual disposal of the XYZ system or any of its systems or components is a part of the risk management process.  This involvement is continuous and should be considered a part of the normal management process.

3.2.2.2  Resources and Training.  An effective risk management program requires resources.  As part of its planning process, each IPT will identify the resources required to implement the risk management actions.  These resources include time, material, personnel, and cost.  Training is major consideration.  All IPT members should receive instruction on the fundamentals of risk management and special training in their area of responsibility, if necessary.

3.2.2.3  Documentation and Reporting.  This RMP establishes the basic documentation and reporting requirements for the program.  IPTs should identify any additional requirements that might be needed to effectively manage risk at their level.  Any such additional requirements must not conflict with the basic requirements in this RMP.

3.2.2.4  Metrics.  Each IPT should establish metrics that will measure the effectiveness of their planned risk-handling options.  See Annex C for an example of metrics that may be used.

3.2.2.5 Risk Planning Tools.  The following tools can be useful in risk planning.  It may be useful to provide this information to the contractors to help them understand the XYZ program’s approach to managing risk.  This list is not meant to be exclusive.

- DoD Manual 4245.7-M, a DoD guide for assessing process technical risk.

- The Navy’s Best Practices Manual, NAVSO P-6071, provides additional insight into each of the Templates in DoD 4245.7-M and a checklist for each template.

- Program Manager’s Work Station (PMWS) software, may be useful to some risk assessors.  PMWS has a Risk Assessment module based on the Template Manual and Best Practices Manual.

- Commercial risk management software offer options.

- Government risk management software, such as Risk Matrix developed by Mitre Corporation for the Air Force and the New Attack Submarine’s On-Line Risk Data Base (OLRDB) are excellent tools.

3.2.2.6  Plan Update.  This RMP will be updated, if necessary, on the following occasions: (1) whenever the acquisition strategy changes, or there is a major change in program emphasis; (2) in preparation for major decision points; (3) in preparation for and immediately following technical audits and reviews; (4) concurrent with the review and update of other program plans; and (5) in preparation for a POM submission.

## 3.3	Risk Assessment

The risk assessment process includes the identification of critical risk events/processes, which could have an adverse impact on the program, and the analyses of these events/processes to determine the likelihood of occurrence/process variance and consequences.  It is the most demanding and time-consuming activity in the risk management process.

### 3.3.1	Process

3.3.1.1  Identification.  Risk identification is the first step in the assessment process.  The basic process involves searching through the entire XYZ program to determine those critical events that would prevent the program from achieving its objectives.  All identified risks will be documented in the RMIS, with a statement of the risk and a description of the conditions or situations causing concern and the context of the risk.

Risks will be identified by all IPTs and by any individual in the program.  The lower-level IPTs can identify significant concerns earlier than otherwise might be the case and identify those events in critical areas that must be dealt with to avoid adverse consequences.  Likewise, individuals involved in the detailed and day-to-day technical, cost, and scheduling aspects of the program are most aware of the potential problems (risks) that need to be managed.

3.3.1.2  Analysis.  This process involves:

- Identification of WBS elements

- Evaluation of the WBS elements using the risk areas to determine risk events

- Assignment of likelihood/probability and consequence to each risk event to establish a risk rating

- Prioritization of each risk event relative to other risks.

Risk analysis should be supported by a study, test results, modeling and simulation, trade study, the opinion of a qualified expert (to include justification of his or her judgment), or any other accepted analysis technique.  The DoD Acquisition Deskbook, Section 2524.2 describes a number of analysis techniques that may be useful.  Evaluators should identify all assumptions made in assessing risk.  When appropriate, a sensitivity analysis should be done on assumptions.

Systems engineering analysis, risk assessments, and manpower risk assessments provide additional information that must be considered.  This includes, among other things, environmental impact, system safety and health analysis, and security considerations.  Classified programs may experience difficulties in access, facilities, and visitor control that can introduce risk and must be considered.

The analysis of individual risk will be the responsibility of the IPT identifying the risk, or the IPT to which the risk has been assigned.  They may use external resources for assistance, such as field activities, Service laboratories, and contractors.  The results of the analysis of all identified risks must be documented in the RMIS.

### 3.3.2	Procedures

3.3.2.1  Assessments—General.  Risk assessment is an iterative process, with each assessment building on the results of previous assessments.  The current baseline assessment is a combination of the risk assessment delivered by the contractors as part of Phase 0, the program office process risk assessment done before Milestone I, and the post-award Integrated Baseline Review (IBR).

For the program office, unless otherwise directed in individual tasking, program level risk assessments will be presented at each Program Review meeting with a final update not later than 6 months before  the next scheduled Milestone decision. The primary source of information for the next assessment will be the current assessment baseline, and existing documentation such as, Phase 0 study results, the design mission profile that was done as part of Phase 0, the Integrated Baseline Review (IBR), which will be conducted immediately after Phase I contract award, the contract WBS that is part of the IBR, industry best practices as described in the PMWS Knowledgebase, the ORD, the Acquisition Program Baseline (APB), and any contractor design documents.

IPTs should continually assess the risks in their areas, reviewing risk-mitigation actions and the critical risk areas whenever necessary to assess progress.  For contractors, risk assessment updates should be made as necessary.

The risk assessment process is intended to be flexible enough so that field activities, service laboratories, and contractors may use their judgment in structuring procedures considered most successful in identifying and analyzing all risk areas.

3.3.2.2  Identification.  Following is a description of step-by-step procedures that evaluators may use as a guide to identify program risks.

- Step One—Understand the requirements and the program performance goals, which are defined as thresholds and objectives (see 5000.2-R).  Describe the operational (functional and environmental) conditions under which the values must be achieved by referring or relating to design documents.  The ORD and APB contain Key Performance Parameters (KPPs).

- Step Two—Determine the engineering and manufacturing processes that are needed to design, develop, produce, and support the system.  Obtain industry best practices for these processes.

- Step Three—Identify contract WBS elements (to include products and processes).

- Step Four—Evaluate each WBS element against sources/areas of risk described in Table 4-2 fo the DSMC Risk Management Guide.

- Step Five—Assign a probability and consequence to each risk event

- Step Six—Prioritize the risk events.

Following are indicators that IPTs may find helpful in identifying and assessing risk:

- Lack of Stability, Clarity, or Understanding of Requirements:  Requirements drive the design of the system.  Changing or poorly stated requirements guarantees the introduction of performance, cost, and schedule problems.

- Failure to Use Best Practices virtually assures that the program will experience some risk.  The further a contractor deviates from best practices, the higher the risk.

- New Processes should always be suspect, whether they are related to design, analysis, or production.  Until they are validated, and until the people who implement them have been trained and have experience in successfully using the process, there is risk.

- Any Process Lacking Rigor should also be suspect; it is inherently risky.  To have rigor, a process should be mature and documented, it should have been validated, and it should be strictly followed.

- Insufficient Resources:  People, funds, schedule, and tools are necessary ingredients for successfully implementing a process.  If any are inadequate, to include the qualifications of the people, there is risk.

- Test Failure may indicate corrective action is necessary.  Some corrective actions may not fit available resources, or the schedule, and (for other reasons as well) may contain risk.

- Qualified Supplier Availability:  A supplier not experienced with the processes for designing and producing a specific product is not a qualified supplier and is a source of risk.

- Negative Trends or Forecasts are cause for concern (risk) and may require specific actions to turn around.

There are a number of techniques and tools available for identifying risks.  Among them are:

- Best Judgment:  The knowledge and experience of the collective, multi-disciplined Integrated Project Team (IPT) members and the opinion of subject matter experts (SMEs) are the most common source of risk identification.

- Lessons Learned from similar processes can serve as a baseline for the successful way to achieve requirements.  If there is a departure from the successful way, there may be risk.

- DoD 4245.7-M, “Transition from Development to Production,” is often called the “Templates” book because it identifies technical risk areas and provides, in “bullet” form, suggestions for avoiding those risks.  It focuses on the technical details of product design, test, and production to help managers proactively manage risk.  It also includes chapters on Facilities, Logistics, and Management, which make this a useful tool in identifying weak areas of XYZ planned processes early enough to implement actions needed to avoid adverse consequences.

- The NAVSO P-6071 Best Practices Manual was developed by the Navy to add depth to the Template Book, DoD 4245.7-M.

- Critical Program Attributes are metrics that the program office developed to measure progress toward meeting our objectives.  Team members, IPTs, functional managers, contractors, etc., may develop their own metrics to support these measurements.  The attributes may be specification requirements, contract requirements, or measurable parameters from any agreement or tasking.  The idea is to provide a means to measure whether we are on track in achieving our objectives.

- Methods and Metrics for Product Success is a manual published by the Office of the Assistant Secretary of the Navy (RDA) Product Integrity Directorate.  It highlights areas related to design, test, and production processes where problems are most often found and metrics for the measurement of effectiveness of the processes.  It also describes the software tool, Program Manager’s Work Station (PMWS).  See next paragraph.

- PMWS contains risk management software, “Technical Risk Identification and Mitigation System (TRIMS) and Knowledgebase.”  They provide a tailorable management system based on NAVSO P-6071 and DoD 4245.7-M.  The PMWS provides a compact disk (CD) that contains the necessary programs for assessing a program’s risk and software for program management.  PMWS can be obtained by calling the Best Manufacturing Program (BMP) Office at (301) 403-8100.

- New Nuclear Submarine (NSSN) On-Line Risk Database (ONLRB) is a software tool may be used to support the XYZ Risk Management Process. The tool helps IPTs in the identification and assessment of risk and management of handling efforts.

- Risk Matrix is another candidate for use by the PMO.  It is an automated tool, developed by Mitre Corporation, that supports a structured approach for identifying risk and assessing its potential program impact.  It is especially helpful for prioritizing risks.

- Requirements Documents describe the output of our efforts.  IPT efforts need to be monitored continuously to ensure requirements are met on time and within budget.  When they aren’t, there is risk.

- Contracting for Risk Management helps ensure the people involved with the details of the technical processes of design, test, and production are involved with managing risk.  The principle here is that those performing the technical details are normally the first ones to know when risks exist.

- Quality Standards, such as ISO9000, ANSI/ASQC Q 9000, MIL-HDBK 9000, and others describe processes for developing and producing quality products.  Comparing our processes with these standards can highlight areas we may want to change to avoid risk.

- Use of Independent Risk Assessors is a method to help ensure all risk is identified.  The knowledgeable, experienced people are independent from the management and execution of the processes and procedures being reviewed.  Independent assessment promotes questions and observations not otherwise achievable.

3.3.2.3  Analysis.  Risk analysis is an evaluation of the identified risk events to determine possible outcomes, critical process variance from known best practices, the likelihood of those events occurring, and the consequences of the outcomes.  Once this information has been determined, the risk event may be rated against the program’s criteria and an overall assessment of low, moderate, or high assigned.  Figure 3-2 depicts the risk analysis process and procedures.

Figure 3-2.  Risk Assessment Process

Critical Process Variance.  For each process risk related event identified, the variance of the process from known standards or best practices must be determined.  As shown in Figure 3-2, there are five levels (a-e) in the XYZ risk assessment process, with the corresponding criteria of Minimal, Small, Acceptable, Large, and Significant.  If there is no variance then there is no risk.

Likelihood/Probability.  For each risk area identified, the likelihood the risk will happen must be determined.  As shown in Figure 3-2, there are five levels (a-e) in the XYZ risk assessment process, with the corresponding criteria of Remote, Unlikely, Likely, Highly Likely, and Near Certainty.  If there is zero likelihood of an event, there is no risk per our definition.

Consequence. For each risk area identified, the following question must be answered: Given the event occurs, what is the magnitude of the consequence?  As shown in the figure, there are five levels of consequence (1-5).  “Consequence” is a multifaceted issue.  For this program, there are four areas that we will evaluate when determining consequence: technical performance, schedule, cost, and impact on other teams.  At least one of the four consequence areas needs to apply for there to be risk; if there is no adverse consequence in any of the areas, there is no risk.

- Technical Performance:  This category includes all requirements that are not included in the other three metrics of the Consequence table.  The wording of each level is oriented toward design processes, production processes, life cycle support, and to retirement of the system.  For example, the word “margin” could apply to weight margin during design, safety margin during testing, or machine performance margin during production.

- Schedule:  The words used in the Schedule column, as in all columns of the Consequence table, are meant to be universally applied.  Avoid excluding a consequence level from consideration just because it doesn’t match your team’s specific definitions.  In other words, phrases such as need dates, key milestones, critical path, and key team milestones are meant to apply to all IPTs.

- Cost:  Since costs vary from component to component and process to process, the percentage criteria shown in the figure may not strictly apply at the lower levels of the WBS.  These team leaders can set the percentage criteria that best reflects their situation.  However, when costs are rolled up at higher levels (e.g., Program), the following definitions will be used:  Level 1—no change, Level 2—<5%, Level 3—5-7%, Level 4—7-10%, and Level 5—>10%.

- Impact on Other Teams:  Both the consequence of a risk and the mitigation actions associated with reducing the risk may impact another team.  This may involve additional coordination or management attention (resources) and may therefore increase the level of risk.  This is especially true of common technical processes.

Risk Rating.  Probability and consequence should not always be considered equally; for example, there may be consequences so severe that it is considered high risk even though the probability to achieve a particular outcome is low.  After deciding a level of process variance/likelihood (a through e) and a level of consequence (1 through 5), enter the Assessment Guide portion of Figure 3-2 to obtain a risk rating (green = LOW, yellow = MOD, and red = HIGH).  For example; consequence/process variance/likelihood level 2b corresponds to LOW risk, level 3d corresponds to MOD risk, level 4c corresponds to HIGH risk.  After obtaining the risk rating, make a subjective comparison of the risk event with the applicable rating definition in Figure 3-2 (e.g., High=unacceptable, major disruptions, etc.).  There should be a close match.  If there isn’t, consider reevaluating the level of likelihood or consequence.  Those risk events that are assessed as moderate or high should be submitted to the XYZ Risk Management Coordinator on a RIF.

Figure 3-2 is useful to convey information to decision makers and will be used primarily for that purpose.  The PMO will use the Risk Tracking Report and Watchlist.  (See Annex D.)

## 3.4	Risk Handling

### 3.4.1	Process

After the program’s risks have been identified and assessed, the approach to handling each significant risk must be developed.  There are essentially four techniques or options for handling risks: avoidance, control, transfer, and assumption.  For all identified risks, the various handling techniques should be evaluated in terms of feasibility, expected effectiveness, cost and schedule implications, and the effect on the system’s technical performance, and the most suitable technique selected.  Section 2524.3 of the DoD Acquisition Deskbook contains information on the risk-handling techniques and various actions that can be used to implement them.  The results of the evaluation and selection will be included and documented in the RMIS using the RIF.  This documentation will include: what must be done, the level of effort and materials required, the estimated cost to implement the plan, a proposed schedule showing the proposed start date, the time phasing of significant risk reduction activities, the completion date, and their relationship to significant Program activities/milestones (an example is provided in Annex B), recommended metrics for tracking the action, a list of all assumptions, and the person responsible for implementing and tracking the selected option.

### 3.4.2	Procedures

The IPT that assessed the risk is responsible for evaluating and recommending to the PM the risk-handling options that are best fitted to the program’s circumstances.  Once approved, these are included in the program’s acquisition strategy or management plans, as appropriate.

For each selected handling option, the responsible IPT will develop specific tasks that, when implemented, will handle the risk.  The task descriptions should explain what has to be done, the level of effort, and identify necessary resources.  It should also provide a proposed schedule to accomplish the actions including the start date, the time phasing of significant risk reduction activities, the completion date, and their relationship to significant Program activities/milestones (an example is provided in Annex B), and a cost estimate.  The description of the handling options should list all assumptions used in the development of the handling tasks.  Assumptions should be included in the RIF.  Recommended actions that require resources outside the scope of a contract or official tasking should be clearly identified, and the IPTs, the risk area, or other handling plans that may be impacted should be listed.

Reducing requirements as a risk avoidance technique will be used only as a last resort, and then only with the participation and approval of the user’s representative.

DoD 4245.7-M Templates and NAVSO P-6071 Best Practices, are useful in developing risk-handling actions for design, test, or manufacturing process risks.

## 3.5	Risk Monitoring

### 3.5.1	Process

Risk monitoring systematically tracks and evaluates the performance of risk-handling actions.  It is part of the PMO function and responsibility and will not become a separate discipline.  Essentially, it compares predicted results of planned actions with the results actually achieved to determine status and the need for any change in risk-handling actions.  The effectiveness of the risk-monitoring process depends on the establishment of a management indicator system (metrics) that provides accurate, timely, and relevant risk information in a clear, easily understood manner.  (See Annex D.)  The metrics selected to monitor program status must adequately portray the true state of the risk events and handling actions.  Otherwise, indicators of risks that are about to become problems will go undetected.

To ensure that significant risks are effectively monitored, risk-handling actions (which include specific events, schedules, and “success” criteria) will be reflected in integrated program planning and scheduling.  Identifying these risk-handling actions and events in the context of Work Breakdown Structure (WBS) elements establishes a linkage between them and specific work packages, making it easier to determine the impact of actions on cost, schedule, and performance.  The detailed information on risk-handling actions and events will be included in the RIF for each identified risk, and thus be resident in the RMIS.

### 3.5.2	Procedures

The functioning of IPTs is crucial to effective risk monitoring.  They are the “front line” for obtaining indications that risk-handling efforts are achieving their desired effects.  Each IPT is responsible for monitoring and reporting the effectiveness of the handling actions for the risks assigned.  Overall XYZ program risk assessment reports will be prepared by the XYZ Risk Management Coordinator working with the cognizant IPT.

Many techniques and tools are available for monitoring the effectiveness of risk-handling actions, and IPTs must ensure that they select those that best suit their needs.  No single technique or tool is capable of providing a complete answer—a combination must be used.  At a minimum, each IPT will maintain a watchlist of identified high priority risks.  See Section 2524.4 of the DoD Acquisition Deskbook for information on specific techniques.

Risks rated as Moderate or High risk will be reported to the XYZ Risk Management Coordinator, who will also track them, using information provided by the appropriate IPT, until the risk is considered Low and recommended for “Close Out.”  The IPT that initially reported the risk retains ownership and cognizance for reporting status and keeping the database current.  Ownership means implementing handling plans and providing periodic status of the risk and of the handling plans.  Risk will be made an agenda item at each management or design review, providing an opportunity for all concerned to offer suggestions for the best approach to managing risk.  Communicating risk increases the program’s credibility and allows early actions to minimize adverse consequences.

The risk management process is continuous.  Information obtained from the monitoring process is fed back for reassessment and evaluations of handling actions.  When a risk area is changed to Low, it is put into a “Historical File” by the Risk Management Coordinator and it is no longer tracked by the XYZ PMO.  The “owners” of all Low risk areas will continue monitoring Low risks to ensure they stay Low.

The status of the risks and the effectiveness of the risk-handling actions will be reported to the Risk Management Coordinator:

- Quarterly

- When the IPT determines that the status of the risk area has changed significantly (as a minimum when the risk changes from high to moderate to low, or vice versa)

- When requested by the Program Manager.

## 4.0	RISK MANAGEMENT INFORMATION SYSTEM AND DOCUMENTATION

The XYZ program will use the XXX database management system as its RMIS.  The system will contain all of the information necessary to satisfy the program documentation and reporting requirements.

## 4.1	Risk Management Information System (RMIS)

The RMIS stores and allows retrieval of risk-related data.  It provides data for creating reports and serves as the repository for all current and historical information related to risk.  This information will include risk assessment documents, contract deliverables, if appropriate, and any other risk-related reports.  The PMO will use data from the RMIS to create reports for senior management and retrieve data for day-to-day management of the program.  The program produces a set of standard reports for periodic reporting and has the ability to create ad hoc reports in response to special queries.  See Annex D for a detailed discussion of the RMIS.

Data are entered into the RMIS using the Risk Information Form (RIF).  The RIF gives members of the project team, both Government and contractors, a standard format for reporting risk-related information.  The RIF should be used when a potential risk event is identified and will be updated as information becomes available as the assessment, handling, and monitoring functions are executed.

## 4.2	Risk Documentation

All program risk management information will be documented, using the RIF as the standard RMIS data entry form.  The following paragraphs provide guidance on documentation requirements for the various risk management functions.

### 4.2.1	Risk-Assessment Documentation

Risk assessments form the basis for many program decisions.  From time to time, the PM will need a detailed report of any assessment of a risk event.  It is critical that all aspects of the risk management process are documented.

### 4.2.2	Risk-Handling Documentation

Risk-handling documentation will be used to provide the PM with the information he needs to choose the preferred mitigation option.

### 4.2.3	Risk-Monitoring Documentation

The PM needs a summary document that tracks the status of high and moderate risks.  The Risk Management Coordinator will produce a risk tracking list, for example, that uses information that has been entered from the RMIS.  This document will be produced on a monthly basis.

## 4.3	Reports

Reports are used to convey information to decision-makers and team members on the status of the program and the effectiveness of the risk management program.  Every effort will be made to generate reports using the data resident in the RMIS.

### 4.3.1	Standard Reports

The RMIS will have a set of standard reports.  If IPTs or functional managers need additional reports, they should work with the Risk Management Coordinator to create them.  Access to the reporting system will be controlled; however, any member of the Government or contractor team may obtain a password to gain access to the information.  See Annex B for a description of the XYZ program reports.

### 4.3.2	Ad Hoc Reports

In addition to standard reports, the PMO will need to create ad hoc reports in response to special queries.  The Risk Management Coordinator will be responsible for these reports.

# Annex A
Critical Program Attributes

| Category | Description | Responsible IPT | Remarks |
| --- | --- | --- | --- |
| Performance/Physical | Speed |  |  |
|  | Weight |  |  |
|  | Endurance |  |  |
|  | Crew Size |  |  |
|  | Survivability |  |  |
|  | Maneuverability |  |  |
|  | Size |  |  |
|  | Receiver Range |  |  |
|  | Transmitter Range |  |  |
|  | Data Link Operations |  |  |
|  | Recovery Time |  |  |
|  | Initial Setup |  |  |
|  | Identification Time |  |  |
|  | Accuracy Location |  |  |
|  | Probability of Accurate ID |  |  |
|  | Reliability |  |  |
|  | Maintainability |  |  |
|  | Availability |  |  |
|  | Etc. |  |  |
| Cost | Operating and Support Costs |  |  |
|  | Etc. |  |  |
| Processes | Requirements Stable |  |  |
|  | Test Plan Approved |  |  |
| Exit Criteria | Engine Bench Test |  |  |
|  | Accuracy Verified by Test Data and Analysis |  |  |
|  | Toolproofing Completed |  |  |
|  | Logistics Support Reviewed by User |  |  |

# Annex B
Program Risk Reduction Schedule

# Annex C
Program Metric Examples

Examples of Product-Related Metrics

| Engineering | Requirements | Production | Support |
| --- | --- | --- | --- |
| Key Design Parameters Weight Size Endurance Range Design Maturity Open problem reports Number of engineer-ing change proposals Number of drawings released Failure activities Computer Resource Utilization Etc. | Requirements Traceability Requirements Stability Threat Stability Design Mission Profile | Manufacturing Yields Incoming Material Yields Delinquent Requisitions Unit Production Cost Process Proofing Waste Personnel Stability | Special Tools and Test Equipment Requirements Support Infrastructure Footprint Manpower Estimates |

Examples of Process- Metrics

| Design Requirements | Trade Studies | Design Process | Integrated Test Plan | Failure Reporting System | Manufacturing Plan |
| --- | --- | --- | --- | --- | --- |
| Development of requirements traceability plan Development of specification tree Specifications reviewed for: Definition of all use environments Definition of all functional requirements for each mission performed | Users needs prioritized Alternative system configurations selected Test methods selected | Design requirements stability Producibility analysis conducted Design analyzed for: Cost Parts reduction Manufacturability Testability | All developmental tests at system and subsystem level identified Identification of who will do test (Government, contractor, supplier) | Contractor corporate-level management involved in failure reporting and corrective action process Responsibility for analysis and corrective action assigned to specific individual with close-out date | Plan documents methods by which design to be built Plan contains sequence and schedule of events at contractor and subcontractor that defines use of materials, fabrication flow, test equipment, tools, facilities, and personnel Reflects manufacturing inclusion in design process. Includes identification and assessment of design facilities |

Examples of Cost and Schedule Metrics

| Cost | Schedule |
| --- | --- |
| Cost variance Cost performance index Estimate at completion Management reserve | Schedule variance Schedule performance index Design Schedule Performance Manufacturing Schedule Performance Test Schedule Performance |

# Annex D
Management Information System and Documentation

## 1.0	Description

In order to manage risk, we need a database management system that stores and allows retrieval of risk-related data.  The Risk Management Information System provides data for creating reports and serves as the repository for all current and historical information related to risk.  This information may include risk assessment documents, contract deliverables, if appropriate, and any other risk-related reports.  The Risk Management Coordinator is responsible for the overall maintenance of the RMIS, and he or his designee are the only persons who may enter data into the database.

The RMIS will have a set of standard reports.  If IPTs or functional managers need additional reports, they should work with the Risk Management Coordinator to create them.  Access to the reporting system will be controlled; however, any member of the Government or contractor team may obtain a password to gain access to the information.

In addition to standard reports, the PMO will need to create ad hoc reports in response to special queries etc.  The Risk Management Coordinator will be responsible for these reports.  Figure B-1 shows a concept for a management and reporting system.

Figure B-1.  Conceptual Risk Management and Reporting System

## 2.0	Risk Management Reports

The following are examples of basic reports that a PMO may use to manage its risk program.  Each office should coordinate with the Risk Management Coordinator to tailor and amplify them, if necessary, to meets its specific needs.

## 2.1	Risk Information Form (Mandatory)

The PMO needs a document that serves the dual purpose of a source of data entry information and a report of basic information for the IPTs, etc.  The Risk Information Form (RIF) serves this purpose.  It gives members of the project team, both Government and contractors, a format for reporting risk-related information.  The RIF should be used when a potential risk event is identified and updated over time as information becomes available and the status changes.  As a source of data entry, the RIF allows the database administrator to control entries.  The format for a RIF is included on page C-26.

## 2.2	Risk Assessment Report (Not Mandatory)

Risk assessments form the basis for many program decisions, and the PM may need a detailed report of assessments of a risk event that has been done.  A Risk Assessment Report (RAR) is prepared by the team that assessed a risk event and amplifies the information in the RIF.  It documents the identification, analysis, and handling processes and results.  The RAR amplifies the summary contained in the RIF, is the basis for developing risk-handling plans, and serves as a historical recording of program risk assessment.  Since RARs may be large documents, they may be stored as files.  RARs should include information that links it to the appropriate RIF.

## 2.3	Risk-Handling Documentation (Not Mandatory)

Risk-handling documentation may be used to provide the PM with information he needs to choose the preferred mitigation option and is the basis for the handling plan summary contained in the RIF.  This document describes the examination process for risk-handling options and gives the basis for the selection of the recommended choice.  After the PM chooses an option, the rationale for that choice may be included.  There should be a time-phased plan for each risk-mitigation task.  Risk-handling plans are based on results of the risk assessment. This document should include information that links it to the appropriate RIF.

## 2.4	Risk Monitoring Documentation (Mandatory)

The PM needs a summary document that tracks the status of high and moderate risks.  The XYZ program will use a risk-tracking list that contains information that has been entered from the RIF.  An example of the tracking list is shown on page C-27.

## 3.0	Database Management System (DBMS)

The XYZ Risk Management Information System (RMIS) provides the means to enter and access data, control access, and create reports.

Key to the MIS are the data elements that reside in the database. Listed below are the types of risk information that will be included in the database.  “Element” is the title of the database field; “Description” is a summary of the field contents.  The Risk Management Coordinator will create the standard reports such as, the RIF, Risk Monitoring, etc.  The RMIS also has the ability to create “ad hoc” reports, which can be designed by users and the Risk Management Coordinator.

DBMS Elements

| Element | Description |
| --- | --- |
| Risk Identification (ID) Number | Identifies the risk and is a critical element of information, assuming that a relational database will be used by the PMO. (Construct the ID number to identify the organization responsible for oversight.) |
| Risk Event | States the risk event and identifies it with a descriptive name. The statement and risk identification number will always be associated in any report. |
| Priority | Reflects the importance of this risk priority assigned by the PMO compared to all other risks, e.g., a one indicates the highest priority. |
| Date Submitted | Gives the date that the RIF was submitted. |
| Major System/ Component | Identifies the major system/component based on the Work Breakdown Structure (WBS). |
| Subsystem/ Functional Area | Identifies the pertinent subsystem or component based on the WBS. |
| Category | Identifies the risk as technical/performance cost or schedule or combination of these. |
| Statement of Risk | Gives a concise statement (one or two sentences) of the risk. |
| Description of Risk | Briefly describes the risk; lists the key processes that are involved in the design, development, and production of the particular system or subsystem. If technical/performance, include how it is manifested (e.g., design and engineering, manufacturing, etc. |
| Key parameters | Identifies the key parameter, minimum acceptable value, and goal value, if appropriate. Identifies associated subsystem values required to meet the minimum acceptable value and describes the principal events planned to demonstrate that the minimum value has been met. |
| Assessment | States if an assessment has been done. Cites the Risk Assessment Report (see next paragraph), if appropriate. |
| Analysis | Briefly describes the analysis done to assess the risk; includes rationale and basis for results |
| Process Variance Probability of Occurrence | States the variance of critical technical processes from known standards or best practices, based on definitions in the program’s risk management plan. States the likelihood of the event occurring, based on definitions in the program’s risk-management plan. |
| Consequence | States the consequence of the event, if it occurs, based on definitions in the program’s risk-management plan. |
| Time Sensitivity | Estimates the relative urgency for implement the risk-handling option. |
| Other Affected Areas | If appropriate, identifies any other subsystem or process that this risk affects. |
| Risk Handling Plans | Briefly describes plans to mitigate the risk. Refers to any detailed plans that may exist, if appropriate. |
| Risk Monitoring Activity | Measurement and metrics for tracking progress in implementing risk-handling plans and achieving planned results for risk reduction. |
| Status | Briefly reports the status of the risk-handling activities and outcomes relevant to any risk-handling milestones. |
| Status Date | Lists date of the status report. |
| Assignment | Lists individual assigned responsibility for mitigation activities. |
| Reported By | Records name and phone number of individual who reported the risk. |

Risk Information Form

Risk Identification Number	Date

Risk Event:

Priority

Major System/ Component/Functional Area:

Category:

Statement of Risk:

Description of Risk:

Key parameters:

Assessment:

Analysis:

Process Variance

Probability of Occurrence:

Consequence:

Time Sensitivity:

Other Affected Areas:

Risk Handling Plans:

Risk Monitoring Activity:

Status:	Status Date:

Assignment:	Reported By:

# RISK TRACKING REPORT 
(Example Report)

Risk Area Status: Design	PF  Hi	CF:  Hi

Significant Design Risks:

1.	Title:  System Weight	PF  Hi	CF:  Hi

Problem:  Exceed system weight by 10%; decreasing the range and increasing fuel consumption.

Action:  Examining sub-systems to determine areas where weight may be reduced.  Reviewing the requirement.  Closely watching the effect on reliability and survivability.

2.	Title:  Design Analysis	Pv:  Hi	Cv:  Hi

Problem:  Failure Modes, Effects and Criticality Analysis (FMECA) is planned too late to identify and correct any critical single point failure points prior to design freeze.

Action:  Additional resources are being sought to expedite performance of FMECA.

Risk Area Status: Supportability	PF  Hi	CF:  Mod/Hi

1. 	Title:  Operational Support	PF  Hi	CF:  Mod/Hi

Problem:  Power supply sub-contractor is in financial trouble and may go out of business.  No other known sources exist.

Action:  Doing trade study to see if alternative designs have a broader power supply vendor base.  Prime contractor is negotiating with the sub-contractor to buy drawings for development of second source.

Watchlist Example

| Potential Risk Event | Risk Reduction Actions | Action Code | Due Date | Date Completed | Explanation |
| --- | --- | --- | --- | --- | --- |
|  Accurately predicting shock environment equipment will experience. |  Use multiple finite element codes & simplified numerical models for early assessments.  Shock test simple isolated structure, simple isolated deck, and proposed isolated structure to improve confidence in predictions. | SE03 SE03 | 31 Aug 97 31 Aug 98 |  |  |
|  Evaluating acoustic impact of ship systems that are not similar to previous designs. |  Concentrate on acoustic modeling and scale testing of technologies not demonstrated successfully in large scale tests or full scale trials.  Factor acoustic signature mitigation from isolated modular decks into system requirements. Continue model tests to validate predictions for isolated decks. | SE031 SE032 | 31 Aug 97 31 Aug 98 |  |  |