## Slide 1: Objective of the Presentation
To get an idea about the data that will be available in the Baan system from the cut-over date

## Slide 2: Definition of Project Cutover
The day TBW becomes operational using the Baan system

## Slide 3: Data Migration
Consists of two paths
  Conversion of data “electronically” from the existing system into the Baan system
  Entry of data “manually” in Baan

## Slide 4: Project Cut Over Plan
Objective
  To give an overall view of the methodology to be adopted to ensure that all the data that is required in the Baan system as of the Cut Off Date is available.
  Data migration

## Slide 5
1. Project
Bought Out Items
(Tp Items)
Manufactured Items
(Ti Items)
1.1
1.2

## Slide 6
1.1 Bought Out Items
(Tp Items)
Purchase Order
Raised
Purchase Order
yet to be Raised
1.1.1

## Slide 7: Purchase Order yet to be Raised
Entries to be Done
Project items to be created
Material detail lines to be entered
Activities to be attached to the Budget Detail Lines
Assumptions
Budget will be created manually and not transferred from an estimate

## Slide 8
1.1.1 Purchase Order Raised
Material Received
(Sent to site)
Material yet to
Received
1.1.1.1

## Slide 9: Material yet to be received
Entries to be done
Project Item code to be created
Material Budget Detail line to be maintained
Activity to be attached at the Budget Detail Line
Purchase Order will be created manually
Assumptions
Purchase Order will be raised only for the undelivered quantity

## Slide 10
1.1.1.1 Material Received (Sent to site)
Debtors
Creditors
1.1.1.1.1
1.1.1.1.2

## Slide 11
1.1.1.1.1 Debtors
Invoice Raised
on the Customer
Invoice yet to
be Raised on the
Customer
1.1.1.1.1.1

## Slide 12: Invoice yet to be Raised on the Customer
Entries to be done
None
Assumption
There will be no direct despatch for which an invoice is yet to be raised on the customer

## Slide 13
1.1.1.1.1.1 Invoice Raised on the Customer
Payment Received
Payment yet to
be Received

## Slide 14: Payment Received
Entries to be done
Maintain Revenues manually in Tp
Assumptions
None

## Slide 15: Payment yet to be Received
Entries to be done
Maintain Revenues manually in Tp
Enter Invoices as Open Entries in Finance
Assumptions
None

## Slide 16
1.1.1.1.2 Creditors
Suppliers Invoice
booked in Finance
Suppliers Invoice
yet to be booked in
Finance

## Slide 17: Suppliers Invoice yet to be Booked in Finance
Entries to be done
None
Assumptions
No entry will be done in Baan as all Suppliers Invoices will be accounted for in the legacy system before the cut over

## Slide 18: Suppliers Invoice Booked in Finance
Entries to be done
The invoices yet to be paid will be entered as open invoices in Finance
Assumptions
E1/E2 form tracking will be available only for those Purchase Orders which are raised from the system

## Slide 19
1.2 Manufactured Items (Ti Items)
Items yet to be
despatched
Items despatched
to Site
1.2.2
1.2.1

## Slide 20
1.2.1 Items Despatched to Site
Invoice Raised
on the Customer
Invoice yet to
be Raised on the
Customer
1.2.1.1

## Slide 21: Invoice yet to be Raised on the Customer
Entries to be done
None
Assumption
There will be no direct despatch for which an invoice is yet to be raised on the customer

## Slide 22
1.2.1.1 Invoice Raised on the Customer
Payment Received
Payment yet to
be Received

## Slide 23: Payment Received
Entries to be done
Maintain Revenues manually in Tp
Assumptions
None

## Slide 24: Payment yet to be Received
Entries to be done
Maintain Revenues manually in Tp
Enter Invoices as Open Entries in Finance
Assumptions
None

## Slide 25
1.2.2 Items yet to be despatched
Items not ready
for despatch
Items ready for
despatch
1.2.3

## Slide 26: Items ready for despatch
Entries to be done
Project item to be created
Material Budget Detail Line entered
Customised item created and linked to project item
Opening Inventory of Customised Item to be Entered
Assumptions
Only complete DU’s will be pending for despatch. Part despatch of DU’s will not take place as on the cut over

## Slide 27
1.2.3. Items not ready for despatch
Items in
Process
Components which
are completed and
lying in store
1.2.4

## Slide 28: Components which are completed and lying in store
Entries to be done
MR to be raised and issued to the shop floor where no part number is being planned for in Baan
For items having codes Opening inventory of customised item will be entered
Assumptions
Since such components will not have any part number in the new system they will be entered as WIP value

## Slide 29
1.2.4 Items in Process
Production Orders
Released
Production Orders
yet to be Released
1.2.5
1.3
Raw Material
Status

## Slide 30: Production Orders to be Released
Entries to be done
None
Assumptions
Ti PRP will generate the Production Orders
BOM will have to entered for all such items

## Slide 31
1.2.5 Production Orders Released
Material issued
to Sub-contractor/
Shop Floor
Material yet to be
Issued
1.2.6

## Slide 32: Material yet to be issued
Entries to be done
Material to be issued will be entered in Maintain Estimated Materials of Production Order
For Production Orders for which Material has already been issued, a dummy material will be issued to reflect the total material and operation cost incurred so far
Production orders being carried out in the shop floor will be created manually
Assumptions
A single dummy item will be created with a cost of Rs.10. Quantity will be adjusted to arrive at the cost
Inspection Orders will be created only for those operations which are completed after cut over

## Slide 33
1.2.6 Material issued to
Sub-contractor
Material yet to be
received back from the
sub-contractor
Material received back
from the
sub-contractor

## Slide 34: Material Received yet to be received from the Subcontractor
Entries to be done
None
Assumptions
All subcontracting Production Orders will be treated as if they are in house Production Orders. All TDC tracking will be continued to de done in the legacy system. Only adjustment entries will be done in Excise records

## Slide 35: Material Received from the Subcontractor but yet to be recorded
Entries to be done
None
Assumptions
There will no such items pending as on the cut over

## Slide 36
1.3 Raw Material Status
Raw Material
in Stock
Raw Material
not in Stock
1.3.1

## Slide 37: Raw Material in Stock
Entries to be done
The customised item or the standard item will be created as appropriate including lots and lot feature values
Assumptions
Only those item codes will be created for which stock exists or there exists an open transaction (e.g. open purchase order)

## Slide 38
Raw Material in Stock
The Stock (Quantity) as of the Cut Off date
will be entered in BaaN.
The data has to be collected by doing a cycle
counting 2 days prior to being entered in BaaN

## Slide 39
1.3.1 Raw Material not in Stock
Purchase Order
Raised
Purchase Order
yet to be Raised
1.3.2

## Slide 40: Purchase Order yet to be raised
Entries to be done
None
Assumptions
Ti PRP/MRP will be used to generate such Purchase Orders

## Slide 41
1.3.2 Purchase Order Raised
Material Received
but not approved
by inspection
Material yet to be
Received

## Slide 42: Material Received but not approved by Inspection
Entries to be done
None
Assumptions
All goods rejected should have been returned to the supplier as of the cut over
There should be no cases for which inspection is still pending.

## Slide 43: Material yet to be received
Entries to be done
Purchase Orders will be created manually with new code numbers and if necessary more number of detailed lines
Assumptions
A translation table between old purchase order lines and new purchase order lines for a certain period. Beyond that letter will go to supplier informing cancellation of old purchase order and enclosing corresponding new purchase order

## Slide 44
1.4 Service
Already
Commissioned
Under
Commissioning
1.4.1

## Slide 45
1.4.1 Already Commissioned
Under Warranty
Not Under
Warranty
Open Service Orders to be entered

## Slide 46
1.5 Indent for Consumables
Purchase Order
Raised
Purchase Order
yet to be Raised
1.5.1

## Slide 47: Purchase Order yet to be raised
Entries to be done
Manually create SIC planned orders
Assumptions
None

## Slide 48
1.5.1 Purchase Order Raised
Material
Received
Material yet
to be Received
1.5.2

## Slide 49: Material yet to be received
Entries to be done
Purchase Orders will be created manually with new code numbers and if necessary more number of detailed lines
Assumptions
A translation table between old purchase order lines and new purchase order lines for a certain period. Beyond that letter will go to supplier informing cancellation of old purchase order and enclosing corresponding new purchase order

## Slide 50
1.5.2 Material Received
Suppliers Invoice
booked in Finance
Suppliers Invoice
not booked in Finance

## Slide 51: Suppliers Invoice yet to be Booked in Finance
Entries to be done
None
Assumptions
No entry will be done in Baan as all Suppliers Invoices will be accounted for in the legacy system before the cut over

## Slide 52: Suppliers Invoice Booked in Finance
Entries to be done
The invoices yet to be paid will be entered as open invoices in Finance
Assumptions
E1/E2 form tracking will be available only for those Purchase Orders which are raised from the system

## Slide 53
AMR Released by Engineering
Purchase Order
not yet
Raised
Purchase Order
Raised

## Slide 54: Purchase Order Raised
Entries to be done
In all cases module planning entries will be done and dummy production order will be raised
Purchase orders will be created manually
Assumption
A translation table between old purchase order lines and new purchase order lines for a certain period. Beyond that letter will go to supplier informing cancellation of old purchase order and enclosing corresponding new purchase order

## Slide 55: Project Activities
The interface with Prima Vera is being developed, therefore it is possible to import all the activities which are yet to be completed as of the Cut Off Date into BaaN

## Slide 56: Finance Data
Entries to be done
Opening Balance for all the Ledger Accounts as of the Cut Off Date
Suppliers Invoices and Customer Invoices which are outstanding as of the Cut Off Date (only which have not been covered in earlier)
Fixed Asset wise Investment Value and Depreciation Value for Sch XIV and Sec 350 of the Companies Act.
Assumptions
The Excise records will be up to date as of the cut over
The value of the Opening Balance of Stocks/WIP will be the same as the figure calculated in the Logistics Package of Baan

## Slide 57: Assumptions for Project Cut Over
Finance Integrations will be set to no till all cut over entries are made in the logistics package
Wherever there are partial receipts, only pending quantity will be handled in the system
If item wise cost details are not available in the legacy system, they will be pro-rated as per the weight of the item
All transactions created in the legacy system will be closed in the legacy system, unless specifically addressed
For goods already despatched/sent to site dummy entries will have to be made in the Maintain Costs session in Tp and in Material Budget Detail Line in Element Budget.Based on the decision taken by TBW, one entry will be done per Project/SA Level/Despatchable Unit

## Slide 58: Assumptions for Stock taking
All items lying in stock will have to have tag as per the new item code
Raw Material issued against a work order and lying in the shop floor should not be considered while taking stock
Items not having a code in Baan will be issued on an MR to Shop Floor prior to stock taking
There should be no item completed/received whose inspection is pending
Items which have been rejected and not returned to supplier will not be considered
New Lot codes will be used for entering item stock