TRANSITION PLAN

Draft

The planned date for going live on Baan is June 2.  ‘Going Live’ means the application will be ready for use by  June 2nd for entering that day’s transactions. All opening balances and open  entries will be entered by June 2nd,during  the period between 24th May and 1st June when the plant is likely to be closed for Maintenance.

This document presents in detail as to what procedures to be followed to cut over to the new system. For this purpose, three transition periods have been defined:

- April & May and just around 22nd  - Transition Period 1

- 23rd May to 1st June - Transition Period 2 and

- After 2nd June - Transition Period 3

For each transition period, the cut over plan is given in two sections viz., Logistics and Finance.  Logistics covers Distribution and Manufacturing areas and Finance covers core Finance, Costing and Statutory areas. The scope of this document is restricted to Direct Material processes only.  Indirect Material processes are expected go live from April 1st, 1998 and transition of IDM is described in a separate document.

Procedures to be followed during April & May and just around May 22nd  - Transition Period 1

During this period, the objective will be to follow procedures which can simplify transfer of data to the new system, minimise the no. of transactions and also close all open transactions by May 23rd to the extent possible.

LOGISTICS

Sales

- No restriction on entering sales orders.

- No restriction on Sales Quotations. If the response from customer comes before 22nd , same will be entered in Unify. If the response does not come, the sales quotation will be entered in Baan with a reference to the old Quotation number during Transition Period 2.

Purchase

- Make all contracts with suppliers  for a period of 3 months April, May and June. While the rate may be fixed for the year, the quantities will be specified only the first three months. Check whether the material can be procured from minimum no. of vendors.

- No restriction on Purchase Orders.

- No restriction on Purchase Inquiry. If the responses come before 23rd, same will be entered in Unify.

Material Inward

- Clear all material in Goods Inward stores and Inspection stores by 22nd. Transfer all material to the respective warehouses.

- For material rejected ??????????

Production

- Complete / Close production orders to the extent possible and transfer material to Sales Warehouse. Short close production orders if required.

Sales Warehouse

- Despatch material for which DA’s  have been generated. Do not hold open DA’s.

Warehouse

Warehouse Transfers

- Complete all transfers by May 22nd .

Planning

- Run MRP in Unify latest by on 22nd  and release all schedules to the suppliers by 22nd for supplies to be made in June.  The schedules can have tentative schedules for the month of July and August as per the current practice. MRP should be run after closing all open transactions wherever possible.

- The suppliers will be informed that there will be new contracts effective July 1st and they will have to supply as per the new contract from July 1st quoting the new contract number.

FINANCE

Suppliers

- Book Bills, including Debit Notes and Credit Notes  of April & May Unify

- Make payments for these bills form of advance payments in Unify.

Customers

- Sales Invoices will be booked in Unify for April & May.

- Receipts will be taken as advances without assigning to invoices.

Procedures to be followed during the period 23rd May to 1st June - Transition Period 2

The objective during this period will be to enter all open transactions into Baan. Enter only summary transactions wherever possible.

LOGISTICS

Opening Balances Entries

Inventory by Warehouse / Location

- The inventory by warehouse/location will be entered as per the closing balance as on May 23rd, 1998. There will be no physical verification as on May 23rd. The book balances will be the basis for entering stock balances.

- Construct a mapping  between the legacy warehouses / locations (including Pune warehouse and sub contractors warehouses) and Baan warehouses and locations. The balances will be entered as per the mapping.

- Sub Contractors will be asked to provide the inventory in their respective warehouses as on May 23rd, which will also be entered in the respective sub-contractors warehouse.

WIP

- Ignore

Transactions

Sales

- Sale Order for which deliveries have not taken place will be entered in Baan.  However, these orders should not affect the Production Plan.  As MRP is generated and production orders prepared around 23rd, there will be no sales order for which production order is not prepared.

Procurement

Supply Chain Purchase Contracts

- Supply Chain Purchase Contracts will be made effective only from July 1998. These contracts will be prepared in June ’98 and schedules given to the suppliers based on the MRP run around 27th June. Hence no action during this period. (ALL OPEN CONTRACTS TO BE ENTERED AS NORMAL CONTRACTS OR SUPPLY CHAIN CONTRACTS - CHECK WITH DSITRIBUTION)

Purchase Contracts

- All open purchase contracts will be entered in Baan.  Open contracts means all contracts  for which material are still to be received or received and waiting at the GRN stores for inspection.  However, the data to be entered in Baan for these purchase contracts will be only those part of the contract for which material are yet to be received.

Purchase Orders

- All open purchase orders will be entered in the system in the same way as purchase contracts.

Purchase Inquiries

- Enter all Purchase Inquiries for which responses have not come from the vendors. Inquiries for which responses have come but PO not raised, enter manual PO in Baan. If PO has already been raised and material not received, follow the procedure for Purchase Orders explained above.

Material Inward

GRNs

- All GRNs for which inspection not carried out will be entered in Baan.

Material Rejected

- For material rejected ????X??xx

Production

Production Orders

- All open production orders, orders for which TNW is not raised, will be entered as manual production orders into the system.  The old production order number will be mentioned as reference in the new production order. Material issues for these production orders will be recorded using Estimated Material Issues session, with backflush ‘No’.

Sales Warehouse

Delivery Advice

- All delivery advices for which material have not been sent out

Warehouse

Inventory Transfers

- Enter all Inventory Transfer transactions for which transfers not complete and material is in transit.

FINANCE

Opening Balances

- The following balances as on 23rd May 1998 (considered same as 31st May 1998) will be entered in Baan latest by June 1st , 1998. The balances pertain to all three divisions viz., Brakes, Kit and Foundry.

- Cash

- Bank (as per SCL - unreconciled)

- PLA

- RG23A

- RG23C

- Closing Stock

- Item wise Direct Material

- Item wise IDM

- Standards Updates

- Itemwise RG1

- Itemwise Pune Stock

- Suspense Account

Transactions

Creditors

- Bills and Advance Payments will be transferred to Baan by May 23rd.

- Need to decide how to handle TDS

Debtors

- Sales Invoices and Receipts will be transferred to Baan by May 23rd.

Fixed Assets

- Book all FA to 507 Account

Stock Balances

- Stock balances (incl. RG1 balances ) will be updated into Baan by 25th May from Finance Database.

Procedure to be followed after June 2nd and before June 31st - Transition Period 3

The objective during this period will be to complete planning ‘runs’ and to reconcile the open transactions.

LOGISTICS

- Prepare fresh contracts with suppliers. (Supply chain contracts)

- Plan to run the first MPS/MRP around 27th June.

- Communicate the new schedule to all the suppliers before 31st June.

FINANCE

- Match the advance payments to suppliers to the bills

- Match the advance receipts from customers to invoices.