## Sheet1
Cut Over Plan |  |  |  | 1999-07-24
Sr | Description
No
1 | MM Inventory on Hand | RMINV | Hold over | Component stores | Tool stores & Maintenance stores in shops
| Inventory adjustments available only for standard items. Hence all items to be brought in only as standard items and then converted to customised items. Alternative suggested by Vikas is to make dummy POs for customised items amd Maintain receipts for them. | Inv transactions (SBU wise splitup): Qty, Value, Physical stock, Location, Lot creation with features. Import/ Local job items, Welding consumables | Closed projects, NTUJ to be entered as Standard items, to ascertain realisable value and to obtain auditors clearance. Live projects (not issued physically) in Finance will be WIP. Items not fitting our codification logic needs to be blocked for future purchases. LPG inventory to be recorded based on meter reading once in a month. | Closed projects, NTUJ to be entered as Standard items, to ascertain realisable value and to obtain auditors clearance. Live projects (not issued physically) in Finance will be WIP. Items not fitting our codification logic needs to be blocked for future purchases. LPG inventory to be recorded based on meter reading once in a month. | FOS items
2 | Imports | GIT | BOND | Warehouse
| Separate accounts for Imports and Local for Raw materials, Components, Consumables | FPOs to be entered for pending quantities. Reversing entry will be passed in Finance at values computed for all these consignments. | FPOs to be entered for pending quantities. Reversing entry will be passed in Finance at values computed for all these consignments. | Inventory adjustment transactions
3 | Purchase Orders | Qty fully delivered but not paid in old system | Qty partly delivered (lines or all) a) Not paid for delivery b) Paid for delivery | Full qty balance to be delivered
| Truth table giving details of old PO vs new PO to be made & given to all concerned. PO lines to be made as per new item codes. | Receipts matching and approvals in old system, Creation of liability and payment in new system. | a) Create PO only for balance qty delivery in BaaN Receipts matching and approvals in old system, Creation of liability and payment in new system. b) Create PO only for balance qty delivery in BaaN | Create PO in BaaN with new number By respective purchase depts or by data entry operators? What if advances are paid?
4 | Sales order: On hand contract note | Full quantity to be despatched a) Advance received - Part b) Advance received - Full | Part qty despatched & invoiced a) Advance: Part/full received b) Outstanding part/ full received | Full qty despatched but outstanding on hand
|  | Create SO with lines, cretae projects | SO to be created for balance despatchable items, with Project creation, etc. | Only open entries for outstanding invoices to be created
5 | FG Inventory | UE Orders | Gr II Project orders
| Which Valuation: a) TP b) Accounts | Inventory adjustments: Standard items to be brought in and converted to customised items where necessary |  | RG-1 should be updated with BaaN identified quantities instead of # Totals. Team to work on this.
6 | BOM Flat/Hierarchical? | Jobs completed: Not to be brought in BaaN | Jobs on Hand WIP cost shall be captured against which cost price components? For such jobs, costing analysis will not be as detailed as totally new jobs put in BaaN.
| Remark: In order to incorporate PWAR in the system, this will be entered as Simulated Price which will be set as First priority in the Cost price calculation code. |  | Jobs recd, No matl ordered, CRS made/ awaited | CRS made, some ordering has taken place | BOM stage, CRS ordered, some of the balance material ordered | FIM jobs
|  |  | Create full CRS onwards | 1. Item definition 2. Enter already released POs into BaaN 3. Create CRS 4. Run PRP. | 1. Item definition 2. Enter POs for balance qty 3. Copy std item inventory to Project 4. Enter BOM | No BOM in BaaN for FIM materials.
7 | Production orders | WIP Jobs |  | Jobs not started | Jobs getting closed by end Dec 99
| SBU-3 jobs to be reviewed in details with RDM/HNS | Jobs getting closed by Dec 99 | Jobs just started on the shop floor | Complete cycle to be followed. Full routings for startup. | Despatchable items to be defined, and items yet to be issued will be included in BOM. One line routings workcenterwise.
A) Sample BOM 1. Heat exch: TOP, Shell, Channel, Tube bundle, Loose, Spares, WMR 2. Column: TOP, Sections, Internals/Externals, Nozzles, D'end assly, …… B) Stores to update stock status wrt Issues actually made, pending MRs to be forwarded to Inventory cell, Inv cell to update all MRs into system |  |  | 1. Hier BOM to be made (Few mfd items, max 3 levels) 2. Issues: a) Coded items: Corelate with estimated materials, Make projectwise dummy items reflecting entire cost of coded items for this project. Already issued items to be deleted from Maintain estimated materials. By Shop planning/progress. b) Bought outs: i) Items physically in stores: Generate Projectwise printouts giving Prodn order, Mfd item, Qty and reference to PO & GRN no. Physical stock verification to be done. OIL printouts to be verified. Items lying in stores to be issued should be taken into Project stock and issued through Outbound. Balance allocations to be covered thru outbound generation. ii) Items in shops: Items already issued should be deleted from estimated materials by shop planning/progress.
8 | Routings | Workcenterwise routing for startup
9 | Hours accounting Attendance records corelated in TMS? | 1. Budget/ Actual HRS comparison: Estimate data will be entered by Works A/c. 2. Projetcwise dummy production order will be made & workcenterwise cumulative hours booked so far will be uploaded using new TMS system. ??? 3. Trainee hours: New TMS will convert for utilisation purpose..
10 | WIP | Generally covered based on above. WIP interest??
11 | Supplier advances Customer advances
12 | Outstanding: Orderwise Milestonewise
13 | Current assets | OB independently in Finance
14 | Liabilities | OB independently in Finance
15 | Fixed assets | Existing team to physically verify and create new Fixed assets codes.